## PROJECT
RESERVES:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR | 91098.34
| FUNDING |  | LRBFY2020 |  |  |  | DESIGN | 180418.93
| STATE RISK NUMBER | [5 empty] | INSPECTION/INSURANCE/DFCM MNGT/COMMISSIONING | 79808.11
| PROJECT TITLE |  | NEW WEST VALLEY CITY ABC STORE RELOCATION |  |  |  | PROPERTY/FFE/INFO TECH/ARTS | 288705.32
| PROJECT # |  | 20387030 | CLOSED |  |  | CONTINGENCY/LEGAL | 292164.37
| CODING BLOCK |  | 3250-300-3229-FVZ-20387030 |  |  | 133.89 | TOTAL | 932195.07 | -932195.07
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
YR | CURRENT TOTALS |  | 6154562.3 | 133.89 | 6154428.41 | 6154562.3 | 0 | 0 |  |  | 0 | 0 |  |  | BOND REQ | BOND TOTAL | BOND DRAW TOTAL
[11 empty] | 0 | 0 |  |  | 7000000 | 6154562.3 | -792894.7
|  |  |  | 0 |  | 0 | 0
FY'20 |  |  |  | 0 |  | 0 | 0
2019-11-07 | INTEGRA REALTY RESOURCES GAX 20C5*1207 | DF |  | 0 | 3000 | 3000 | 0 |  |  | 6861
2020-01-06 | FRANK N MURDOCK JR GAX 20C5*1711 | DF |  | 0 | 3000 | 3000 | 0 |  |  | 6861
2020-02-20 | MERIDIAN ENGINEERING GAX 20C5*2067 | DF |  | 0 | 5575 | 5575 | 0 |  |  | 6855
2020-04-03 | JVDP 20TA*047 WVC BOND PROCEEDS | DF | 7000000 | 7000000 |  | 0 | 7000000 |  |  | 4776
2020-05-01 | MERIDIAN TITLE COMPANY - PROPERTY PURCHASE | N/A |  | 0 |  | 2550000 | 0 |  | 2070420
2020-05-14 | MERIDIAN TITLE COMPANY AMD 001 | CO |  | 0 |  | 540 | 0 |  | 2070420
2020-05-14 | MERIDIAN ENGINEERING GAX 205*2964 | DF |  | 0 | 5870 | 5870 | 0 |  |  | 6901
2020-05-15 | MERIDIAN TITLE CO GAX 20C5*2969 | DF |  | 0 | 2550000 | 0 | 0 |  | 2070420 | 6855
2020-05-21 | MERIDIAN TITLE CO GAX 20C5*3051 | DF |  | 0 | 540 | 0 | 0 |  | 2070420 | 6855
2020-05-18 | JVDP 20TA*056 WVC BOND PROCEEDS | DF | 1594.37 | 1594.37 |  | 0 | 1594.37 |  |  | 2603
2020-06-20 | JVDP 20TA*060 WVC BOND PROCEEDS | DW | 8286.09 | 8286.09 |  | 0 | 8286.09
13/20 | JVDP 20TA*064 WVC BOND PROCEEDS | PG | 7112.69 | 7112.69 |  | 0 | 7112.69
13/20 | JVYE05020AR*002 20 WVC INTEREST | NP | 5469.16 | 5469.16 |  | 0 | 5469.16 |  |  | 2603
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'21 |  |  |  | 0 |  | 0 | 0
2020-07-30 | JACOBY ARCHITECTS - CONTRACT | N/A |  | 0 |  | 238775 | 0 |  | 2170549
2020-08-04 | ROBERT JACOBY GAX 21C5*079 | DF |  | 0 | 10500 | 0 | 0 |  | 2070549 | 6861
2020-09-08 | ROBERT JACOBY GAX 21C8*034 | DF |  | 0 | 25977.5 | 0 | 0 |  | 2170549 | 6861
2020-09-01 | JVDP 21TA*0012 WVC PROJ INT | DF | 4415.99 | 4415.99 |  | 0 | 4415.99 |  |  | 2603
2020-10-14 | ROBERT JACOBY GAX 21C7*246 | DF |  | 0 | 39187.5 | 0 | 0 |  | 2170549 | 6861
2020-10-19 | JVDP 21TA*0015 WVC PROJ INT | DF | 3302.42 | 3302.42 |  | 0 | 3302.42 |  |  | 2603
2020-11-13 | ROBERT JACOBY GAX 21C7*462 | DF |  | 0 | 26693 | 0 | 0 |  | 2170549 | 6861
2020-11-24 | MORRISON HERSHFIELD CORPORATION - CONTRACT | N/A |  | 0 |  | 15000 | 0 |  | 2170829
2020-12-20 | ETC GROUP INC- COMMISSIONING | N/A |  | 0 |  | 30000 | 0 |  | 2170777
2020-11-13 | JVDP 21TA*0016 WVC PROJ INT | DF | 3062.51 | 3062.51 |  | 0 | 3062.51 |  |  | 2603
2020-12-14 | ROBERT JACOBY GAX 21C5*1065 | DF |  | 0 | 27972 | 0 | 0 |  | 2170549 | 6861
2020-12-28 | MERIDIAN ENG GAX F20*106 | DF |  | 0 | 2750 | 2750 | 0 |  |  | 6855 |  |  |  | BOND REQ #1 | 2701065 | 2701065 | 2701065
2020-12-07 | JVDP 21TA*0020 WVC PROJ INT REV | DF | 3100.12 | 3100.12 |  | 0 | 3100.12 |  |  | 2603
2021-01-08 | ROBERT JACOBY GAX 21C8*303 | DF |  | 0 | 17010.5 | 0 | 0 |  | 2170549 | 6861
2021-01-15 | JVDP 21TA*0024 WVC PROJ INT REV | DF | 2999 | 2999 |  | 0 | 2999 |  |  | 2602
2021-02-11 | ROBERT JACOBY GAX 21C5*1540 | DF |  | 0 | 22617.5 | 0 | 0 |  | 2170549 | 6861
2021-02-19 | ETC GROUP LLC GAX 21C7*996 | DF |  | 0 | 3000 | 0 | 0 |  | 2170777 | 6873
2021-02-10 | JVDP 21TA*0029 WVC PROJ INT REV | DF | 2926.49 | 2926.49 |  | 0 | 2926.49 |  |  | 2603
2021-03-10 | ROBERT JACOBY GAX 21C5*1716 | DF |  | 0 | 9791 | 0 | 0 |  | 2170549 | 6861
2021-03-04 | ITA 30 21*049 % OF THE ARTS | DF |  | 0 | 41859 | 41859 | 0 |  |  | 6284
2021-03-18 | WC3 GAX 21C5*1759 | DF |  | 0 | 550 | 550 | 0 |  |  | 6861
2021-03-24 | ETC GROUP GAX 21C5*1789 | DF |  | 0 | 1500 | 0 | 0 |  | 2170777 | 6873
2021-03-24 | MORRISON HERSHFIELD CORP GAX 21C5*1790 | DF |  | 0 | 1000 | 0 | 0 |  | 2170829 | 6873
2021-03-24 | MORRISON HERSHFIELD CORP GAX 21C5*1791 | DF |  | 0 | 750 | 0 | 0 |  | 2170829 | 6873
2021-03-29 | MORRISON HERSHFIELD CORP GAX 21C5*1831 | DF |  | 0 | 2000 | 0 | 0 |  | 2170829 | 6873
2021-03-29 | MORRISON HERSHFIELD CORP GAX 21C5*1832 | DF |  | 0 | 750 | 0 | 0 |  | 2170829 | 6873
2021-03-31 | ETC GROUP LLC GAX 21C5*1861 | DF |  | 0 | 2250 | 0 | 0 |  | 2170777 | 6873
2021-03-05 | JVDP 21TA*0034 WVC PROJ INT REV | DF | 1967.1 | 1967.1 |  | 0 | 1967.1 |  |  | 2603
2021-04-06 | KELLER CONSTRUCTION INC. - CONTRACT | N/A |  | 0 |  | 2894000 | 0 |  | 2175404
2021-04-08 | ROBERT JACOBY GAX 21C5*1924 | DF |  | 0 | 8991 | 0 | 0 |  | 2170549 | 6861
2021-04-09 | SUNRISE ENGINEERING, INC. - CONTRACT | N/A |  | 0 |  | 31000 | 0 |  | 2171116
2021-04-08 | JVDP 21TA*038 WVC PROJ INT REV | DF | 1493.51 | 1493.51 |  | 0 | 1493.51 |  |  | 2603
2021-05-11 | ROBERT JACOBY GAX 21C7*1479 | DF |  | 0 | 1998 | 0 | 0 |  | 2170549 | 6861
2021-05-13 | ARBOR GARDNER HIGHBURY GAX 21C7*1491 | DF |  | 0 | 1116.62 | 1116.62 | 0 |  |  | 6811 |  |  |  | BOND REQ #2 | 115183.62 | 115183.62 | 115183.62
2021-05-25 | QUESTAR GAS GAX 21C9*025 | DF |  | 0 | 300 | 300 | 0 |  |  | 6811
2021-05-19 | JACOBY ARCHITECTS AMD 002 | CO |  | 0 |  | 1552.5 | 0 |  | 2170549
2021-06-01 | UT ST FIRE MRSHLS OFFC GAX 21C5*2279 | DF |  | 0 | 298.65 | 298.65 | 0 |  |  | 6861
2021-06-09 | JACOBY ARCHITECTS AMD 003 | CO |  | 0 |  | 3671 | 0 |  | 2170549
2021-05-10 | JVDP 21TA*045 WVC PROJ INT REV | DF | 1568.8 | 1568.8 |  | 0 | 1568.8 |  |  | 2603
2021-06-07 | ROBERT JACOBY GAX 21C9*316 | NP |  | 0 | 7546.5 | 0 | 0 |  | 2170549 | 6861
2021-06-08 | SUNRISE ENG GAX 21C9*322 | NP |  | 0 | 678.16 | 0 | 0 |  | 2171116 | 6873
2021-06-09 | ZIONS/KELLER CONST RTNG GAX 21C7*1624 | NP |  | 0 | 16062.5 | 0 | 0 |  | 2175404 | 6811
2021-06-09 | KELLER CONST GAX 21C7*1625 | NP |  | 0 | 305187.5 | 0 | 0 |  | 2175404 | 6811
2021-06-25 | COFC INSURANCE ITA 2*074 | NP |  | 0 | 1533.82 | 1533.82 | 0 |  |  | 6872 |  |  |  | BOND REQ #3 | 331607.13 | 331607.13 | 331607.13
2021-06-24 | ZIONS/KELLER CONST RTNG GAX 21C7*1691 | NP |  | 0 | 23140 | 0 | 0 |  | 2175404 | 6811
2021-06-24 | KELLER CONST GAX 21C7*1692 | NP |  | 0 | 439660 | 0 | 0 |  | 2175404 | 6811
2020-08-05 | JVYE0502008050006 WV ABC INTEREST | NP | 5469.16 | 5469.16 |  | 0 | 5469.16
2020-09-01 | JVDP05021TA*008 WV ABC INTEREST | NP | -5469.16 | -5469.16 |  | 0 | -5469.16 |  |  | 2603
2021-06-04 | JVDP05021TA*049 ABC WV INTEREST | NP | 1506.17 | 1506.17 |  | 0 | 1506.17
13/21 | ROBERT JACOBY GAX 21C7*1786 | NP |  | 0 | 8628.7 | 0 | 0 |  | 2170549 | 6861
13/21 | SUNRISE ENG GAX 21C9*772 | NP |  | 0 | 2196.2 | 0 | 0 |  | 2171116 | 6873
13/21 | ETC GROUP GAX 21C9*797 | NP |  | 0 | 2070 | 0 | 0 |  | 2170777 | 6873
13/21 | ETC GROUP GAX 21C9*798 | NP |  | 0 | 2020 | 0 | 0 |  | 2170777 | 6873
13/21 | ETC GROUP GAX 21C9*835 | NP |  | 0 | 2300 | 0 | 0 |  | 2170777 | 6873
13/21 | SUNRISE ENG GAX 21C9*887 | NP |  | 0 | 1878.1 | 0 | 0 |  | 2171116 | 6873
13/21 | MORRISON HERSHFIELD CORP GAX 21C7*1905 | NP |  | 0 | 1000 | 0 | 0 |  | 2170829 | 6873
13/21 | UTAH STATE FIRE MARSHALS GAX 21C5-2498 | NP |  | 0 | 298.65 | 298.65 | 0 |  |  | 6861
13/21 | ZIONS/KELLER CONST RTNG GAX 21C5*2538 | NP |  | 0 | 8585 | 0 | 0 |  | 2175404 | 6811
13/21 | KELLER CONST GAX 21C5*2539 | NP |  | 0 | 163115 | 0 | 0 |  | 2175404 | 6811
13-21 | JVYE05021AR000001 - INTEREST EARNINGS | NP | 1272.22 | 1272.22 |  | 0 | 1272.22 |  |  | 2603
13/21 | JVDP 050 21TA *063 | NP | 1478.82 | 1478.82 |  | 0 | 1478.82 |  |  | 2603
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'22 |  |  |  | 0 |  | 0 | 0
2021-08-17 | ROBERT JACOBY GAX 22C9*122 | DF |  | 0 | 5194.8 | 0 | 0 |  | 2170549 | 6861
2021-08-23 | ZIONS/KELLER CONST RTNG GAX 22C7*057 | DF |  | 0 | 15354 | 0 | 0 |  | 2175404 | 6811
2021-08-23 | KELLER CONST GAX 22C7*058 | DF |  | 0 | 291726 | 0 | 0 |  | 2175404 | 6811
2021-09-07 | ROBERT JACOBY GAX 22C9*202 | DF |  | 0 | 5831.5 | 0 | 0 |  | 2170549 | 6861
2021-08-12 | JVDP22TA*004 DABC WVC PROJ INTEREST | DF | 1272.22 | 1272.22 |  | 0 | 1272.22 |  |  | 2603
2021-09-20 | WC3 GAX 22C5*226 | DF |  | 0 | 110 | 110 | 0 |  |  | 6861
2021-09-28 | ETC GROUP GAX FC20210927174 | DF |  | 0 | 1200 | 0 | 0 |  | 2170777 | 6873
2021-09-29 | MORRISON HERSHFIELD GAX FC20210928242 | DF |  | 0 | 2092.5 | 0 | 0 |  | 2170829 | 6873
2021-09-29 | ETC GROUP GAX FC20210928280 | DF |  | 0 | 720 | 0 | 0 |  | 2170777 | 6873
2021-09-29 | MORRISON HERSHFIELD GAX FC20210928286 | DF |  | 0 | 1390 | 0 | 0 |  | 2170829 | 6873
2021-10-01 | IDT PRJ MANAGER FEES | DF |  | 0 | 32500 | 32500 | 0 |  |  | 6865
2021-09-08 | JVYE2108050007 DABC WVC PROJ INTEREST | DF | -1272.22 | -1272.22 |  | 0 | -1272.22 |  |  | 2603
2021-09-09 | JVDP22TA000009 DABC WVC PROJ INTEREST | DF | 1194.24 | 1194.24 |  | 0 | 1194.24 |  |  | 2603
2021-10-06 | SUNRISE ENG GAX FC20211006556 | DF |  | 0 | 3252.55 | 0 | 0 |  | 2171116 | 6873
2021-10-06 | SUNRISE ENG GAX FC20211006567 | DF |  | 0 | 382.46 | 0 | 0 |  | 2171116 | 6873
2021-10-20 | KELLER CONST GAX FC20211020829 | DF |  | 0 | 255409.4 | 0 | 0 |  | 2175404 | 6811
2021-10-20 | ZIONS/KELLER CONST RTNG GAX FC20211020830 | DF |  | 0 | 13442.6 | 0 | 0 |  | 2175404 | 6811
2021-10-20 | ROBERT JACOBY GAX FC20211020816 | DF |  | 0 | 3996 | 0 | 0 |  | 2170549 | 6861
2021-10-27 | KELLER CONST GAX FC20211027949 | DF |  | 0 | 256466.75 | 0 | 0 |  | 2175404 | 6811
2021-10-27 | ZIONS/KELLER CONST RTNG GAX FC20211027950 | DF |  | 0 | 13498.25 | 0 | 0 |  | 2175404 | 6811
2021-11-08 | SUNRISE ENG GAX FC202111081221 | DF |  | 0 | 425.38 | 0 | 0 |  | 2171116 | 6873
2021-11-09 | MORRISON HERSHFIELD GAX FC202111091324 | DF |  | 0 | 500 | 0 | 0 |  | 2170829 | 6873
2021-10-08 | JVDP 22TA*014 RECORD DABC WVC PROJ INT | DF | 1088.98 | 1088.98 |  | 0 | 1088.98 |  |  | 2603
2021-11-10 | UT ST FIRE MARSHAL GAX 22C5*245 | DF |  | 0 | 298.65 | 298.65 | 0 |  |  | 6861
2021-11-24 | JVDP22TA*0018 RECORD DABC WVC PROJ INT | DF | 1023.22 | 1023.22 |  | 0 | 1023.22 |  |  | 2603
2021-11-29 | WC3 GAX 22C5*259 | DF |  | 0 | 220 | 220 | 0 |  |  | 6861
2021-12-03 | JVDP05022TA000021 RECORD DABC WVC PROJ INT | DF | 1099.25 | 1099.25 |  | 0 | 1099.25 |  |  | 2603
2021-12-03 | SUNRISE ENG GAX FC202112031707 | DF |  | 0 | 152.18 | 0 | 0 |  | 2171116 | 6873
2021-12-07 | ROBERT JACOBY AX FC202112071773 | DF |  | 0 | 11121 | 0 | 0 |  | 2170549 | 6861
2021-12-07 | KELLER CONST GAX FC202112071797 | DF |  | 0 | 607040.8 | 0 | 0 |  | 2175404 | 6811
2021-12-07 | KELLER CONST GAX FX202112131931 | DF |  | 0 | 31949.52 | 0 | 0 |  | 2070407 | 6861
2021-11-03 | ROBERT JACOBY GAX FC202111031089 | DF |  | 0 | 3996 | 0 | 0 |  | 2170549 | 6861
2021-12-20 | WC3 GAX 22C5*281 | DF |  | 0 | 110 | 110 | 0 |  |  | 6861
2021-12-29 | MORRISON HERSHFIELD GAX FC202112292194 | DF |  | 0 | 2500 | 0 | 0 |  | 2170829 | 6873 |  |  |  | BOND REQ #4 | 2270461.99 | 2270461.99 | 2270461.99
2021-12-30 | JVDP05022TA000026 RECORD DABC WVC PROJ INT | DF | 1116.36 | 1116.36 |  | 0 | 1116.36 |  |  | 2603
2022-01-07 | SUNRISE ENG GAX FC202201072378 | DF |  | 0 | 203.6 | 0 | 0 |  | 2171116 | 6873
2022-01-18 | ROBERT JACOBY GAX FC202201182531 | DF |  | 0 | 3423 | 0 | 0 |  | 2170549 | 6861
2022-01-24 | IET1102207B0240000070 PRC AMER TECH | DF |  | 0 | 11590.36 | 11590.36 | 0 |  |  | 6481
2022-01-25 | SUNRISE ENG GAX FC202201252652 | DF |  | 0 | 272.9 | 0 | 0 |  | 2171116 | 6873
2022-02-02 | MORRISON HERSHFIELD GAX FC202202022850 | DF |  | 0 | 1517.5 | 0 | 0 |  | 2170829 | 6873
2022-02-03 | JVDP05022TA000029 RECORD DABC WVC PROJ INT | DF | 1227.59 | 1227.59 |  | 0 | 1227.59 |  |  | 2603
2022-02-07 | MORRISON HERSHFIELD GAX FC202202072914 | DF |  | 0 | 750 | 0 | 0 |  | 2170829 | 6873
2022-03-03 | JVDP05022TA000034 DABC WVC PROJ INT | DF | 821.97 | 821.97 |  | 0 | 821.97 |  |  | 2603
2022-03-08 | SUNRISE ENG GAX FC202203083514 | DF |  | 0 | 152.18 | 0 | 0 |  | 2171116 | 6873
2022-03-15 | JVDP05022TA000036 RECORD DABC WVC PROJ INT | DF | 616.72 | 616.72 |  | 0 | 616.72 |  |  | 2603
2022-03-28 | MERIDIAN TITLE GAX 22C7*115 | DF |  | 0 | 7938 | 7938 | 0 |  |  | 6855
2022-03-29 | IET1102209B0880000095 PRC AMER TECH | DF |  | 0 | 2321.32 | 2321.32 | 0 |  |  | 6853
2022-04-04 | SUNRISE ENG GAX FC202204044003 | DF |  | 0 | 191.18 | 0 | 0 |  | 2171116 | 6873 |  |  |  | BOND REQ #5 | 28359.54 | 28359.54 | 28359.54
2022-04-19 | JVDP05022TA000041 DABC WVC PROJ INT | DF | 760.9 | 760.9 |  | 0 | 760.9 |  |  | 2603
2022-05-26 | JVDP05022TA000045 DABC WVC PROJ INT | DF | 868.12 | 868.12 |  | 0 | 868.12 |  |  | 2603
2022-06-06 | ETC GROUP GAX FC202206065547 | NP |  | 0 | 10440 | 0 | 0 |  | 2170777 | 6873
2022-06-09 | KELLER CONST CO 001 | CO |  | 0 |  | 167449.95 | 0 |  | 2175404 |  |  |  |  | BOND REQ #6 | 10440 | 10440 | 10440
2022-06-28 | JVDP05022A000053 DABC WVC PROJ INT | NP | 1144.39 | 1144.39 |  | 0 | 1144.39 |  |  | 2603
13/22 | SUNRISE ENG GAX 22C9*559 | NP |  | 0 | 152.18 | 0 | 0 |  | 2171116 | 6873
13/22 | JVYE05022AR000003 DABC WVC PROJ INT | NP | 1542.9 | 1542.9 |  | 0 | 1542.9 |  |  | 2603
13/22 | KELLER CONSTR INC - CO 002 | CO |  | 0 |  | 109540.78 | 0 |  | 2175404
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'23 |  |  |  | 0 |  | 0 | 0
2022-07-18 | SUNRISE ENG AMD 001 | CO |  | 0 |  | -21062.93 |  |  | 2171116
2022-08-08 | ETC GROUP GAX F22*034 | DF |  | 0 | 2500 | 0 | 0 |  | 2170777 | 6873
2022-08-11 | KELLER CONST GAX F22*058 | DF |  | 0 | 36571.67 | 0 | 0 |  | 2175404 | 6811
2022-07-15 | JVDP5023TA000003 RECORD DABC WVC PROJ INT | DF | 1542.9 | 1542.9 |  | 0 | 1542.9 |  |  | 2603
2022-07-15 | JVYE0502207150012 RECORD DABC WVC PROJ INT | DF | -1542.9 | -1542.9 |  | 0 | -1542.9 |  |  | 2603
2022-08-16 | KELLER CONST GAX F22*057 | DF |  | 0 | 693835.74 | 0 | 0 |  | 2175404 | 6811
2022-08-23 | JVDP05023TA000010 DABC WVC PROJ INT | DF | 2318.19 | 2318.19 |  | 0 | 2318.19 |  |  | 2603
2022-08-24 | MERIDIAN ENG GAX F22*084 | DF |  | 0 | 4880 | 4880 | 0 |  |  | 6855
2022-08-26 | KELLER CONST CO 003 | CO |  | 0 |  | 0 | 0 |  | 2175404
2022-10-05 | JVDP05023TA000015 DABC WVC PROJ INT | DF | 3127.07 | 3127.07 |  | 0 | 3127.07 |  |  | 2603
1902-10-21 | JVDP05023TA000020 DABC WVC PROJ INT | DF | 3396.56 | 3396.56 |  | 0 | 3396.56 |  |  | 2603 |  |  |  | BOND REQ #7 | 737886.09 | 737886.09 | 737886.09
2022-11-16 | JVDP05023TA000021 WVC PROJ INT | NP | 4059.66 | 4059.66 |  | 0 | 4059.66 |  |  | 2603
2022-12-01 | MORRISON HERSHFIELD GAX FC2022120111666 | NP |  | 0 | 750 | 0 | 0 |  | 2170829 | 6873
2022-12-01 | ETC GROUP GAX FC2022120111667 | NP |  | 0 | 2000 | 0 | 0 |  | 2170777 | 6873
2022-12-22 | JVDP05023TA000029 DABC WVC PROJ INT | NP | 4568.47 | 4568.47 |  | 0 | 4568.47 |  |  | 2603
2022-12-28 | HARRIS MOUNTAIN WEST, LLC - CONTRACT | N/A |  | 0 |  | 5828.93 | 0 |  | 2375324
2023-01-18 | JVDP05023TA000033 DABC WVC PROJ INT | DF | 3080.32 | 3080.32 |  | 0 | 3080.32 |  |  | 2603 | RESERVES CHECKED TO THIS POINT
2023-02-15 | JVDP05023TA000038 DABC WVC PROJ INT | DF | 3430.22 | 3430.22 |  | 0 | 3430.22 |  |  | 2603 |  |  |  | BOND REQ #8 | 2750 | 2750 | 2750
2023-03-15 | JVDP05023TA000043 DABC WVC PROJ INT | DF | 3390.89 | 3390.89 |  | 0 | 3390.89 |  |  | 2603
2023-04-19 | JVDP05023TA000049 DABC WVC PROJ INT | DF | 3874.07 | 3874.07 |  | 0 | 3874.07 |  |  | 2603
2023-05-18 | JVDP05023TA000051 DABC WVC PROJ INT | DF | 3918.26 | 3918.26 |  | 0 | 3918.26 |  |  | 2603
2023-06-14 | ROBERT JACOBY GAX FC2023061420579 | DF |  | 0 | 3523 | 0 | 0 |  | 2170549 | 6861
2023-06-15 | JVDP05023TA000057 DABC WVC PROJ INT | DF | 4110.77 | 4110.77 |  | 0 | 4110.77 |  |  | 2603
13/23 | HARRIS MTN WEST GAX FC2023070321452 | DF |  | 0 | 5828.93 | 0 | 0 |  | 2375324 | 6188
13/23 | JVYE05023AR000001 RECORD FARMINGTON PROJ INT | DF | 4085.15 | 4085.15 |  | 0 | 4085.15 |  |  | 2603
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'24 |  |  |  | 0 |  | 0 | 0
2023-07-12 | JVDP05024TA000001 RECORD DABC WVC PROJ INT | DF | 4085.15 | 4085.15 |  | 0 | 4085.15 |  |  | 2603
2023-07-20 | JVYE0502307170016 RECORD FARMINGTON PROJ INT | DF | -4085.15 | -4085.15 |  | 0 | -4085.15 |  |  | 2603
2023-08-10 | JVDP05024TA000009 RECORD WVC PROJ INT | DF | 4239.5 | 4239.5 |  | 0 | 4239.5 |  |  | 2603
2023-09-18 | JVDP05024TA000013 WVC PROJ INT | DF | 4361.18 | 4361.18 |  | 0 | 4361.18 |  |  | 2603
2023-10-10 | JVDP05024TA000018 DABC WVC PROJ INT | DF | 4342.94 | 4342.94 |  | 0 | 4342.94 |  |  | 2603 |  |  | NEED TO REQUEST | BOND REQ #9 | 9351.93 | 9351.93 | 9351.93
2023-12-04 | JVDP05024TA000026 DABC WVC PROJ INT | DF | 4508.96 | 4508.96 |  | 0 | 4508.96 |  |  | 2603
2023-12-14 | JVDP05024TA000028 DABC WVC PROJ INT | DF | 4428.17 | 4428.17 |  | 0 | 4428.17 |  |  | 2603
2024-01-16 | JVDP05024TA000032 DABC WVC PROJ INT | DF | 4586.92 | 4586.92 |  | 0 | 4586.92 |  |  | 2603
2024-02-15 | JVDP05024TA000035 DABC WVC PROJ INT | DF | 4612.95 | 4612.95 |  | 0 | 4612.95 |  |  | 2603
2024-03-11 | JVDP05024TA00040 DABC WVC PROJ INT | DF | 4334.71 | 4334.71 |  | 0 | 4334.71 |  |  | 2603
2024-03-24 | TRNSF TO 21257300 FROM 20387030 LEGAL FEES | DF |  | 0 | 2093 | 2093 | 0 |  |  | 6870
2024-04-18 | JVDP05024TA000044 DABC WVC PROJ INT | DF | 4622.44 | 4622.44 |  | 0 | 4622.44 |  |  | 2603
2022-08-11 | KELLER CONST GAX F22*058 | DF |  | 0 |  | 0 | 0 |  | 2175404 | 6811 |  | never fixed in FINET
2022-08-11 | KELLER CONST GAX F22*058 | DF |  | 0 |  | 54 | 0 |  | 2175404 | 6811 |  | TO CORRECT THE AMOUNT PAID
2024-05-22 | JVDP05024TA000053 DABC WVC PROJ INT | DF | 4496.54 | 4496.54 |  | 0 | 4496.54 |  |  | 2603
2024-06-12 | JVDP05024TA000060 DABC WVC PROJ INT |  | 4654 | 4654 |  | 0 | 4654 |  |  | 2603
13/24 | IDT 24C3* XFER WVC PRO INT FROM 19405030 |  | 4531.04 | 4531.04 |  | 0 | 4531.04 |  |  | 2603
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'25 |  |  |  | 0 |  | 0 | 0
2024-08-15 | JVA15025F000055 REVERSE DUPT JVA | DF | 1018075.71 | 1018075.71 |  | 0 | 1018075.71 |  |  | 4776
2024-07-11 | JVDP05025TA000001 DABC WVC PROJ INT | DF | 4531.04 | 4531.04 |  | 0 | 4531.04 |  |  | 2603
2024-08-15 | JVA15025F000055 REVERSE DUPT JVA | DF | -1018075.71 | -1018075.71 |  | 0 | -1018075.71 |  |  | 4776 |  |  |  | Pat emailed Diana Artica to add Project number to this transaction
2024-08-01 | JVA15025F0000028 Closeout 2020 LR W.V.C. ABC Store Project Fund (xxx8308) & Trfr remaining funds to the 2020 Bond Fun | DF | -1018075.71 | -1018075.71 |  | 0 | -1018075.71 |  |  | 4776
2024-11-15 | REV TRNSF TO 21257300 FROM 20387030 LEGAL FEES | DF | 6967.89 | 6967.89 |  |  | 6967.89 |  |  | 4737
2026-07-14 | IDT15026DP000212 Americom Refund |  |  |  | -133.89 |  |  |  |  | 6481
PROJECT CLOSED
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 20387030
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency