## PROJECT
RESERVES:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR/HAZ MAT | 12442613
| FUNDING |  | LRBFY2019$10,091,100 |  |  |  | DESIGN/PROGRAMMING | 0
| STATE RISK NUMBER | [5 empty] | PROPERTY/FFE/INFO TECH/ARTS | 484876
| PROJECT TITLE |  | SLC DOWN TOWN RELOCATION STORE |  |  |  | INSPECTION/INSURANCE/DFCM MNGT/COMMISSIONING | 194375
| PROJECT # |  | 21329030 | OPEN |  |  | CONTINGENCY/LEGAL/OTHER COSTS | 339292.03
| CODING BLOCK |  | 3250-300-3229-FVZ-21329030 |  |  | 288151.86 | TOTAL | 13461156.03 | -8179159.75
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
YR | CURRENT TOTALS |  | 16236770.78 | 5570148.14 | 10666622.64 | 10954774.5 | 5281996.28 | 0 |  |  | 0 | 0 |  |  |  | BOND REQ | BOND TOTAL | BOND DRAW TOTAL
[11 empty] | 0 | 0 |  |  |  | 10585277.56 | 16236770.78 | -7778380.01
|  |  |  | 0 |  | 0 | 0
FY'21 |  |  |  | 0 |  | 0 | 0
2020-11-09 | JACOBY ARCHITECTS, INC. - CONTRACT | N/A |  | 0 |  | 544495 | 0 |  | 2170763
2020-12-14 | ROBERT JACOBY GAX 21C5*1066 | DF |  | 0 | 18000 | 0 | 0 |  | 2170763 | 6861
2021-01-08 | ROBERT JACOBY GAX 21C8*302 | DF |  | 0 | 23358.6 | 0 | 0 |  | 2170763 | 6861
2021-02-10 | ROBERT JACOBY GAX 21C7*969 | DF |  | 0 | 78574.04 | 0 | 0 |  | 2170763 | 6861
2021-02-25 | GRIFFIN ENERG CONSULTING LLC - CONTRACT | N/A |  | 0 |  | 10990 | 0 |  | 2170997
2021-02-25 | NEDERLAND REFRIGERATION CORP dba E CUBE INC - CONTRACT | N/A |  | 0 |  | 27150 | 0 |  | 2170998
2021-02-25 | ARCHITECTURAL TESTING, INC. - CONTRACT | N/A |  | 0 |  | 17200 | 0 |  | 2170999
2021-03-10 | ROBERT JACOBY GAX 21C5*1718 | DF | 0 | 0 | 74203.1 | 0 | 0 |  | 2170763 | 6861
2021-03-04 | ITA 300 21*050 % OF ARTS | DF |  | 0 | 78643 | 78643 | 0 |  |  | 6284
2021-04-08 | ROBERT JACOBY GAX 21C5*1925 | DF |  | 0 | 73050.45 | 0 | 0 |  | 2170763 | 6861
2021-04-21 | GRIFFIN ENERG CONSULTING GAX 21C9*037 | DF |  | 0 | 2940 | 0 | 0 |  | 2170997 | 6849
2021-05-11 | ROBERT JACOBY GAX 21C7*1477 | DF |  | 0 | 79570.65 | 0 | 0 |  | 2170763 | 6861
2021-06-03 | JACOBY ARCHITECTS AMD 001 | CO |  | 0 |  | 3050 | 0 |  | 2170763
2021-06-02 | GRIFFIN ENERG CONSULTING GAX 21C9*232 | DF |  | 0 | 3290 | 0 | 0 |  | 2170997 | 6849
2021-06-02 | ARCHITECTURAL TEST GAX 21C9*237 | DF |  | 0 | 1800 | 0 | 0 |  | 2170999 | 6849
2021-06-09 | JACOBY ARCHI AMD 002 | CO |  | 0 |  | 3220 | 0 |  | 2170763
2021-06-09 | JACOBY ARCHI AMD 003 | CO |  | 0 |  | 5946.7 | 0 |  | 2170763
2021-06-07 | ROBERT JACOBY GAX 21C9*314 | NP |  | 0 | 81922.1 | 0 | 0 |  | 2170763 | 6861
13/21 | ROBERT JACOBY GAX 21C7*1777 | NP |  | 0 | 63921.3 | 0 | 0 |  | 2170763 | 6861
13/21 | ARCHITECTURAL TESTING GAX 21C9*836 | NP |  | 0 | 185 | 0 | 0 |  | 2170999 | 6849
2021-06-01 | JACOBY ARCHITECTS INC - AMD 004 | CO |  | 0 |  | 403590 | 0 |  | 2170763
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'22 |  |  |  | 0 |  | 0 | 0
2021-08-17 | ROBERT JACOBY GAX 22C9*121 | DF |  | 0 | 158389.76 | 0 | 0 |  | 2170763 | 6861
2021-09-03 | PACIFIC CORP GAX 22C5*204 | DF |  | 0 | 17004 | 17004 | 0 |  |  | 6811
2021-09-07 | ROBERT JACOBY GAX 22C9*201 | DF |  | 0 | 62678.6 | 0 | 0 |  | 2170763 | 6861
2021-09-23 | JACOBY ARCHI AMD 006 | CO |  | 0 |  | 1035 | 0 |  | 2170763
2021-09-29 | ARCHI TEST GAX FC2021GAX0928272 | DF |  | 0 | 1200 | 0 | 0 |  | 2170999 | 6849
2021-10-08 | ARCHITECTURAL TESTING AMD 001 | CO |  | 0 |  | 3000 | 0 |  | 2170999
2021-10-19 | WC3 GAC 22C5*236 | DF |  | 0 | 1650 | 1650 | 0 |  |  | 6861
2021-10-20 | ROBERT JACOBY GAX FC20211020817 | DF |  | 0 | 22356.6 | 0 | 0 |  | 2170763 | 6861
2021-08-01 | JACOBY ARCHITECTS, INC- AMD 005 | CO |  | 0 |  | 6000 | 0 |  | 2170763
2021-11-29 | WC3 GAX 22C5*259 | DF |  | 0 | 660 | 660 | 0 |  |  | 6861
2021-11-29 | NEDERLAND REF GAX FC202111291584 | DF |  | 0 | 204 | 0 | 0 |  | 2170998 | 6849
2021-11-30 | NEDERLAND REF GAX FC202111301636 | DF |  | 0 | 1506 | 0 | 0 |  | 2170998 | 6849
2021-11-30 | GRIFFIN ENERGY GAX FC202111301639 | DF |  | 0 | 4760 | 0 | 0 |  | 2170997 | 6849
2021-12-07 | UT ST FIRE MRSHL GAX 22C5*269 | DF |  | 0 | 3817.26 | 3817.26 | 0 |  |  | 6861
2021-12-20 | WC3 GAX 22C5*281 | DF |  | 0 | 110 | 110 | 0 |  |  | 6861
2022-01-03 | ARCHITECTURAL TESTING GAX FC202112302209 | DF |  | 0 | 400 | 0 | 0 |  | 2170999 | 6849
2022-01-18 | WADMAN CORP GAX FC202201182523 | DF |  | 0 | 4995 | 4995 | 0 |  |  | 6873
2022-01-18 | ROBEERT JACOBY GAX FC202201182530 | DF |  | 0 | 20059.8 | 0 | 0 |  | 21362 | 6861
2022-01-31 | NEDERLAND REF A/C GAX FC202201312776 | DF |  | 0 | 205 | 0 | 0 |  | 2170998 | 6849
2022-02-07 | ROBERT JACOBY GAX FC202202072927 | DF |  | 0 | 10029.9 | 0 | 0 |  | 2170763 | 6861
2022-02-07 | ARCHI TEXTING GAX FC202202072920 | DF |  | 0 | 210 | 0 | 0 |  | 210999 | 6849
2022-03-08 | TBSE GAX FC202203083495 | DF |  | 0 | 5000 | 5000 | 0 |  |  | 6861
2022-03-09 | CONST CONTROL GAX FC202203093541 | DF |  | 0 | 990 | 990 | 0 |  |  | 6879
2022-03-28 | CONST CONTROL GAX FC202203283853 | DF |  | 0 | 2977 | 2977 | 0 |  |  | 6879
2022-04-18 | NEDERLAND REF A/C GAX FC202204184259 | DF |  | 0 | 384.75 | 0 | 0 |  | 2170998 | 6849
2022-06-01 | PBIET100220513108520858 TARGET | DF |  | 0 | 8.07 | 8.07 | 0 |  |  | 6879
2022-06-01 | PBIET100220513108520858 CAFÉ ZUPAS | DF |  | 0 | 76.14 | 76.14 | 0 |  |  | 6879
2022-06-02 | IDT30022C3000050 PROJ MNGR FEES | DF |  |  | 42000 | 42000 | 0 |  |  | 6865
2022-06-14 | NEDERLAND REF GAX FC202206145838 | NP |  | 0 | 128.25 | 0 | 0 |  | 2170998 | 6849
2022-06-22 | ROBERT JACOBY GAX FC202206225964 | NP |  | 0 | 18793.2 | 0 | 0 |  | 2170763 | 6861
13/22 | JVDP05022TA00054 NET BOND PROCEDS DOWNTOWN | NP | 14591000 | 14591000 |  | 0 | 14591000 |  |  | 4776
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY '23 |  |  |  | 0 |  | 0 | 0
2022-08-17 | LAYTON CONSTRUCTION COMPANY LLC - CONTRACT | N/A |  | 0 |  | 40000 | 0 |  | 2270590
2022-08-18 | JVDP05023TA000007 DABC DOWNTOWN PROJ INT | DF | 3595.91 | 3595.91 |  | 0 | 3595.91 |  |  | 2603
2022-08-23 | JVDP05023TA000010 DABC DOWNTOWN PROJ INT | DF | 20361.29 | 20361.29 |  | 0 | 20361.29 |  |  | 2603
2022-08-31 | JACOBY ARCHI AMD 007 | CO |  | 0 |  | 108000 | 0 |  | 2170763
2022-10-05 | JVDP05023TA000015 DABC DOWNTOWN PROJ INT | DF | 27465.33 | 27465.33 |  |  | 27465.33 |  |  | 2603
2022-10-06 | ROBERT JACOBY GAX FC202210069297 | DF |  | 0 | 84432.6 | 0 | 0 |  | 2170763 | 6861
2022-10-20 | ARCHI TESTING GAX FC202210179599 | DF |  | 0 | 615 | 0 | 0 |  | 2170999 | 6849
2022-10-25 | JVDP05023TA000020 DABC DOWNTOWN PROJ INT | DF | 29832.94 | 29832.94 |  | 0 | 29832.94 |  |  | 2603 |  |  |  |  | BOND REQ #1 | 1045103.17 | 1045103.17 | 1045103.17
2022-11-16 | JVDP05023TA000021 DOWNTOWN PROJ INT | NP | 35657.16 | 35657.16 |  | 0 | 35657.16 |  |  | 2603
2022-12-15 | WC3 PLAN REVIEW SVCS NOV 22 | NP |  | 0 | 550 | 550 | 0 |  |  | 6861
2022-12-22 | JVDP05023TA00029 DABC DOWNTOWN PROJ INT | NP | 40628.17 | 40628.17 |  | 0 | 40628.17 |  |  | 2603
2023-01-12 | ROBERT JACOBY GAX FC2023011213538 | DF |  | 0 | 112513.15 | 0 | 0 |  | 2170763 | 6861
2023-01-13 | UT ST FIRE MARSHAL GAX 23C5*132 | DF |  | 0 | 75 | 75 | 0 |  |  | 6861
2023-01-18 | JVDP05023TA00033 DABC DOWNTOWN PROJ INT | DF | 44847.4 | 44847.4 |  | 0 | 44847.4 |  |  | 2603
2023-02-15 | JVDP05023TA00038 DABC DOWNTOWN PROJ INT | DF | 49941.54 | 49941.54 |  | 0 | 49941.54 |  |  | 2603
2023-02-21 | LAYTON CONSTRUCTION COMPANY LLC - CONTRACT | N/A |  | 0 |  | 8744377 | 0 |  | 2375361
2023-02-21 | WC3 PLAN REVIEW SERVICES JAN 23-GAX 23C5*185 | DF |  | 0 | 110 | 110 | 0 |  |  | 6861 |  |  |  |  | BOND REQ #2 | 113248.15 | 113248.15 | 113248.15
2023-03-15 | JVDP05023TA00043 DABC DOWNTOWN PROJ INT | DF | 49368.94 | 49368.94 |  | 0 | 49368.94 |  |  | 2603
2023-03-20 | NOVA GEOTECHNICAL & INSPECTION dba UNIVERSAL - CONTRACT | N/A |  | 0 |  | 31670 | 0 |  | 2370331
2023-03-30 | NEDERLAND REF A/C & HEAT GAX FC2023033016853 | DF |  | 0 | 2314 | 0 | 0 |  | 2170998 | 6849
2023-04-01 | LAYTON CONST GAX FC2023040116967 | DF |  | 0 | 111096.78 | 0 | 0 |  | 2375361 | 6811
2023-04-01 | ZIONS/LAYTON RTNG GAX FC2023040116968 | DF |  | 0 | 5847.2 | 0 | 0 |  | 2375361 | 6811
2023-04-05 | ROBERT JACOBY GAX FC2023040517161 | DF |  | 0 | 9590.3 | 0 | 0 |  | 2170763 | 6861
2023-04-10 | LAYTON CONST GAX FC2023041017331 | DF |  | 0 | 40000 | 0 | 0 |  | 2270590 | 6879
2023-04-10 | NEDERLAND REF A/C & HEAT GAX FC2023041017339 | DF |  | 0 | 445 | 0 | 0 |  | 2170998 | 6849
2023-04-19 | JVDP05023TA000049 DABC DOWNTOWN PROJ INT | DF | 56297.71 | 56297.71 |  | 0 | 56297.71 |  |  | 2603
2023-04-21 | LAYTON CONST GAX FC2023042117815 | DF |  | 0 | 745285.31 | 0 | 0 |  | 2375361 | 6811
2023-04-21 | ZIONS/LAYTON RTNG GAX FC2023042117816 | DF |  | 0 | 39225.54 | 0 | 0 |  | 2375361 | 6811
2023-04-21 | LAYTON CONST CO 001 | CO |  | 0 |  | 10222.37 | 0 |  | 2375361
2023-04-10 | ROBERT JACOBY AMD 008 | CO |  | 0 |  | 32898 | 0 |  | 2170763
2023-05-03 | ITA 300 23*062 COFC INSURANCE | DF |  | 0 | 8744.38 | 8744.38 | 0 |  |  | 6872
2023-05-08 | NOVA GEOTECH GAX FC2023050818625 | DF |  | 0 | 2689.81 | 0 | 0 |  | 2370331 | 6873
2023-05-09 | NEDERLAND REF A/C & HEAT GAX FC2023050918667 | DF |  | 0 | 267 | 0 | 0 |  | 2170998 | 6849
2023-05-09 | ROBERT JACOBY GAX FC2023050918668 | DF |  | 0 | 37693.15 | 0 | 0 |  | 2170763 | 6861
2023-05-10 | ARCHI TESTING GAX FC2023050918666 | DF |  | 0 | 1260 | 0 | 0 |  | 2170999 | 6849
2023-05-10 | LAYTON CONST GAX FC2023051018723 | DF |  | 0 | 389814.74 | 0 | 0 |  | 2375361 | 6811
2023-05-10 | ZIONS/LAYTON RTNG GAX FC2023051018724 | DF |  | 0 | 20516.57 | 0 | 0 |  | 2375361 | 6811
2023-05-18 | JVDP05023TA000051 DABC DOWNTOWN PROJ INT | DF | 56745.38 | 56745.38 |  | 0 | 56745.38 |  |  | 2603
2023-05-22 | HARRIS MOUNTAIN WEST LLC - CONTRACT | N/A |  | 0 |  | 131207.8 | 0 |  | 2375490
2023-05-31 | ARCHI TESTING GAX FC2023053019487 | DF |  | 0 | 210 | 0 | 0 |  | 2170999 | 6849 |  |  |  |  | BOND REQ#3 | 1414999.78 | 1414999.78 | 1414999.78
2023-06-12 | NOVA GEOTECH GAX FC2023061220322 | DF |  | 0 | 2041.9 | 0 | 0 |  | 2370331 | 6873
2023-06-13 | NEDERLAND REF A/C & HEAT GAX FC2023061320446 | DF |  | 0 | 339 | 0 | 0 |  | 2170998 | 6849
2023-06-14 | ROBERT JACOBY AX FC2023061420571 | DF |  | 0 | 4795.15 | 0 | 0 |  | 2170763 | 6861
2023-06-14 | LAYTON CONST GAX FC2023061420608 | DF |  | 0 | 762583.25 | 0 | 0 |  | 2375361 | 6811
2023-06-14 | ZIONS/LAYTON CONST RTNG GAX FC2023061420609 | DF |  | 0 | 40135.96 | 0 | 0 |  | 2375361 | 6811
2023-06-15 | JVDP05023TA000057 DABC DOWNTOWN PROJ INT | DF | 59533.33 | 59533.33 |  | 0 | 59533.33 |  |  | 2603
2023-06-13 | LAYTON CONST CO 002 | CO |  | 0 |  | 137583.83 | 0 |  | 2375361
13/23 | ARCHI NEXUS GAX FC2023070421477 | DF |  | 0 | 210 | 0 | 0 |  | 2170999 | 6849
13/23 | WC3 GAX 23C5*573 | DF |  | 0 | 110 | 110 | 0 |  |  | 6861
13/23 | NOVA GEOTECH GAX FC2023070621657 | DF |  | 0 | 4483.23 | 0 | 0 |  | 2370331 | 6873
13/23 | JVYE05023AR000001 RECORD FARMINGTON PROJ INT | DF | 55951.83 | 55951.83 |  | 0 | 55951.83 |  |  | 2603
13/23 | GSH MATERIALS TESTING GAX FC2023071322253 | DF |  | 0 | 2367.5 | 2367.5 | 0 |  |  | 6873
13/23 | GSH MATERIALS TESTING GAX FC2023071322255 | DF |  | 0 | 1500 | 1500 | 0 |  |  | 6873
13/23 | LAYTON CONST GAX FC2023071422473 | DF |  | 0 | 680356.57 | 0 | 0 |  | 2375361 | 6811
13/23 | ZIONS/LAYTON RTNG GAX FC2023071422474 | DF |  | 0 | 35808.24 | 0 | 0 |  | 2375361 | 6811
13/23 | ITA 300 23*091 COFC INSURANCE | DF |  | 0 | 131.21 | 131.21 | 0 |  |  | 6872
13/23 | WC3 PLAN REVIEW GAX 23C5*627 | DF |  | 0 | 220 | 220 | 0 |  |  | 6861
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'24 |  |  |  | 0 |  | 0 | 0
2023-07-12 | JVDP05024TA000001 DABC DOWNTOWN PROJ INT | DF | 55951.83 | 55951.83 |  | 0 | 55951.83 |  |  | 2603
2023-07-20 | JVYE0502307170016 DABC FARMINTON PROJ INTEREST | DF | -55951.83 | -55951.83 |  | 0 | -55951.83 |  |  | 2603
1900-01-06 16:48 | NEDERLAND REF A/C & HEAT GAX FC2023080823371 | DF |  | 0 | 623 | 0 | 0 |  | 2170998 | 6849
2023-08-08 | ROBERT JACOBY GAX FC2023080823372 | DF |  | 0 | 9590.3 | 0 | 0 |  | 2170763 | 6861
2023-08-10 | JVDP05024TA000009 DABC DOWNTOWN PROJ INT | DF | 55162.99 | 55162.99 |  | 0 | 55162.99 |  |  | 2603
2023-08-16 | LAYTON CONST GAX FC2023081623731 | DF |  | 0 | 907749.76 | 0 | 0 |  | 2375361 | 6811
2023-08-16 | ZIONS/LAYTON RTNG GAX FC2023081623732 | DF |  | 0 | 47776.3 | 0 | 0 |  | 2375361 | 6811
2023-08-31 | TRNSF TO 21329030 FROM 21136300 CD PRJ FUND CO 003 | DF | 82193.23 | 82193.23 |  | 0 | 82193.23 |  |  | 4666
2023-08-28 | LAYTON CONST CO 003 | CO |  | 0 |  | 82193.23 | 0 |  | 2375361
2023-08-30 | ARCHI TESTING GAX FC2023083024309 | DF |  | 0 | 840 | 0 | 0 |  | 2170999 | 6849
2023-09-01 | NOVA GEOTECH GAX FC2023090124421 | DF |  | 0 | 4102.15 | 0 | 0 |  | 2370331 | 6873 |  |  |  |  | BOND REQ#4 | 2505763.52 | 2505763.52 | 2505763.52
2023-08-31 | JACOBY ARCHI AMD 009 | CO |  | 0 |  | 8105 | 0 |  | 2170763
2023-09-08 | NEDELAND REF A/C & HEAT GAX FC2023090824677 | DF |  | 0 | 4155.26 | 0 | 0 |  | 2170998 | 6849
2023-09-08 | LAYTON CONST GAX FC2023090824701 | DF |  | 0 | 617304.19 | 0 | 0 |  | 2375361 | 6811
2023-09-08 | ZIONS/LAYTON RTNG GAX FC2023090824702 | DF |  | 0 | 32489.69 | 0 | 0 |  | 2375361 | 6811
2023-09-18 | JVDP05024TA000013 DOWNTOWN PROJ INT | DF | 56746.38 | 56746.38 |  | 0 | 56746.38 |  |  | 2603
2023-09-25 | ARCHI TESTING GAX FC2023092525458 | DF |  | 0 | 400 | 0 | 0 |  | 2170999 | 6849
2023-09-27 | ACTION COMPACTION EQUIPMENT CO - CONTRACT | N/A |  | 0 |  | 29965.39 | 0 |  | 2475117
2023-10-04 | NOVA GEOTECH GAX FC2023100425823 | DF |  | 0 | 4163.99 | 0 | 0 |  | 2370331 | 6873
2023-10-31 | TRNSF TO 21329030 FROM 21137300 PROJ RESV LAYTON CO 004 | DF | 25918.57 | 25918.57 |  | 0 | 25918.57 |  |  | 4666
2023-10-06 | ROBERT JACOBY GAX FC2023100626013 | DF |  | 0 | 22490.45 | 0 | 0 |  | 2170763 | 6861
2023-10-10 | JVDP05024TA000018 DABC DOWNTOWN PROJ INT | DF | 47561.01 | 47561.01 |  | 0 | 47561.01 |  |  | 2603
2023-10-04 | LAYTON CONST CO 004 | CO |  | 0 |  | 25918.57 | 0 |  | 2375361
2023-10-22 | SLCC PUBLIC UTIL GAX 150 F23*071 | DF |  | 0 | 142.25 | 142.25 | 0 |  |  | 6811
2023-10-31 | SLCC PUBLIC UTIL GAX 150 24M*427 | DF |  | 0 | 319.55 | 319.55 | 0 |  |  | 6811
2023-11-01 | ARCHI TESTING GAX FC2023110127009 | DF |  | 0 | 200 | 0 | 0 |  | 2170999 | 6849
2023-11-07 | ACTION EQPT GAX FC2023110727342 | DF |  | 0 | 14982.7 | 0 | 0 |  | 2475117 | 6832
2023-11-07 | LAYTON CONST GAX FC2023110727353 | DF |  | 0 | 575230.22 | 0 | 0 |  | 2375361 | 6811
2023-11-07 | ZIONS/LAYTON RTNG GAX FC2023110727354 | DF |  | 0 | 30275.28 | 0 | 0 |  | 2375361 | 6811
2023-11-22 | LAYTON CONST GAX FC2023112228040 | DF |  | 0 | 878047.84 | 0 | 0 |  | 2375361 | 6811
2023-11-22 | ZIONS/LAYTON RTNG GAX FC2023112228041 | DF |  | 0 | 46213.04 | 0 | 0 |  | 2375361 | 6811
2023-11-21 | NEDERLAND REF Z/C GAX FC2023112127982 | DF |  | 0 | 1243.4 | 0 | 0 |  | 2170998 | 6849
2023-11-02 | ARCHITECTURAL TESTING AMD 002 | CO |  | 0 |  | -3000 | 0 |  | 2170999
2023-11-17 | NOVA GEOTECH GAX FC2023111727843 | DF |  | 0 | 2522.46 | 0 | 0 |  | 2370331 | 6873
2023-11-17 | NOVA GEOTECH GAX FC2023111727844 | DF |  | 0 | 1825.65 | 0 | 0 |  | 2370331 | 6873
2023-11-24 | ITA 24*033 PUBLIC ARTS FOR THE DABS SLC DOWNTOWN-ADD TO LAYTON | DF | 7323.93 | 7323.93 |  | 0 | 7323.93 |  |  | 4737
2023-12-01 | SLCC PUB UTIL GAX 150 24M58542 | DF |  | 0 | 6.07 | 6.07 | 0 |  |  | 6811
2023-12-01 | ARCHI TEST GAX FC2023120128409 | DF |  | 0 | 1200 | 0 | 0 |  | 2170999 | 6849
2023-12-04 | JVDP05024TA000026 DABC DOWNTOWN PROJ INT | DF | 47066.95 | 47066.95 |  | 0 | 47066.95 |  |  | 2603
2023-12-07 | LAYTON CONST CO 005 | CO |  | 0 |  | 36565.47 | 0 |  | 2375361
2023-12-14 | JVDP05024TA000028 DABC DOWNTOWN PROJ INT | DF | 46223.6 | 46223.6 |  | 0 | 46223.6 |  |  | 2603
2023-12-15 | NEDERLAND REF A/C & HEAT GAX FC2023121529122 | DF |  | 0 | 2223.5 | 0 | 0 |  | 2170998 | 6849
2023-12-19 | LAYTON CONST GAX FC2023121929296 | DF |  | 0 | 599038.09 | 0 | 0 |  | 2375361 | 6811
2023-12-19 | ZIONS/LAYTON RTNG GAX FC2023121929297 | DF |  | 0 | 31528.32 | 0 | 0 |  | 2375361 | 6811
2024-12-28 | HARRIS MTN WEST GAX FC2023122829602 | DF |  | 0 | 8025.41 | 0 | 0 |  | 2375490 | 6832
2024-12-28 | ZIONS/HARRIS RTNG GAX FC2023122829603 | DF |  | 0 | 422.39 | 0 | 0 |  | 2375490 | 6832
2024-01-02 | HARRIS MTN WEST GAX FC2024010229656 | DF |  | 0 | 63175 | 0 | 0 |  | 2375490 | 6832
2024-01-02 | ZIONS/HARRIS RTNG GAX FC2024010229657 | DF |  | 0 | 3325 | 0 | 0 |  | 2375490 | 6832
2024-01-05 | ROBERT JACOBY GAX FC2024010529950 | DF |  | 0 | 23975.75 | 0 | 0 |  | 2170763 | 6861
2024-01-05 | NEDERLAND REF A/C & HEAT GAX FC2024010529951 | DF |  | 0 | 1242.82 | 0 | 0 |  | 2170998 | 6849
2024-01-09 | CFS INVENTIONS GAX FC2024010930046 | DF |  | 0 | 7441.84 | 7441.84 | 0 |  |  | 6832
2024-01-11 | LAYTON CONST GAX FC2024011130276 | DF |  | 0 | 353735.31 | 0 | 0 |  | 2375361 | 6811
2024-01-11 | ZIONS/LAYTON RTNG GAX FC2024011130277 | DF |  | 0 | 18617.65 | 0 | 0 |  | 2375361 | 6811
2024-01-16 | JVDP05024TA000032 DABC DOWNTOWN PROJ INT | DF | 47881.95 | 47881.95 |  | 0 | 47881.95 |  |  | 2603
2024-01-18 | SLCC PUB UTIL GAX 150 24M5*722 | DF |  | 0 | 826.46 | 826.46 | 0 |  |  | 6811
2024-01-19 | NOVA GEOTECH GAX FC2024011930649 | DF |  | 0 | 1807.67 | 0 | 0 |  | 2370331 | 6873
2024-01-22 | ITA 24*053 COFC INS | DF |  | 0 | 29.97 | 29.97 | 0 |  |  | 6872
2024-02-01 | HARRIS MTN GAX FC2024020131292 | DF |  | 0 | 22158.75 | 0 | 0 |  | 2375490 | 6832
2024-02-01 | ZIONS/HARRIS RTNG GAX FC2024020131293 | DF |  | 0 | 1166.25 | 0 | 0 |  | 2375490 | 6832 |  |  |  |  | BOND REQ#5 | 3379276.15 | 3379276.15 | 3379276.15
2024-02-08 | SLCC PUB UTIL GAX 150 24M5*817 | DF |  | 0 | 216.48 | 216.48 | 0 |  |  | 6811
2024-02-09 | LAYTON CONST GAX FC2024020931683 | DF |  | 0 | 428062.81 | 0 | 0 |  | 2375361 | 6811
2024-02-09 | ZIONS/LAYTON RTNG GAX FC2024020931684 | DF |  | 0 | 22529.62 | 0 | 0 |  | 2375361 | 6811
2024-02-15 | JVDP05024TA000035 DABC DOWNTOWN PROJ INT | DF | 48152.46 | 48152.46 |  | 0 | 48152.46 |  |  | 2603
2024-02-15 | NEDERLAND REF A/C & HEAT GAX FC2024021531957 | DF |  | 0 | 1474.84 | 0 | 0 |  | 2170998 | 6849
2024-02-14 | LAYTON CONST CO 006 | CO |  | 0 |  | 15649.29 | 0 |  | 2375361
2024-02-23 | NOVA GEOTECHNICAL GAXFC2024022332348 | DF |  | 0 | 138.35 | 0 | 0 |  | 2370331 | 6873
2024-02-24 | ARCHITECTURAL TESTING GAXFC2024022732480 | DF |  | 0 | 870 | 0 | 0 |  | 2170999 | 6849
2024-03-06 | SLCC PUB UTIL GAX 150 24M5*929 | DF |  | 0 | 215.64 | 215.64 | 0 |  |  | 6811
2024-03-07 | LAYTON CONST GAX FC2024030732881 | DF |  | 0 | 344680.8 | 0 | 0 |  | 2375361 | 6811
2024-03-07 | ZIONS/LAYTON RTNG GAX FC2024030732882 | DF |  | 0 | 18141.1 | 0 | 0 |  | 2375361 | 6811
2024-03-08 | ROBERT JACOBY GAX FC2024030832902 | DF |  | 0 | 14385.45 | 0 | 0 |  | 2170763 | 6861
2024-03-11 | JVDP05024TA00040 DABC DOWNTOWN PROJ INT | DF | 33068.62 | 33068.62 |  | 0 | 33068.62 |  |  | 2603
2024-03-12 | NEDERLAND REF A/C & HEAT GAX FC2024031232997 | DF |  | 0 | 550.63 | 0 | 0 |  | 2170998 | 6849
2024-03-14 | UT ST FIRE MARSHAL GAX 24C5*228 | DF |  |  | 285.43 |  |  |  |  | 6861
2024-03-15 | HARRIS MTN WEST GAX FC2024031533234 | DF |  | 0 | 26142.75 | 0 | 0 |  | 2375490 | 6832
2024-03-15 | ZIONS/HARRIS MTN RTNG GAX FC2024031533235 | DF |  | 0 | 1375.93 | 0 | 0 |  | 2375490 | 6832
2024-03-22 | NOVA GEOTECH GAX FC2024032233606 | DF |  | 0 | 550.1 | 0 | 0 |  | 2370331 | 6873
2024-03-24 | TRNSF TO 21257300 FROM 21329030 LEGAL FEES | DF |  | 0 | 3932 | 3932 | 0 |  |  | 6870
2024-03-28 | SLCC PUB UTIL GAX 150 24M5*1059 | DF |  | 0 | 205.31 | 205.31 | 0 |  |  | 6811
2024-04-01 | IET1502409B092*110 AMER TECH L&M | DF |  |  | 34245.11 |  |  |  |  | 6853
2024-04-02 | ARCHI TEST GAX FC2024040234093 | DF |  | 0 | 2000 | 0 | 0 |  | 2170999 | 6849
2024-04-02 | ARCHI TEST GAX FC2024040234094 | DF |  | 0 | 1200 | 0 | 0 |  | 2170999 | 6849
2024-04-09 | ROBERT JACOBY GAX FC2024040934492 | DF |  | 0 | 6220.15 | 0 | 0 |  | 2170763 | 6861
2024-04-09 | NEDERLAND REF A/C & HEAT GAX FC2024040934493 | DF |  | 0 | 6378.42 | 0 | 0 |  | 2170998 | 6849
2024-04-17 | LAYTON CONST CO 007 | CO |  | 0 |  | 0.00 | 0 |  | 2375361
2024-04-17 | LAYTON CONST CO 008 | CO |  | 0 |  | 0.00 | 0 |  | 2375361 | [5 empty] | BOND REQ#6 | 913800.92 | 913800.92 | 913800.92
2024-04-18 | JVDP05024TA000044 DABC DOWNTOWN PROJ INT | DF | 32570.97 | 32570.97 |  | 0 | 32570.97 |  |  | 2603
2024-04-11 | JACOBY ARCHI AMD 010 | CO |  | 0 |  | 1100 | 0 |  | 2170763
2024-04-24 | LAYTON CONST GAX FC2024042435185 | DF |  | 0 | 323309.13 | 0 | 0 |  | 2375361 | 6811
2024-04-24 | ZIONS/LAYTON RTNG GAX FC2024042435186 | DF |  | 0 | 17016.27 | 0 | 0 |  | 2375361 | 6811
2024-04-25 | SLCC PUB UTIL GAX 150 24M5*1191 | DF |  | 0 | 269.92 | 269.92 | 0 |  |  | 6811
2024-05-02 | NOVA GEOTECH GAX FC2024050235604 | DF |  | 0 | 220 | 0 | 0 |  | 2370331 | 6873
2024-05-03 | ARCHI TESTING GAX FC2024050335667 | DF |  | 0 | 4000 | 0 | 0 |  | 2170999 | 6849
2024-05-01 | LAYTON CONST CO 009 | CO |  | 0 |  | 0.00 | 0 |  | 2375361
2024-05-06 | IET1502411B1270000091 PRC AMER M&L | DF |  | 0 | 1268.24 | 1268.24 | 0 |  |  | 6853
2024-05-09 | NEDERLAND REF A/C GAX FC2024050935946 | DF |  | 0 | 3418.28 | 0 | 0 |  | 2170998 | 6849
2024-05-20 | CFS INVENTIONS GAX FC2024052036400 | DF |  | 0 | 7190.98 | 7190.98 | 0 |  |  | 6832
2024-05-22 | LAYTON CONST GAX FC2024052236619 | DF |  | 0 | 153632.02 | 0 | 0 |  | 2375361 | 6811
2024-05-22 | ZIONS/LAYTON RTNG GAX FC2024052236620 | DF |  | 0 | 8085.9 | 0 | 0 |  | 2375361 | 6811
2024-05-22 | JVDP05024TA00053 DOWNTOWN PROJ INT | DF | 30593.08 | 30593.08 |  | 0 | 30593.08 |  |  | 2603 |  |  | Not on FP11 Rev Report, but in COGNOS
2024-05-29 | ARCHI TESTING GAX F2024052936839 | DF |  | 0 | 400 | 0 | 0 |  | 2170999 | 6849
2024-05-29 | ITA 300 24*147 DISPLAY SET UP FOR NEW ABS CONTRACT | DF |  | 0 | 57789.81 | 57789.81 | 0 |  |  | 6839
2024-06-11 | ITA 24*156 REIMB EXPENSE FOR COOLERS FOR DISPLAY | TR |  | 0 | 50807.25 | 50807.25 | 0 |  |  | 6832
2024-06-10 | LAYTON CONST CO 010 | CO |  | 0 |  | 0.00 | 0 |  | 2375361
2024-06-12 | JVDP05024TA000060 DABC DOWNTOWN PROJ INT | TR | 28573.11 | 28573.11 |  | 0 | 28573.11 |  |  | 2603
2024-06-13 | SLCC UB UTIL GAX 150 24M5*1349 | TR |  | 0 | 218.87 | 218.87 | 0 |  |  | 6811
2024-06-20 | NEDERLAND REF A/C GAX FC2024062038224 | TR |  | 0 | 46.85 | 0 | 0 |  | 2170998 | 6849
2024-06-21 | LAYTON CONST GAX FC2024062138309 | TR |  | 0 | 45474.65 | 0 | 0 |  | 2375361 | 6811
2024-06-21 | ZIONS/LAYTON RTNG GAX FC2024062138310 | TR |  | 0 | 2393.4 | 0 | 0 |  | 2375361 | 6811
2024-06-26 | 2B GAX FC2024062638542 | TR |  | 0 | 74908.84 | 74908.84 | 0 |  |  | 6855
13/24 | ACTION EQPT GAX FC2024070839410 | TR |  | 0 | 14982.69 | 0 | 0 |  | 2475117 | 6832
13/24 | HARRIS MTN WEST GAX FC2024070839411 | TR |  | 0 | 5145.5 | 0 | 0 |  | 2375490 | 6832
13/24 | ZIONS/HARRIS RTNG GAX FC2024070839412 | TR |  | 0 | 270.82 | 0 | 0 |  | 2375490 | 6832
13/24 | JVYE05024AR000002 DOWNTOWN PROJ INT | TR | 27818.88 | 27818.88 |  | 0 | 27818.88 |  |  | 2603
13/24 | LAYTON CONST GAX FC2024071539933 | TR |  | 0 | 133112.84 | 0 | 0 |  | 2375361 | 6811
13/24 | ZIONS/LAYTON RTNG GAX FC2024071539934 | TR |  | 0 | 7005.94 | 0 | 0 |  | 2375361 | 6811
13/24 | ITA 24*192 REIMB TO ABS STORE 001 FFE FUNDS | TR |  | 0 | 18731.74 | 18731.74 | 0 |  |  | 6832
13/24 | NOVA GEOTECH GAX FC2024071740089 | TR |  | 0 | 3175.49 | 0 | 0 |  | 2370331 | 6873 |  |  |  |  | BOND REQ#7 | 932875.43 | 932875.43 | 932875.43
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'25 |  |  |  | 0 |  | 0 | 0
2024-07-22 | LAYTON CONST CO 011 | CO |  | 0 |  | 0.00 | 0 |  | 2375361
2024-08-07 | LAYTON CONST CO 012 | CO |  | 0 |  | 0.00 | 0 |  | 2375361
2024-08-09 | LAYTON CONST GAX FC2024080940892 | DF |  | 0 | 195784.26 | 0 | 0 |  | 2375361 | 6811
2024-08-09 | ZIONS/LAYTON RTNG GAX FC2024080940893 | DF |  | 0 | 10304.43 | 0 | 0 |  | 2375361 | 6811
2024-07-11 | JVDP0502TA000001 DABC DOWNTOWN PROJ INT | DF | 27818.88 | 27818.88 |  | 0 | 27818.88 |  |  | 2603
2024-07-26 | JVYE0502407110026 DABC DOWNTOWN PROJ INT | DF | -27818.88 | -27818.88 |  | 0 | -27818.88 |  |  | 2603
2024-08-22 | JVDP05025TA000010 DABC DOWNTOWN PROJ INT | DF | 28830.93 | 28830.93 |  | 0 | 28830.93 |  |  | 2603
2024-09-03 | ROBERT JACOBY GAX FC2024090341880 | DF |  | 0 | 6845.15 | 0 | 0 |  | 2170763 | 6861
2024-09-18 | LAYTON CONST CO 013 | CO |  | 0 |  | -336750.52 | 0 |  | 2375361
2024-09-18 | JVDP05025TA000017 DABC DOWNTOWN PROJ INT | DF | 24635.97 | 24635.97 |  | 0 | 24635.97 |  |  | 2603
2024-10-08 | LAYTON CONST GAX FC2024100843723 | DF |  | 0 | 35672.71 | 0 | 0 |  | 2375361 | 6811
2024-10-08 | ZIONS/LAYTON RTNG GAX FC2024100843724 | DF |  | 0 | 1877.51 | 0 | 0 |  | 2375361 | 6811 |  |  |  | Adj- Off by $0.01
2024-10-08 | ITA 25*016 | DF |  | 0 | 3525.78 | 3525.78 | 0 |  |  | 6811
2024-10-10 | JVDP05025TA000028 DABC DOWNTOWN PROJ INT | DF | 23587.01 | 23587.01 |  | 0 | 23587.01 |  |  | 2603 |  |  |  |  | BOND REQ#8 | 254009.85 | 254009.85 | 254009.85
2024-11-27 | JVDP05025TA000038 DABC DOWNTON PROJ INT | EH | 23163.02 | 23163.02 |  | 0 | 23163.02 |  |  | 2603
2024-12-24 | JVDP05025TA000047 DABC DOWNTOWN PROJ INT | EH | 21477.12 | 21477.12 |  | 0 | 21477.12 |  |  | 2603
2025-01-29 | RECORD DABC DOWNTOWN PROJ INTEREST | EH | -169.84 | -169.84 |  | 0 | -169.84 |  |  | 2603 |  |  | ADDED PER FP07 REV REPORT
2025-03-04 | TROMMER & ASSOCIATES INC GAX300FC2025030450288 | HH |  | 0 | 6405 | 6405 | 0 |  |  | 6879
2025-03-10 | RECORD DABC DOWNTOWN PROJ INTEREST | HH | 20933.4 | 20933.4 |  | 0 | 20933.4
2025-03-21 | JVDP05025TA000061 | HH | 20170.41 | 20170.41 |  | 0 | 20170.41 |  |  | 2603
2025-03-21 | JVDP05025TA000062 | HH | 18210.99 | 18210.99 |  | 0 | 18210.99 |  |  | 2603
2025-04-01 | JVDP05025TA000063 | HH | -13.9 | -13.9 |  | 0 | -13.9 |  |  | 2603
2025-04-15 | JVDP05025TA000065 | HH | 20052.22 | 20052.22 |  | 0 | 20052.22 |  |  | 2603
2025-04-22 | LOGAN SIMPSON DESIGN, INC. GAX300FC2025042252606 | HH |  | 0 | 1625 | 0 | 0 |  | 2570215 | 6861
2025-04-24 | MOST WANTED BUILDERS GAX300FC2025042452767 | HH |  | 0 | 18170.59 | 18170.59 | 0 |  |  | 6879
2025-05-24 | JVDP05025TA000070 Record DABC Downtown Proj Interest | HH | 19485.68 | 19485.68 |  | 0 | 19485.68 |  |  | 2603
2025-06-06 | JVDP05025TA000072 DABC DOWNTOWN PROJ INT | TR | 20142.15 | 20142.15 |  | 0 | 20142.15 |  |  | 2603 |  |  |  |  | BOND REQ#9 | 26200.59 | 26200.59 | 26200.59
13/25 | JVYE05025AR000001 Record DABC Downtown Proj Interest | HH | 19599.1 | 19599.1 |  | 0 | 19599.1 |  |  | 2603
1st year parking lot lease to be paid by bond.
FY'26
2025-07-11 | JVDP05026TA000002 Record DABC Downtown Proj Interest | HH | 19599.1 | 19599.1 |  | 0 | 19599.1 |  |  | 2603
2025-07-19 | JVYE0502507140032 Record DABC Downtown Proj Interest | HH | -19599.1 | -19599.1 |  | 0 | -19599.1 |  |  | 2603
2025-08-14 | JVDP05026TA000005 Record DABC Downtown Proj Interest | HH | 20209.3 | 20209.3 |  | 0 | 20209.3 |  |  | 2603
2025-09-13 | JVDP05026TA000009 Record DABC Downtown Proj Interest | HH | 20241.72 | 20241.72 |  | 0 | 20241.72 |  |  | 2603
2026-11-07 | JVDP05026TA000013 Record DABC Downtown Proj Interest | HH | 19299.75 | 19299.75 |  | 0 | 19299.75 |  |  | 2603
2026-12-11 | JVDP05026TA000018 Record DABC Downtown Proj Interest | HH | 19499.48 | 19499.48 |  | 0 | 19499.48 |  |  | 2603
2025-11-06 | JACOBY ARCHITECTS INC CONTRACT | CO |  | 0 |  | 3900 | 0 |  | 2670236
2025-12-12 | JVDP05026TA000025 Record DABC Downtown Proj Interest | HH | 18329.54 | 18329.54 |  | 0 | 18329.54 |  |  | 2603
2025-12-09 | 2B, LLC CONTRACT | CO |  | 0 |  | 405730.4 | 0 |  | 2670263
2025-12-17 | 2B, LLC GAX300FC2025121663451 CONTRACT 2670263-PARKING LOT SUBLEASE AGREEMENT #242431 | HH |  | 0 | 77905.2 | 0 | 0 |  | 2670263 | 6855
2026-01-10 | JVDP05026TA000028 Record DABC Downtown Proj Interest | HH | 18446.46 | 18446.46 |  | 0 | 18446.46 |  |  | 2603
2026-02-11 | LOGAN SIMPSON DESIGN, INC. GAX300FC2026021065886 CONTRACT 2570215-DABS SLC DOWNTOWN RELOCATION STORE | HH |  | 0 | 7467 | 0 | 0 |  | 2570215 | 6861
2026-02-18 | JVDP05026TA000032 Record DABC Downtown Proj Interest | HH | 17800.09 | 17800.09 |  | 0 | 17800.09 |  |  | 2603
2026-03-17 | JACOBY ARCHITECTS INC GAX300FC2026031667462 CONTRACT 2670236-DABS SLC DOWN TOWN RELOCATION STORE | HH |  | 0 | 3900 | 0 | 0 |  | 2670236 | 6861
2026-03-10 | JVDP05026TA000034 Record DABC Downtown Proj Interest | HH | 16125.43 | 16125.43 |  | 0 | 16125.43 |  |  | 2603
2026-03-20 | CR30026M5000021 HARRIS REFUND CHECK | HH |  | 0 | -64.84 | -64.84 | 0 |  |  | 6832
2026-04-03 | Harris Mountain West, LLC GAX300FC2026040268161 PO 245154-DABS SLC DOWN TOWN RELOCATION STORE #1 RETNG INTEREST | HH |  | 0 | 64.84 | 64.84 | 0 |  |  | 6811
2026-04-15 | JVDP05026TA000036 Record DABC Downtown Proj Interest | HH | 17919.04 | 17919.04 |  | 0 | 17919.04 |  |  | 2603
2026-04-22 | WEST COAST CODE CONSULTANTS INC GAX30026C2000179 Plan Review Services 02/19/2026-1st Review | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2026-05-13 | JVDP05026TA000038 Record DABC Downtown Proj Interest | HH | 17384.56 | 17384.56 |  | 0 | 17384.56 |  |  | 2603
2026-06-06 | JVDP05026TA000042 Record DABC Downtown Proj Interest | HH | 18027.61 | 18027.61 |  | 0 | 18027.61 |  |  | 2603
13/26 | JVYE05026AR000001 Record DABC Downtown Proj Interest | HH | 17650.44 | 17650.44 |  | 0 | 17650.44 |  |  | 2603
13/26 | JVDP05027TA000001 | HH | 17650.44 | 17650.44 |  | 0 | 17650.44 |  |  | 2603
13/26 | IDT15026DP000212 Americom Refund |  |  | 0 | -724.18 | -724.18 | 0 |  |  | 6481
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 21329030
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency