## PROJECT
RESERVES:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR
| FUNDING |  | GFFY2024 S/B DABS FUNDED |  |  |  | DESIGN
| STATE RISK NUMBER |  | 00000 |  |  |  | INSPECTION
| PROJECT TITLE |  | DABS NEW MOAB STORE |  |  |  | INSURANCE
| PROJECT # |  | 24167030 | OPEN |  |  | CONTINGENCY/LEGAL
| CODING BLOCK |  | 3000-300-3347-FWCAA-24167030 |  |  | 25572.31 | TOTAL | 0
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
YR | CURRENT TOTALS |  | 9189613.09 | 3.81 | 9189609.28 | 9215181.59 | -25568.5 | 0 |  |  |  | 0
0
| 5482-650-8004-5482-7520 |  |  | 0 |  | 0 | 0
FY'23 |  |  |  | 0 |  | 0 | 0
2023-06-29 | INTEGRA REALTY GAX FC2023062921235 | DF |  | 0 | 4500 | 4500 | 0 |  |  | 6855
|  |  |  | 0 |  | 0 | 0
FY'24 |  |  |  | 0 |  | 0 | 0
2023-11-30 | RMEC ENVIRO GAX FC2023113028327 | DF |  | 0 | 3632.5 | 3632.5 | 0 |  |  | 6855
2023-12-12 | RED DESERT LAND GAX FC2023121228872 | DF |  | 0 | 2650 | 2650 | 0 |  |  | 6855
2024-01-03 | BUDGETED CD CONTINGENCY - 24167030 | DF | -302908 | -302908 |  | 0 | -302908 |  |  | 4663
2024-01-12 | MOAB GEOTECH GAX FC2024011230290 | DF |  | 0 | 7366 | 7366 | 0 |  |  | 6861
2024-01-31 | TRNSF FY24 CAP DEV FUNDS TO 24167030 FROM 24376300 SB 3 ITEM 531 | DF | 12000000 | 12000000 |  | 0 | 12000000 |  |  | 4667
2024-02-13 | ROBERT JACOBY GAX FC2024021331751 | DF |  | 0 | 3590 | 3590 | 0 |  |  | 6861
2024-03-31 | REV TRNSF FY24 CAP DEV FUNDS TO 24167030 FROM 24376300 SB 3 ITEM 531 | DF | -12000000 | -12000000 |  | 0 | -12000000 |  |  | 4667
2024-03-12 | METRO NATIONAL TITLE GAX FC2024031232998 | DF |  | 0 | 1997781.86 | 0 | 0 |  | 2470314 | 6855
2024-04-05 | JACOBY ARCHITECTS INC - CONTRACT | N/A |  | 0 |  | 450342 | 0 |  | 2470416
2024-05-14 | ITA 24*131 MOAB DABS STORE | DF |  | 0 | 59394 | 59394 | 0 |  |  | 6284
2024-06-11 | METRO NATIONAL AMD 001 | CO |  | 0 |  | -52218.14 | 0 |  | 2470314
2024-06-19 | ROBERT JACOBY GAX FC2024061938091 | TR |  | 0 | 45795.67 | 0 | 0 |  | 2470416 | 6861
2024-06-29 | ROBERT JACOBY GAX FC2024062938876 | TR |  | 0 | 18735.75 | 0 | 0 |  | 2470416 | 6861
13/24 | ITA 24* 094 WAS $2,446,353,78 | TR | 2143445.78 | 2143445.78 |  | 0 | 2143445.78 |  |  | 4737
13/24 | REV BUDGETED CD CONTINGENCY - 24167030 -DABS FUNDING | TR | 302908 | 302908 |  | 0 | 302908 |  |  | 4664
13/24 | DFCM MGMT FEES TO 24425300 FROM 24167030 | TR | -49836 | -49836 |  | 0 | -49836
13/24 | REV BUDGETED CD CONTINGENCY - 24169030 -DABS FUNDING | TR | 277454 | 277454 |  | 0 | 277454
|  |  |  | 0 |  | 0 | 0
FY'25 |  |  |  | 0 |  | 0 | 0
2024-08-05 | ROBERT JACOBY GAX FC2024080540727 | DF |  | 0 | 50449.46 | 0 | 0 |  | 2470416 | 6861
2024-08-06 | IDT 25C3*006 XFER LEGAL FEES TO 21257300 | DF |  | 0 | 2970 | 2970 | 0 |  |  | 6870
2024-09-12 | ROBERT JACOBY GAX FC2024091242369 | DF |  | 0 | 28799.92 | 0 | 0 |  | 2470416 | 6861
2024-12-27 | ROCKY MTN P&L GAX FC2024122747353 | EH |  | 0 | 22914.2 | 22914.2 | 0 |  |  | 6811
2025-01-10 | ROBERT JACOBY GAX300FC2025011047911 | EH |  | 0 | 120784.46 | 0 | 0 |  | 2470416 | 6861
2025-01-14 | UTAH STATE FIRE MARSHAL GAX30025C2000091 | EH |  | 0 | 271.92 | 271.92 | 0 |  |  | 6873
2025-01-23 | WC3 GAX30025C5*095 | EH |  | 0 | 1000 | 1000 | 0 |  |  | 6873
2024-02-09 | ITA 25*057 FC24167 MOAB UT. RES#893888 | HH |  | 0 | 1800 | 1800 | 0 |  |  | 6879
2025-02-15 | ITA 650 25*058 | HH | 1371.96 | 1371.96 |  | 0 | 1371.96 |  |  | 4737
2025-02-25 | NEDERLAND REF A/C GAX300FC2025022550004 | HH |  | 0 | 514 | 0 | 0 |  | 2570177 | 6849
2025-02-25 | ROBERT JACOBY GAX300FC2025022550005 | HH |  | 0 | 37949.51 | 0 | 0 |  | 2470416 | 6861
2025-03-21 | REV BUDGETED CD CONTINGENCY - 24169030 -DABS FUNDING | HH | -277454 | -277454 |  | 0 | -277454 |  |  | 4664
2025-03-14 | ITA3002500000068 DFCM Course of Construction | HH |  | 0 | 13666.24 | 13666.24 | 0 |  |  | 6872
2025-03-20 | ITA 650 25*076 | HH | 329583.75 | 329583.75 |  | 0 | 329583.75 |  |  | 4737
2025-03-24 | NEDERLAND REF A/C & HEATING CORP GAX300FC2025032451351 | HH |  | 0 | 220 | 0 | 0 |  | 2570177 | 6849
2025-03-25 | GRAND WATER & SEWER SERV GAX300FC2025032551415 | HH |  | 0 | 320 | 320 | 0 |  |  | 6811
2025-03-26 | MOAB CITY GAX300FC2025032651503 | HH |  | 0 | 3845.2 | 3845.2 | 0 |  |  | 6811
2025-04-03 | ITA3002500000072 DFCM Course of Construction | HH |  | 0 | 12561.67 | 12561.67 | 0 |  |  | 6872
2024-03-07 | METRO NATIONAL - CONTRACT | TR |  | 0 |  | 2050000 | 0 |  | 2470314
2025-01-03 | NEDERLAND REF A/C - CONTRACT | TR |  | 0 |  | 36600 | 0 |  | 2570177
2025-03-06 | SHUMS CODA - CONTRACT | TR |  | 0 |  | 48436 | 0 |  | 2570253
2025-02-06 | SIRQ, INC - CONTRACT | TR |  | 0 |  | 6356390 | 0 |  | 2575361
2025-04-03 | ITA300 25*079 DFCM Course of Construction | HH |  | 0 | -12561.67 | -12561.67 | 0 |  |  | 6872
2025-04-10 | ITA 650 25*78 | TR | 4385.2 | 4385.2 |  | 0 | 4385.2 |  |  | 4737
2025-04-22 | SIRQ INC GAX300FC2025042252641 | HH |  | 0 | 126662.44 | 0 | 0 |  | 2575361 | 6811
2025-04-22 | SIRQ INC GAX300FC2025042252642 | HH |  | 0 | 6666.44 | 0 | 0 |  | 2575361 | 6811
2025-05-02 | NEDERLAND REF A/C & HEATING CORP GAX300FC2025050253165 | HH |  | 0 | 1760 | 0 | 0 |  | 2570177 | 6849
2025-05-08 | ITA 650 25*89 | HH | 135088.88 | 135088.88 |  | 0 | 135088.88 |  |  | 4737
2025-05-12 | SIRQ INC GAX300FC2025051253639 | HH |  | 0 | 305418.39 | 0 | 0 |  | 2575361 | 6811
2025-05-12 | SIRQ INC GAX300FC2025051253640 | HH |  | 0 | 16074.65 | 0 | 0 |  | 2575361 | 6811
2025-05-16 | ROBERT JACOBY GAX300FC2025051653935 | HH |  | 0 | 30336.19 | 0 | 0 |  | 2470416 | 6861
2025-06-10 | ROBERT JACOBY GAX300FC2025060954960 CONTRACT 2470416-NEW MOAB STORE | HH |  | 0 | 8581.41 | 0 | 0 |  | 2470416 | 6861
2025-06-10 | SIRQ INC GAX300FC2025060955000 CONTRACT 2575361-PAY APP #3-NEW MOAB STORE | HH |  | 0 | 355500.91 | 0 | 0 |  | 2575361 | 6811
2025-06-10 | SIRQ INC GAX300FC2025060955001 CONTRACT 2575361-PAY APP #3-NEW MOAB STORE | HH |  | 0 | 18710.57 | 0 | 0 |  | 2575361 | 6811
2025-06-10 | ITA 650 25*99 | HH | 734622.12 | 734622.12 |  | 0 | 734622.12 |  |  | 4737
13/25 | NEDERLAND REF A/C & HEATING CORP GAX300FC2025063055998 CONTRACT 2570177-NEW MOAB LIQUOR STORE | HH |  | 0 | 1045 | 0 | 0 |  | 2570177 | 6849
13/25 | ITA 650 25*111 | HH | 1045 | 1045 |  | 0 | 1045 |  |  | 4737
13/25 | SHUMS CODA ASSOCIATES INC GAX300FC2025070356379 CONTRACT 2570253-NEW MOAB STORE | HH |  | 0 | 4783.4 | 0 | 0 |  | 2570253 | 6873
13/25 | SHUMS CODA ASSOCIATES INC GAX300FC2025070356381 CONTRACT 2570253-NEW MOAB STORE | HH |  | 0 | 6296.9 | 0 | 0 |  | 2570253 | 6873
13/25 | ROBERT JACOBY GAX300FC2025071056743 CONTRACT 2470416-NEW MOAB STORE | HH |  | 0 | 8211.71 | 0 | 0 |  | 2470416 | 6861
13/25 | SIRQ INC GAX300FC2025071056760 CONTRACT 2575361-PAY APP #4-NEW MOAB STORE | HH |  | 0 | 866801.55 | 0 | 0 |  | 2575361 | 6811
13/25 | SIRQ INC GAX300FC2025071056761 CONTRACT 2575361-PAY APP #4-NEW MOAB STORE | HH |  | 0 | 45621.13 | 0 | 0 |  | 2575361 | 6811
13/25 | ITA 650 25*119 | HH | 931714.69 | 931714.69 |  | 0 | 931714.69 |  |  | 4737
13/25 | SHUMS CODA ASSOCIATES INC GAX300FC2025071857184 CONTRACT 2570253-NEW MOAB STORE | HH |  | 0 | 5695.68 | 0 | 0 |  | 2570253 | 6873
13/25 | ITA 650 25*128 | HH | 5695.68 | 5695.68 |  | 0 | 5695.68 |  |  | 4737
FY'26
2025-07-15 | QUESTAR GAS COMPANY GAX300FC2025071456922 PO 237437-DABS NEW MOAB STORE ENBRIDGE GAS IMPACT FEES | HH |  | 0 | 6363.94 | 6363.94 | 0 |  |  | 6855
2025-08-01 | ITA3002600000002 RES #920825 CANYONLANDS/MOAB 7/14/2025 FC24167 | HH |  | 0 | 2000 | 2000 | 0 |  |  | 6007
2025-08-12 | ROBERT JACOBY GAX300FC2025081157949 CONTRACT 2470416-NEW MOAB STORE | HH |  | 0 | 10638.64 | 0 | 0 |  | 2470416 | 6861
2025-08-12 | SIRQ INC GAX300FC2025081157971 CONTRACT 2575361-PAY APP #5-NEW MOAB STORE | HH |  | 0 | 645827.38 | 0 | 0 |  | 2575361 | 6811
2025-08-12 | SIRQ INC GAX300FC2025081157972 CONTRACT 2575361-PAY APP #5-NEW MOAB STORE | HH |  | 0 | 33990.91 | 0 | 0 |  | 2575361 | 6811
2025-08-23 | NEDERLAND REF A/C & HEATING CORP GAX300FC2025082258511 CONTRACT 2570177-NEW MOAB LIQUOR STORE | HH |  | 0 | 550 | 0 | 0 |  | 2570177 | 6849
2025-08-30 | SHUMS CODA ASSOCIATES INC GAX300FC2025082958814 CONTRACT 2570253-NEW MOAB STORE | HH |  | 0 | 6990.9 | 0 | 0 |  | 2570253 | 6873
2025-09-05 | ITA3002600000009 RES #922129 CANYONLANDS/MOAB 8/11/2025 FC24167 | HH |  | 0 | 1800 | 1800 | 0 |  |  | 6007
2025-09-05 | ITA 650 26*007 | HH | 708161.77 | 708161.77 |  | 0 | 708161.77 |  |  | 4737
2025-09-06 | WEST COAST CODE CONSULTANTS INC GAX30026C5000017 Plan Review Services 07/29/2025-1ST REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-09-06 | WEST COAST CODE CONSULTANTS INC GAX30026C5000017 Plan Review Services 07/22/2025-1ST REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-09-09 | SIRQ INC GAX300FC2025090859128 CONTRACT 2575361-PAY APP #6-NEW MOAB STORE | HH |  | 0 | 598950.88 | 0 | 0 |  | 2575361 | 6811
2025-09-09 | SIRQ INC GAX300FC2025090859129 CONTRACT 2575361-PAY APP #6-NEW MOAB STORE | HH |  | 0 | 31523.73 | 0 | 0 |  | 2575361 | 6811
2025-09-12 | ROBERT JACOBY GAX300FC2025091159342 CONTRACT 2470416-NEW MOAB STORE | HH |  | 0 | 15552.05 | 0 | 0 |  | 2470416 | 6861
2025-09-13 | IDT30026C30000014 CORRECT PROJECT UTAH STATE FIRE MARSHAL'S OFFICE GAX30026C5000011 INV 2025-01393 | HH |  | 0 | 267.56 | 267.56 | 0 |  |  | 6873
2025-09-19 08:50 | SIRQ INC CO 001 | CO |  | 0 |  | 2865.8 | 0 |  | 2575361
2025-10-04 | SHUMS CODA ASSOCIATES INC GAX300FC2025100360351 CONTRACT 2570253-NEW MOAB STORE | HH |  | 0 | 1890.1 | 0 | 0 |  | 2570253 | 6873
2025-10-07 | ITA 650 26*015 | HH | 648434.32 | 648434.32 |  | 0 | 648434.32 |  |  | 4737
2025-10-10 | SIRQ INC GAX300FC2025100960663 CONTRACT 2575361-PAY APP #7-NEW MOAB STORE | HH |  | 0 | 1018742.84 | 0 | 0 |  | 2575361 | 6811
2025-10-10 | SIRQ INC GAX300FC2025100960664 CONTRACT 2575361-PAY APP #7-NEW MOAB STORE | HH |  | 0 | 53618.04 | 0 | 0 |  | 2575361 | 6811
2025-10-07 | NEDERLAND REF A/C & HEATING CORP GAX300FC2025100660421 CONTRACT 2570177-NEW MOAB LIQUOR STORE | HH |  | 0 | 2420 | 0 | 0 |  | 2570177 | 6849
2025-10-24 | NEDERLAND REF A/C & HEATING CORP GAX300FC2025102361197 CONTRACT 2570177-DABS - NEW MOAB LIQUOR STORE | HH |  | 0 | 330 | 0 | 0 |  | 2570177 | 6849
2025-10-24 | NEDERLAND REF A/C & HEATING CORP GAX300FC2025102361198 CONTRACT 2570177-DABS - NEW MOAB LIQUOR STORE | HH |  | 0 | 749.89 | 0 | 0 |  | 2570177 | 6849
2025-10-29 | WEST COAST CODE CONSULTANTS INC GAX30026C5000058 Plan Review Services 09/22/2025-1ST REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-11-01 | SHUMS CODA ASSOCIATES INC GAX300FC2025103161503 CONTRACT 2570253-NEW MOAB STORE | HH |  | 0 | 1762.35 | 0 | 0 |  | 2570253 | 6873
2025-11-06 | ITA 650 26*026 | HH | 1077748.12 | 1077748.12 |  | 0 | 1077748.12 |  |  | 4737
2025-11-07 | SIRQ INC GAX300FC2025110661775 CONTRACT 2575361-PAY APP #8-NEW MOAB STORE | HH |  | 0 | 786782.43 | 0 | 0 |  | 2575361 | 6811
2025-11-07 | SIRQ INC GAX300FC2025110661776 CONTRACT 2575361-PAY APP #8-NEW MOAB STORE | HH |  | 0 | 41409.6 | 0 | 0 |  | 2575361 | 6811
2025-11-15 | NEDERLAND REF A/C & HEATING CORP GAX300FC2025111462135 CONTRACT 2570177-DABS - NEW MOAB LIQUOR STORE | HH |  | 0 | 310.31 | 0 | 0 |  | 2570177 | 6849
2025-11-13 | SIRQ INC CO 002 | CO |  | 0 |  | 26144.85 | 0 |  | 2575361
2025-12-02 | SHUMS CODA ASSOCIATES INC GAX300FC2025120162728 CONTRACT 2570253-NEW MOAB STORE | HH |  | 0 | 5560.3 | 0 | 0 |  | 2570253 | 6873
2025-12-03 | WEST COAST CODE CONSULTANTS INC GAX30026C5000078 Plan Review Services 10/22/2025-1ST REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-12-04 | ITA 650 26*033 | HH | 834187.64 | 834187.64 |  | 0 | 834187.64 |  |  | 4737
2025-12-06 | SIRQ INC GAX300FC2025120563010 CONTRACT 2575361-PAY APP #9-NEW MOAB STORE | HH |  | 0 | 853281.46 | 0 | 0 |  | 2575361 | 6811
2025-12-06 | SIRQ INC GAX300FC2025120563011 CONTRACT 2575361-PAY APP #9-NEW MOAB STORE | HH |  | 0 | 44909.55 | 0 | 0 |  | 2575361 | 6811
2025-12-20 | Nederland Refrigeration, Air Conditioning and Heating Corp GAX300FC2025121963660 CONTRACT 2570177-DABS - NEW MOAB LIQUOR STORE | HH |  | 0 | 2465.3 | 0 | 0 |  | 2570177 | 6849
2026-01-06 | ITA 650 26*042 | HH | 900656.31 | 900656.31 |  | 0 | 900656.31 |  |  | 4737
2026-01-10 | ROBERT JACOBY GAX300FC2026010964271 CONTRACT 2470416-NEW MOAB STORE | HH |  | 0 | 42116.44 | 0 | 0 |  | 2470416 | 6861
2026-01-13 | SIRQ INC GAX300FC2026011264425 CONTRACT 2575361-PAY APP #10-NEW MOAB STORE | HH |  | 0 | 470334.45 | 0 | 0 |  | 2575361 | 6811
2026-01-13 | SIRQ INC GAX300FC2026011264426 CONTRACT 2575361-PAY APP #10-NEW MOAB STORE | HH |  | 0 | 24754.45 | 0 | 0 |  | 2575361 | 6811
2026-09-11 | ROBERT JACOBY AMD 001 | CO |  | 0 |  | 4168 | 0 |  | 2470416
2026-01-22 | Nederland Refrigeration, Air Conditioning and Heating Corp GAX300FC2026012164830 CONTRACT 2570177-DABS - NEW MOAB LIQUOR STORE | HH |  | 0 | 10187.93 | 0 | 0 |  | 2570177 | 6849
2026-01-23 | SHUMS CODA ASSOCIATES INC GAX300FC2026012264891 CONTRACT 2570253-NEW MOAB STORE | HH |  | 0 | 5184.85 | 0 | 0 |  | 2570253 | 6873
2026-01-22 | ITA3002600000062 RES #931505 CANYONLANDS/MOAB 12/18/2025 FC24167 | HH |  | 0 | 1683 | 1683 | 0 |  |  | 6007
2026-02-03 | IDT30026C30000055 REQ0346533 APG Heavy Duty Cash Drawer Stainless-Steel-Front Cash Drawer MultiPRO 32 PRC300DTS0006367 | HH |  | 0 | 480.72 | 480.72 | 0 |  |  | 6853
2026-02-05 | ITA 650 26*053 | HH | 554741.84 | 554741.84 |  | 0 | 554741.84 |  |  | 4737
2026-02-10 | SIRQ INC GAX300FC2026020965845 CONTRACT 2575361-PAY APP #11-NEW MOAB STORE | HH |  | 0 | 107359.86 | 0 | 0 |  | 2575361 | 6811
2026-02-10 | SIRQ INC GAX300FC2026020965846 CONTRACT 2575361-PAY APP #11-NEW MOAB STORE | HH |  | 0 | 5650.52 | 0 | 0 |  | 2575361 | 6811
2026-02-03 12:17 | SIRQ INC CO 003 | CO |  | 0 |  | 82852.74 | 0 |  | 2575361
2026-02-19 | Nederland Refrigeration, Air Conditioning and Heating Corp GAX300FC2026021866190 CONTRACT 2570177-DABS - NEW MOAB LIQUOR STORE | HH |  | 0 | 4220.2 | 0 | 0 |  | 2570177 | 6849
2026-02-04 | 6360:Technician Hourly Rate IET150260703400003742 | HH |  | 0 | 2339.04 | 2339.04 | 0 |  |  | 6300
2026-03-05 | IET150260806300002712 6360:Technician Hourly Rate | HH |  | 0 | 478.44 | 478.44 | 0 |  |  | 6300
2026-03-05 | IET150260806300003746 6360:Technician Hourly Rate | HH |  | 0 | 3614.88 | 3614.88 | 0 |  |  | 6300
2026-03-10 | ITA 650 26*061 | HH | 123662.94 | 123662.94 |  | 0 | 123662.94 |  |  | 4737
2026-03-07 | SHUMS CODA ASSOCIATES INC GAX300FC2026030666976 CONTRACT 2570253-NEW MOAB STORE | HH |  | 0 | 143 | 0 | 0 |  | 2570253 | 6873
2026-03-13 | ITA3002600000091 RES #931506 CANYONLANDS/MOAB 2/2/2026 FC24167 | HH |  | 0 | 1800 | 1800 | 0 |  |  | 6879
2026-04-07 | ITA 650 26*067 | HH | 1943 | 1943 |  | 0 | 1943 |  |  | 4760
2026-04-14 | CDW GOVERNMENT INC PRC300DTS0006717 REQ0351311 Heavy Duty Cash Drawer | HH |  | 0 | -240.36 | -240.36 | 0 |  |  | 6853
2026-04-14 | CDW GOVERNMENT INC PRC300DTS0006717 REQ0351311 APG Heavy Duty Cash Drawer | HH |  | 0 | 240.36 | 240.36 | 0 |  |  | 6853
2026-04-21 | Nederland Refrigeration, Air Conditioning and Heating Corp GAX300FC2026042068906 CONTRACT 2570177-DABS - NEW MOAB LIQUOR STORE | HH |  | 0 | 8287.4 | 0 | 0 |  | 2570177 | 6849
2026-04-03 | NEDERLAND AMD 001 | CO |  | 0 |  | -3539.97 | 0 |  | 2570177
2026-05-06 | ITA 650 26*081 | HH | 8287.4 | 8287.4 |  | 0 | 8287.4 |  |  | 4760
2026-05-09 | ROBERT JACOBY GAX300FC2026050869794 CONTRACT 2470416-NEW MOAB STORE | HH |  | 0 | 5670.84 | 0 | 0 |  | 2470416 | 6861
2026-05-13 | CDW GOVERNMENT INC PRC300DTS0006723 REQ0353146 Cherry Advanced Performance Line LPOS G86-71401 | HH |  | 0 | 211.12 | 211.12 | 0 |  |  | 6853
2026-05-13 | Americom Technology, LLC PRC300DTS0006742 REQ0330956 Americom (Wiring) ALL Standard/Non standard labor hours | HH |  | 0 | 5964.23 | 5964.23 | 0 |  |  | 6481
2026-05-13 | Americom Technology, LLC PRC300DTS0006898 REQ0330956 Americom Quote 76265 DABS Moab/Standard Labor Hours/Material/Consumables | HH |  | 0 | 15555.91 | 15555.91 | 0 |  |  | 6481
2026-05-13 | VALCOM COMPUTER CENTER OF SLC PRC300DTS0006622 REQ0353092 HP Workstation Z2 G1i | HH |  | 0 | 2769.62 | 2769.62 | 0 |  |  | 6853
2026-05-13 | CDW GOVERNMENT INC PRC300DTS0007077 REQ0351311 APG Heavy Duty Cash Drawer Stainless | HH |  | 0 | 495.96 | 495.96 | 0 |  |  | 6853
2026-06-08 | ITA 650 26*087 | HH | 30667.68 | 30667.68 |  | 0 | 30667.68 |  |  | 4760
2026-06-13 | SIRQ INC GAX300FC2026061271389 CONTRACT 2575361-PAY APP #12-NEW MOAB STORE | HH |  | 0 | 60804.76 | 0 | 0 |  | 2575361 | 6811
2026-06-13 | SIRQ INC GAX300FC2026061271390 CONTRACT 2575361-PAY APP #12-NEW MOAB STORE | HH |  | 0 | 3200.25 | 0 | 0 |  | 2575361 | 6811
2026-06-08 | ITA 650 26*100 | HH | 64005.01 | 64005.01 |  | 0 | 64005.01 |  |  | 4760
2026-07-14 | IDT15026DP000212 Americom Refund | HH |  | 0 | -106.99 | -106.99 | 0 |  |  | 6481
2026-06-05 11:03 | SIRQ INC CO 004 | CO |  | 0 |  | 54343.8 | 0 |  | 2575361
2026-05-27 10:50 | ROBERT JACOBY AMD 002 | CO |  | 0 |  | -15444.16 | 0 |  | 2470416
13/26 | IET150261319800002705 6374:Communication Parts |  |  | 0 | 103.18 | 103.18 | 0 |  |  | 6300
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 24167030
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency