## PROJECT
RESERVES:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR
| FUNDING |  | OTHER AGENCY FUNDS |  |  |  | DESIGN
| STATE RISK NUMBER |  | 00000 |  |  |  | INSPECTION
| PROJECT TITLE |  | ALANO CLUB IMPROVEMENTS - ROOFING, MECHANICAL AND ELECTRICAL |  |  |  | INSURANCE
| PROJECT # |  | 24284400 | OPEN |  |  | CONTINGENCY/LEGAL
| CODING BLOCK |  | 3000-300-3500-FXAAA-24284400 |  |  | 7500 | TOTAL | 0
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
YR | CURRENT TOTALS |  | 1049085.7 | 0 | 1049085.7 | 1056585.7 | -7500 | 0 |  |  |  | 0
0
| 1000-250-3632-KPBBB-7117-BGFADACNL-SFY26(Program Period) |  |  | 0 |  | 0 | 0
FY'24 |  |  |  | 0 |  | 0 | 0
2023-09-07 | FFKR ARCHITECTS PLANNERS II - CONTRACT | CO |  | 0 |  | 9500 | 0 |  | 2470096
2023-12-07 | FFKR ARCHI GAX FC2023120728753 | DF |  | 0 | 9500 | 0 | 0 |  | 2470096 | 6137
2024-01-12 | FFKR ARCHITECTS PLANNERS II - CONTRACT | CO |  | 0 |  | 43650 | 0 |  | 2470269
2024-01-31 | COMFORT SYS USA GAX FC2024013131242 | DF |  | 0 | 452 | 452 | 0 |  |  | 6400
2024-01-31 | COMFORT SYS USA GAX FC2024013131243 | DF |  | 0 | 854 | 854 | 0 |  |  | 6400
2024-03-22 | FFKR ARCHI GAX FC2024032233603 | DF |  | 0 | 1637 | 0 | 0 |  | 2470269 | 6137
2024-04-05 | FFKR ARCHI GAX FC2024040534281 | DF |  | 0 | 6002 | 0 | 0 |  | 2470269 | 6137
2024-05-17 | FFKR ARCHI GAX FC2024051736373 | DF |  | 0 | 16369 | 0 | 0 |  | 2470269 | 6137
13/24 | FFKR ARCHI GAX FC2024071539857 | TR |  |  | 4365 |  |  |  | 2470269 | 6137
13/24 | ITA 24*194 BGFADAC4 ALDO 24INV347 JUNE 24 | HH |  | 0 | -34814 | -34814 | 0 |  |  | 7117
0
FY'25
13/24 | IDT 24C3*412 MGMT FEES | TR | -15520 | -15520 |  | 0 | -15520 |  |  | 4672
13/24 | IDT 24C3*408 CORRECT OBJ TO REV | TR |  | 0 | 34814 | 34814 | 0 |  |  | 7117
13/24 | IDT 24C3*408 CORRECT OBJ TO REV | TR | 34814 | 34814 |  | 0 | 34814 |  |  | 4737
2024-08-06 | IDT 25C3*006 XFER LEGAL FEES TO 21257300 | DF |  | 0 | 779 | 779 | 0 |  |  | 6138
2024-10-22 | FFKR ARCHI GAX FC2024102244332 | DF |  | 0 | 2619 | 0 | 0 |  | 2470269 | 6137
2024-12-18 | FFKR ARCHI GAX FC2024121846882 | EH |  | 0 | 1746 | 0 | 0 |  | 2470269 | 6137
2025-01-02 | ROD LEWIS CONSTRUCTION LLC - CONTRACT | CO |  | 0 |  | 669734 | 0 |  | 2575299
2024-12-13 | IDT 25C3*086 MGMT FEES TO 24425300 | EH |  | 0 | 15520 | 15520 | 0 |  |  | 6865 |  |  | ADDED PER FP06 EXP REPORT
2024-12-27 | REV MGMT FEES FROM 24284400 TO 24425300 | EH | 15520 | 15520 |  | 0 | 15520 |  |  | 4672 |  |  | ADDED PER FP06 REV REPORT
2025-01-30 | FFKR ARCH GAX300FC2025013048908 | EH |  | 0 | 2182 | 0 | 0 |  | 2470269 | 6137
2025-02-26 | RSANALYSIS GAX300FC2025022650068 | HH |  | 0 | 3680 | 3680 | 0 |  |  | 6400
2025-02-27 | murray city pwr gax300fc2025022750113 | HH |  | 0 | 2843.24 | 2843.24 | 0 |  |  | 6400
2025-02-27 | Murray City Pwr GAX 300fc2025022750114 | HH |  | 0 | 26470.25 | 26470.25 | 0 |  |  | 6400
2025-03-06 | FFKR ARCHITECTS / PLANNERS II GAX300FC2025030650520 | HH |  | 0 | 1309.5 | 0 | 0 |  | 2470269 | 6137
2025-03-11 | FFKR ARCHITECTS / PLANNERS II GAX300FC2025031150847 | HH |  | 0 | 873 | 0 | 0 |  | 2470269 | 6137
2025-04-18 | Rod Lewis Construction, LLC GAX300FC2025041852541 | HH |  | 0 | 175242.7 | 0 | 0 |  | 2575299 | 6400
2025-04-18 | Rod Lewis Construction, LLC GAX300FC2025041852542 | HH |  | 0 | 9223.3 | 0 | 0 |  | 2575299 | 6400
2025-02-28 | ROD LEWIS CONST CO 001 | CO |  | 0 |  | 10250.62 | 0 |  | 2575299
2025-04-30 | JOHN STAHELI GAX300FC2025043053037 | HH |  | 0 | 345.22 | 345.22 | 0 |  |  | 6139
2025-05-13 | FFKR ARCHITECTS / PLANNERS II GAX300FC2025051353711 | HH |  | 0 | 2182.5 | 0 | 0 |  | 2470269 | 6137
2025-05-15 | PARTIAL DEPOSIT REFUND-ALANOCLUB CR30025M5000119 | HH |  | 0 | -1854.68 | -1854.68 | 0 |  |  | 6400
2025-05-16 11:02 | ROD LEWIS CONST CO 002 | CO |  | 0 |  | 3996.45 | 0 |  | 2575299
2025-06-11 | Rod Lewis Construction, LLC GAX300FC2025061055086 CONTRACT 2575299-PAY APP #2-ALANO CLUB REMODEL | HH |  | 0 | 174724 | 0 | 0 |  | 2575299 | 6400
2025-06-11 | Rod Lewis Construction, LLC GAX300FC2025061055087 CONTRACT 2575299-PAY APP #2-ALANO CLUB REMODEL | HH |  | 0 | 9196 | 0 | 0 |  | 2575299 | 6400
2025-06-12 | FFKR ARCHITECTS / PLANNERS II GAX300FC2025061155191 CONTRACT 2470269 - ALANO CLUB IMPROVEMENTS | HH |  | 0 | 1746 | 0 | 0 |  | 2470269 | 6137
13/25 | JOHN STAHELI GAX300FC2025070156050 236856-ALANO CLUB REMODEL | HH |  | 0 | 604.44 | 604.44 | 0 |  |  | 6139
13/25 | ITA3002500000121 25INV344 DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT JUN 433796.47 USD | HH | 433796.47 | 433796.47 |  | 0 | 433796.47 |  |  | 4737
13/25 | FFKR ARCHITECTS / PLANNERS II GAX300FC2025071056747 CONTRACT 2470269 - ALANO CLUB IMPROVEMENTS | TR |  | 0 | 873 | 0 | 0 |  | 2470269 | 6137
13/25 | ITA3002500000129 25INV366 DFCM JUN 95065.44 USD | TR | 95065.44 | 95065.44 |  | 0 | 95065.44 |  |  | 4737
13/25 | Rod Lewis Construction, LLC GAX300FC2025071456966 CONTRACT 2575299-PAY APP #3-ALANO CLUB REMODEL | TR |  | 0 | 88079.25 | 0 | 0 |  | 2575299 | 6400
13/25 | Rod Lewis Construction, LLC GAX300FC2025071456967 CONTRACT 2575299-PAY APP #3-ALANO CLUB REMODEL | TR |  | 0 | 4635.75 | 0 | 0 |  | 2575299 | 6400
13/25 | ROD LEWIS CONST CO 003 | CO |  | 0 |  | 50785.27 | 0 |  | 2575299
13/25 | ROD LEWIS CONST CO 004 | CO |  | 0 |  | -3996.45 | 0 |  | 2575299
2025-03-12 | EAGLE ENVIRONMENTAL INC CONTRACT | CO |  | 0 |  | 12710 | 0 |  | 2575405
13/25 | FFKR ARCHITECTS PLANNERS II AMD 001 | CO |  | 0 |  | 4430 | 0 |  | 2470269
FY'26
2025-08-09 | Rod Lewis Construction, LLC GAX300FC2025080857926 CONTRACT 2575299-PAY APP #4-ALANO CLUB REMODEL | HH |  | 0 | 47270.06 | 0 | 0 |  | 2575299 | 6400
2025-08-09 | Rod Lewis Construction, LLC GAX300FC2025080857927 CONTRACT 2575299-PAY APP #4-ALANO CLUB REMODEL | HH |  | 0 | 2487.9 | 0 | 0 |  | 2575299 | 6400
2025-09-12 | Rod Lewis Construction, LLC GAX300FC2025091159374 CONTRACT 2575299-PAY APP #5-ALANO CLUB REMODEL | HH |  | 0 | 98057.1 | 0 | 0 |  | 2575299 | 6400
2025-09-12 | Rod Lewis Construction, LLC GAX300FC2025091159375 CONTRACT 2575299-PAY APP #5-ALANO CLUB REMODEL | HH |  | 0 | 5160.9 | 0 | 0 |  | 2575299 | 6400
2025-09-12 | FFKR ARCHITECTS / PLANNERS II GAX300FC2025091159323 CONTRACT 2470269 - ALANO CLUB IMPROVEMENTS | HH |  | 0 | 4430 | 0 | 0 |  | 2470269 | 6137
2025-09-13 | IDT30026C30000014 TRNSF TO 24284400 FROM 21137300 CI RESERVE FOR CO 001 | HH | 99661.5 | 99661.5 |  | 0 | 99661.5 |  |  | 4666
2025-09-13 | EAGLE ENVIRONMENTAL INC GAX300FC2025091259435 CONTRACT 2575405-PAY APP 1-ALANO CLUB IMP-ROOFING, MECH & ELEC (ABAT) | HH |  | 0 | 142178.42 | 0 | 0 |  | 2575405 | 6404
2025-09-13 | EAGLE ENVIRONMENTAL INC GAX300FC2025091259436 CONTRACT 2575405-PAY APP 1-ALANO CLUB IMP-ROOFING, MECH & ELEC (ABAT) | HH |  | 0 | 7483.08 | 0 | 0 |  | 2575405 | 6404
2025-09-08 | EAGLE ENVIRONMENTAL CO 001 | CO |  | 0 |  | 136951.5 | 0 |  | 2575405
2025-10-11 | FFKR ARCHITECTS / PLANNERS II GAX300FC2025101060698 CONTRACT 2470269 - ALANO CLUB IMPROVEMENTS | HH |  | 0 | 436.5 | 0 | 0 |  | 2470269 | 6137
2025-10-17 | FFKR ARCHITECTS / PLANNERS II GAX300FC2025101660896 CONTRACT 2470269 - ALANO CLUB IMPROVEMENTS | HH |  | 0 | 873 | 0 | 0 |  | 2470269 | 6137
2025-10-25 | JOHN STAHELI GAX300FC2025102361141 PO 240283-DHHS ALANO CLUB REMODEL | HH |  | 0 | 343.7 | 343.7 | 0 |  |  | 6139
2025-11-19 | Rod Lewis Construction, LLC GAX300FC2025111862292 CONTRACT 2575299-PAY APP #6-ALANO CLUB REMODEL | HH |  | 0 | 95756.2 | 0 | 0 |  | 2575299 | 6400
2025-11-19 | Rod Lewis Construction, LLC GAX300FC2025111862293 CONTRACT 2575299-PAY APP #6-ALANO CLUB REMODEL | HH |  | 0 | 5039.8 | 0 | 0 |  | 2575299 | 6400
2025-11-04 | ROD LEWIS CONST CO 005 | CO |  | 0 |  | 1656.11 | 0 |  | 2575299
2025-12-17 | JOHN STAHELI GAX300FC2025121663354 241609-DHHS ALANO CLUB REMODEL | HH |  | 0 | 392.7 | 392.7 | 0 |  |  | 6139
2025-12-16 | JEMZA ROOFING SLC INC CONTRACT | CO |  | 0 |  | 23347.5 | 0 |  | 2675251
2026-01-12 | TIMPANOGOS ELEVATOR COMPANY LLC CONTRACT | CO |  | 0 |  | 15000 | 0 |  | 2675262
2026-01-27 | TIMPANOGOS ELEVATOR COMPANY LLC GAX300FC2026012664974 CONTRACT 2675262-PAY APP #1-ALANO CLUB RENOVATIONS | HH |  | 0 | 7500 | 0 | 0 |  | 2675262 | 6400
2026-01-13 | ITA 250 26*1185 | HH | 316270.42 | 316270.42 |  | 0 | 316270.42 |  |  | 4737
2026-02-19 | JEMZA ROOFING SLC INC GAX300FC2026021866219 CONTRACT 2675251-DHHS ALANO CLUB RENOVATION | HH |  | 0 | 27997.5 | 0 | 0 |  | 2675251 | 6400
2026-02-13 | JEMZA ROOFING SLC CO 001 | CO |  | 0 |  | 4650 | 0 |  | 2675251
2026-03-10 | ITA 250 26*1593 | HH | 27997.5 | 27997.5 |  | 0 | 27997.5 |  |  | 4737
2026-04-21 | Rod Lewis Construction, LLC GAX300FC2026042068923 CONTRACT 2575299-PAY APP #7-ALANO CLUB REMODEL | HH |  | 0 | 16675.39 | 0 | 0 |  | 2575299 | 6400
2026-04-21 | Rod Lewis Construction, LLC GAX300FC2026042068924 CONTRACT 2575299-PAY APP #7-ALANO CLUB REMODEL | HH |  | 0 | 877.65 | 0 | 0 |  | 2575299 | 6400
2026-04-25 | FFKR ARCHITECTS / PLANNERS II GAX300FC2026042469106 CONTRACT 2470269 - ALANO CLUB IMPROVEMENTS | HH |  | 0 | 436.5 | 0 | 0 |  | 2470269 | 6137
2026-03-02 | 243937-ALANO CLUB REMODEL GAX300FC2026030266602 | HH |  | 0 | 343.7 | 343.7 | 0 |  |  | 6139
2026-05-06 | ITA 250 26*2145 | HH | 18333.24 | 18333.24 |  | 0 | 18333.24 |  |  | 4760
2026-05-23 | HILLS CONSTRUCTION INC GAX300FC2026052270320 PO 246546-BUILD PLATFORM & INSTALL OPENING IN BLDING FOR ADA LIFT | HH |  | 0 | 23147.13 | 23147.13 | 0 |  |  | 6400
2026-06-08 | ITA 250 26*2402 | HH | 23147.13 | 23147.13 |  | 0 | 23147.13 |  |  | 4760
13/26 | IDT30026000000322 CHANGING REVENUE_SOURCE TO 4658 | HH | -316270.42 | -316270.42 |  | 0 | -316270.42 |  |  | 4737
13/26 | IDT30026000000322 CHANGING REVENUE_SOURCE TO 4658 | HH | 27997.5 | 27997.5 |  | 0 | 27997.5 |  |  | 4658
13/26 | IDT30026000000322 CHANGING REVENUE_SOURCE TO 4658 | HH | -23147.13 | -23147.13 |  | 0 | -23147.13 |  |  | 4760
13/26 | IDT30026000000322 CHANGING REVENUE_SOURCE TO 4658 | HH | 316270.42 | 316270.42 |  | 0 | 316270.42 |  |  | 4658
13/26 | IDT30026000000322 CHANGING REVENUE_SOURCE TO 4658 | HH | 23147.13 | 23147.13 |  | 0 | 23147.13 |  |  | 4658
13/26 | IDT30026000000322 CHANGING REVENUE_SOURCE TO 4658 | HH | -27997.5 | -27997.5 |  | 0 | -27997.5 |  |  | 4737
13/26 | IDT30026000000321 CHANGING REVENUE_SOURCE TO 4658 | HH | 18333.24 | 18333.24 |  | 0 | 18333.24 |  |  | 4658
13/26 | IDT30026000000321 CHANGING REVENUE_SOURCE TO 4658 | HH | -18333.24 | -18333.24 |  | 0 | -18333.24 |  |  | 4760
|  |  |  | 0 |  | 0 | 0
FY'27 |  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 24284400
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency