## PROJECT
RESERVES:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR
| FUNDING |  | GFFY2025 |  |  |  | DESIGN
| STATE RISK NUMBER |  | 08610 |  |  |  | INSPECTION
| PROJECT TITLE |  | DHHS - JJS PROVO SCYC REPLACE ALL EXTERIOR DOOR AND WINDOW FRAMES THAT ARE RUSTED THROUGH |  |  |  | INSURANCE
| PROJECT # |  | 25238430 | OPEN |  |  | CONTINGENCY/LEGAL
| CODING BLOCK |  | 3000-300-3348-FXAAA-25238430 |  |  | 54108.98 | TOTAL | 0
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
514085.29
YR | CURRENT TOTALS |  | 663664 | 149578.71 | 514085.29 | 568194.27 | 95469.73 | 0 |  |  | 0 | 0
[11 empty] | 514085.29 | 0
|  |  |  | 0 |  | 0 | 0
FY'25 |  |  |  | 0 |  | 0 | 0
2024-08-12 | Trfr to 25238430 from FY25 GFFY Capital Improvement Funds | df | 70985 | 70985 |  |  | 70985 |  |  | 4667
2024-08-07 | IDT 25C3*008 XFER LEGAL FEES TO 21257300 | DF |  | 0 | 54 | 54 | 0 |  |  | 6870
2024-09-27 | DESIGN SEQUENCE - CONTRACT | N/A |  | 0 |  | 30480 | 0 |  | 2570081
2025-03-18 | DESIGN SEQUENCE GAX300FC2025031851114 | HH |  | 0 | 10454.4 | 0 | 0 |  | 2570081 | 6861
2025-04-18 | UTAH STATE FIRE MARSHAL'S OFFICE GAX30025C5000128 | HH |  | 0 | 132 | 132 | 0 |  |  | 6873
FY'26
2025-08-15 | IDT30026C30000004 2025 GS FY 26 CAPITAL IMPROVEMENT (HB6,SB2,SB3) - INCOME FUND | HH | 592679 | 592679 |  | 0 | 592679 |  |  | 4667
2025-12-17 | Northway Mountain Division LLC CONTRACT | CO |  | 0 |  | 524527 | 0 |  | 2675258
2026-01-15 | IDT30026C30000047 LEGAL FEES FROM 25238430 TO 21257300 FY26 Q2 BILLINGS | HH |  | 0 | 475 | 475 | 0 |  |  | 6870
2026-01-29 | ITA3002600000063 DFCM Course of Construction FY26 AND PRIOR COC CAPITAL IMPROVEMENT PROJECTS 9-25-25 CI_OY | HH |  | 0 | 1102 | 1102 | 0 |  |  | 6872
2026-02-11 | JOHN STAHELI CONTRACT | CO |  | 0 |  | 5245.27 | 0 |  | 2670317
2026-04-28 | Northway Mountain Division LLC GAX300FC2026042769183 CONTRACT 2675258-PAY APP #1-JJYS SLATE CANYON WIN/DOOR REPAIR | HH |  | 0 | 85064.06 | 0 | 0 |  | 2675258 | 6813
2026-04-28 | Northway Mountain Division LLC GAX300FC2026042769184 CONTRACT 2675258-PAY APP #1-JJYS SLATE CANYON WIN/DOOR REPAIR | HH |  | 0 | 4477.06 | 0 | 0 |  | 2675258 | 6813
2026-04-28 | CONTRACT 2670317-SLATE CANYON JJS WINDOW AND DOOR REPLACEMENT GAX300FC2026042869231 | HH |  | 0 | 712.6 | 0 | 0 |  | 2670317 | 6873
2026-05-30 | Northway Mountain Division LLC GAX300FC2026052970646 CONTRACT 2675258-PAY APP #2-JJYS SLATE CANYON WIN/DOOR REPAIR | HH |  | 0 | 135119.6 | 0 | 0 |  | 2675258 | 6813
2026-05-30 | Northway Mountain Division LLC GAX300FC2026052970647 CONTRACT 2675258-PAY APP #2-JJYS SLATE CANYON WIN/DOOR REPAIR | HH |  | 0 | 7111.56 | 0 | 0 |  | 2675258 | 6813
2026-06-02 | JOHN STAHELI GAX300FC2026060170707 CONTRACT 2670317-SLATE CANYON JJS WINDOW AND DOOR REPLACEMENT | HH |  | 0 | 221.2 | 0 | 0 |  | 2670317 | 6873
2026-06-25 | JOHN STAHELI GAX300FC2026062471905 CONTRACT 2670317-SLATE CANYON JJS WINDOW AND DOOR REPLACEMENT | HH |  | 0 | 442.4 | 0 | 0 |  | 2670317 | 6873
2026-06-13 | Northway Mountain Division LLC GAX300FC2026061271413 CONTRACT 2675258-PAY APP #3-JJYS SLATE CANYON WIN/DOOR REPAIR | HH |  | 0 | 160070.43 | 0 | 0 |  | 2675258 | 6813
2026-06-13 | Northway Mountain Division LLC GAX300FC2026061271414 CONTRACT 2675258-PAY APP #3-JJYS SLATE CANYON WIN/DOOR REPAIR | HH |  | 0 | 8424.76 | 0 | 0 |  | 2675258 | 6813
2026-07-03 | Northway Mountain Division LLC GAX300FC2026070272396 CONTRACT 2675258-PAY APP #4-JJYS SLATE CANYON WIN/DOOR REPAIR | HH |  | 0 | 4821.94 | 0 | 0 |  | 2675258 | 6813
2026-07-03 | Northway Mountain Division LLC GAX300FC2026070272395 CONTRACT 2675258-PAY APP #4-JJYS SLATE CANYON WIN/DOOR REPAIR | HH |  | 0 | 91616.88 | 0 | 0 |  | 2675258 | 6813
2026-07-07 | DESIGN SEQUENCE GAX300FC2026070672449 CONTRACT 2570081-SLATE CANYON DOOR & WINDOW REPLACEMENT | HH |  | 0 | 3121.8 | 0 | 0 |  | 2570081 | 6861
2026-07-10 | JOHN STAHELI GAX300FC2026070972724 CONTRACT 2670317-SLATE CANYON JJS WINDOW AND DOOR REPLACEMENT | HH |  | 0 | 663.6 | 0 | 0 |  | 2670317 | 6873
2026-06-12 07:21 | Northway Mountain Division LLC CO 001 | CO |  | 0 |  | 6179 | 0 |  | 2675258
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 25238430
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency