## PROJECT
[7 empty] | RESERVES: |  |  |  | FUNDING
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR |  |  |  | FEDERAL (ARPA) | 1398400 | 80.34%
| FUNDING |  | OTHER-ARPA FROM GOPB QRTLY - $1,398,400 |  |  |  | DESIGN |  |  |  | AGENCY | 342110.54 | 19.66%
| STATE RISK NUMBER |  | 09026, 08915, 05310, 02217, 09203, 08914, 08610, 09703, 02312 |  |  |  | INSPECTION |  |  |  |  | 1740510.54
| PROJECT TITLE |  | JJYS NO CLIMB SECURITY FENCING |  |  |  | INSURANCE
| PROJECT # |  | 25264430 | OPEN |  |  | CONTINGENCY/LEGAL
| CODING BLOCK |  | 3000-300-3348-FXAAA-25264430 |  |  | 741926.87 | TOTAL | 0
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
-325872.54
YR | CURRENT TOTALS |  | 1724272.54 | 0 | 1724272.54 | 2466199.41 | -741926.87 | 0 |  |  | 0 | 0
[11 empty] | -325872.54 | 0
|  |  |  | 0 |  | 0 | 0
FY'24 |  |  |  | 0 |  | 0 | 0
2024-04-22 | LEGACY DESIGN GROUP, LLC - CONTRACT | N/A |  | 0 |  | 88628 | 0 |  | 2470487
2024-05-14 | LEGACY DESIGN GAX 24C2*209 | DF |  | 0 | 4431 | 0 | 0 |  | 2470487 | 6137
2024-06-11 | LEGACY DESIGN GAX 24C2*297 | DF |  | 0 | 18244.58 | 0 | 0 |  | 2470487 | 6137
13/24 | LEGACY DESIGN GAX 24C2*395 | DF |  | 0 | 6466.38 | 0 | 0 |  | 2470487 | 6137
13/24 | DFCM MGMT FEES TO 24425300 FROM 25264430 | DF | -16238 | -16238 |  | 0 | -16238 |  |  | 4672
|  |  |  | 0 |  | 0 | 0
FY'25 |  |  |  | 0 |  | 0 | 0
2024-08-12 | LEGACY DESIGN GAX FC024081240977 | DF |  | 0 | 15953 | 0 | 0 |  | 2470487 | 6137
2024-08-30 | LEGACY DESIGN AMD 001 | CO |  | 0 |  | 11950 | 0 |  | 2470487
2024-09-18 | LEGACY DESIGN GAX 25C2*006 | DF |  | 0 | 16092 | 0 | 0 |  | 2470487 | 6137
2024-11-12 | LEGACY DESIGN GAX FC2024111245274 | DF |  | 0 | 8698.88 | 0 | 0 |  | 2470487 | 6137
2024-11-20 | UT ST FIRE MARSHAL GAX 25C5*059 | DF |  | 0 | 225 | 225 | 0 |  |  | 6139
2024-12-02 | WC3 PLAN REVIEW GAX 25C5*068 | DF |  | 0 | 375 | 375 | 0 |  |  | 6139
2024-12-10 | LEGACY DESIGN GAX 25C2*074 | EH |  | 0 | 5029 | 0 | 0 |  | 2470487 | 6137
2024-12-12 | LEGACY DESIGN GAX 25C2*073 | EH |  | 0 | 10576.58 | 0 | 0 |  | 2470487 | 6137
2024-12-20 | CUSTOM FENCE - CONTRACT | N/A |  | 0 |  | 1334037 | 0 |  | 2575292
2025-01-10 | LEGACY DES. GAXFC2025010947836 | EH |  | 0 | 5029 | 0 | 0 |  | 2470487 | 6137
2024-12-13 | IDT 25C3*093 LEGAL FEES TO 21257300 | EH |  | 0 | 1179 | 1179 | 0 |  |  | 6138 |  |  | ADDED PER FP06 EXP REPORT
2024-12-13 | IDT 25C3*086 MGMT FEES TO 24425300 | EH |  | 0 | 16238 | 16238 | 0 |  |  | 6865 |  |  | ADDED PER FP06 EXP REPORT
2024-12-27 | REV MGMT FEES FROM 25264430 TO 24425300 | EH | 16238 | 16238 |  |  | 16238 |  |  | 4672 |  |  | ADDED PER FP06 REV REPORT
2025-02-24 | WC3 GAX30025C5*111 | HH |  | 0 | 375 | 375 | 0 |  |  | 6139
2025-03-21 | Legacy Design Group, LLC GAX30025C2000212 | HH |  | 0 | 3017 | 0 | 0 |  | 2470487 | 6137
2025-04-14 | IDT 25C3*123 ASSIGN PROGRAM/PHASE - JJYS NO CLIMBING ARPA FUNDING | TR | 55810.54 | 55810.54 |  | 0 | 55810.54 |  |  | 3805
2025-04-30 | JOHN STAHELI GAX300FC2025043053028 | TR |  | 0 | 171.52 | 171.52 | 0 |  |  | 6139
2025-05-20 | CUSTOM FENCE GAX30025C2000344 | TR |  | 0 | 3216.3 | 0 | 0 |  | 2575292 | 6400
2025-05-20 | CUSTOM FENCE GAX30025C2000342 | TR |  | 0 | 6517.71 | 0 | 0 |  | 2575292 | 6400
2025-05-20 | CUSTOM FENCE GAX30025C2000341 | TR |  | 0 | 123836.44 | 0 | 0 |  | 2575292 | 6400
2025-05-20 | CUSTOM FENCE GAX30025C2000343 | TR |  | 0 | 61109.7 | 0 | 0 |  | 2575292 | 6400
2025-05-30 | ASSIGN PROGRAM/PHASE - JVA25F*699 JJYS NO CLIMBING ARPA FUNDING | HH | 55293.88 | 55293.88 |  | 0 | 55293.88 |  |  | 3805
2025-06-10 | JOHN STAHELI GAX300FC2025060954898 236337-JJYS NO CLIMB SECURITY FENCING -CASTLE COUNTY YTH CENTER | HH |  | 0 | 1447.62 | 1447.62 | 0 |  |  | 6139
2025-06-12 | JOHN STAHELI GAX30025C2000446 236042-JJYS NO CLIMB SECURITY FENCING -SLATE CANYON YTH CENTER | HH |  | 0 | 1845.48 | 1845.48 | 0 |  |  | 6139
2025-06-14 | IDT30025C30000151 ASSIGN ARPA GAX300FC2025060954898 236337-JJYS NO CLIMB SECURITY FENCING | TR |  | 0 | 1447.62 | 1447.62 | 0 |  |  | 6139
2025-06-14 | IDT30025C30000151 ASSIGN ARPA GAX300FC2025060954898 236337-JJYS NO CLIMB SECURITY FENCING | TR |  | 0 | -1447.62 | -1447.62 | 0 |  |  | 6139
13/25 | GEM ENGINEERING GAX300FC2025072357326 237665-JJYS NO CLIMB SECURITY FENCING-SOUTHWEST YTH CENTER | TR |  | 0 | 308 | 308 | 0 |  |  | 6139
13/25 | CUSTOM FENCE GAX30025C2000516 ONTRACT 2575292 PAYAPP#1-JJYS NO CLIMB SECURITY FENCING - SW Cedar City | TR |  | 0 | 3100 | 0 | 0 |  | 575292 | 6400
13/25 | CUSTOM FENCE GAX30025C2000515 ONTRACT 2575292 PAYAPP#1-JJYS NO CLIMB SECURITY FENCING - SW Cedar City | TR |  | 0 | 58900 | 0 | 0 |  | 575292 | 6400
13/25 | RECODE JVA15025F0000830 - FY25 QUARTER 4 ARPA JJYS CLIMBING FENCE | TR | 198969.77 | 198969.77 |  | 0 | 198969.77 |  |  | 3805
13/25 | IDT30025C30000083 ADD ARPA FUNCTION DFCM MGMT FEES TO 24425300 FROM 25264430 | TR | -16238 | -16238 |  | 0 | -16238 |  |  | 4672
13/25 | IDT30025C30000083 ADD ARPA FUNCTION DFCM MGMT FEES TO 24425300 FROM 25264430 | TR | 16238 | 16238 |  | 0 | 16238 |  |  | 4672
13/25 | RECODE JVA15025F0000866 - FY25 July Old ARPA JJYS CLIMBING FENCE | TR | 62308 | 62308 |  | 0 | 62308 |  |  | 3805
FY'26
2025-08-14 | Legacy Design Group, LLC GAX30026C2000012 CONTRACT 2470487- JJYS NO CLIMB SECURITY FENCING | HH |  | 0 | 1006 | 0 | 0 |  | 2470487 | 6137
2025-08-29 | GEM ENGINEERING GAX300FC2025082858720 238838-JJYS NO CLIMB SECURITY FENCING-SOUTHWEST YTH CENTER | HH |  | 0 | 1734.1 | 1734.1 | 0 |  |  | 6139
2025-09-17 | Legacy Design Group, LLC GAX30026C2000023 CONTRACT 2470487-JJYS NO CLIMB SECURITY FENCING | HH |  | 0 | 1006 | 0 | 0 |  | 2470487 | 6137
2025-10-09 | CUSTOM FENCE GAX30026C5000039 Contract 2575292-Pay App 2- Retainage | HH |  | 0 | 3735.77 | 0 | 0 |  | 2575292 | 6400
2025-10-09 | CUSTOM FENCE GAX30026C5000039 Contract 2575292-Pay App 2 | HH |  | 0 | 70979.6 | 0 | 0 |  | 2575292 | 6400
2025-10-08 | GEM ENGINEERING GAX300FC2025100760487 239931-JJYS NO CLIMB SECURITY FENCING-SOUTHWEST YTH CENTER | HH |  | 0 | 94.95 | 94.95 | 0 |  |  | 6139
2025-10-17 | CUSTOM FENCE GAX30026C2000041 CONTRACT 2575292 PAYAPP#2B-JJYS NO CLIMB SECURITY FENCING-SW Cedar City | HH |  | 0 | 17131.55 | 0 | 0 |  | 2575292 | 6400
2025-10-17 | CUSTOM FENCE GAX30026C2000040 CONTRACT 2575292 PAYAPP#2B-JJYS NO CLIMB SECURITY FENCING-SW Cedar City | HH |  | 0 | 325499.46 | 0 | 0 |  | 2575292 | 6400
2025-10-25 | Legacy Design Group, LLC GAX300FC2025102461240 CONTRACT 2470487- JJYS NO CLIMB SECURITY FENCING | HH |  | 0 | 1006 | 0 | 0 |  | 2470487 | 6137
2025-11-07 | JOHN STAHELI GAX300FC2025110661715 PO 240281-DHHS JJYS NO CLIMB SECURITY FENCING -CASTLE CNTY YTH CNTR | HH |  | 0 | 2029.2 | 2029.2 | 0 |  |  | 6139
2025-11-25 | Legacy Design Group, LLC GAX300FC2025112462555 CONTRACT 2470487- JJYS NO CLIMB SECURITY FENCING | HH |  | 0 | 2012 | 0 | 0 |  | 2470487 | 6137
2025-12-04 | GEM ENGINEERING GAX300FC2025120362863 241523-JJYS NO CLIMB SECURITY FENCING-SOUTHWEST YTH CENTER | HH |  | 0 | 1046.85 | 1046.85 | 0 |  |  | 6139
2025-12-05 | JVA15026F0000281 Transfer ARPA Funds to budget for distribution | HH | 2012 | 2012 |  | 0 | 2012 |  |  | 3805
2025-12-17 | JOHN STAHELI GAX300FC2025121663353 241614-JJYS NO CLIMB SECURITY FENCING -CASTLE COUNTY YTH CENTER | HH |  | 0 | 1566.65 | 1566.65 | 0 |  |  | 6139
2025-12-25 | CUSTOM FENCE GAX30026C2000077 CONTRACT 2575292 PAYAPP#3A-JJYS NO CLIMB SECURITY FENCING-SW Cedar City | HH |  | 0 | 11033.2 | 11033.2 | 0 |  |  | 6400
2026-01-13 | IDT30026C30000046 ADD ARPA (PARTIAL) GAX30026C2000090 Contract 2575292 CUSTOM FENCE | HH |  | 0 | 259966.74 | 259966.74 | 0 |  |  | 6400
2026-01-13 | IDT30026C30000046 ADD ARPA (PARTIAL) GAX30026C2000090 Contract 2575292 CUSTOM FENCE | HH |  | 0 | -259966.74 | -259966.74 | 0 |  |  | 6400
2026-01-08 | CONTRACT 2575292 PAYAPP#3A-JJYS NO CLIMB SECURITY FENCING-SW Cedar City GAX30026C2000076 | HH |  | 0 | 209630.79 | 209630.79 | 0 |  |  | 6400
2026-01-08 | CONTRACT 2575292 PAYAPP#3-JJYS NO CLIMB SECURITY FENCING-Castle Country Price GAX30026C2000079 | HH |  | 0 | 138067.9 | 138067.9 | 0 |  |  | 6400
2026-01-08 | CONTRACT 2575292 PAYAPP#3-JJYS NO CLIMB SECURITY FENCING-Castle Country Price GAX30026C2000079 | HH |  | 0 | 7266.73 | 7266.73 | 0 |  |  | 6400
2026-01-08 | GAX30026C2000090 Contract 2575292-JJYS No Climb Security Fencing - Slate Canyon Provo | HH |  | 0 | 356176.1 | 356176.1 | 0 |  |  | 6400
2026-01-08 | GAX30026C2000090 Contract 2575292-JJYS No Climb Security Fencing - Slate Canyon Provo | HH |  | 0 | 18746.11 | 18746.11 | 0 |  |  | 6400
2026-01-08 | GAX300FC2026010864223 CONTRACT 2470487- JJYS NO CLIMB SECURITY FENCING | HH |  | 0 | 1006 | 1006 | 0 |  |  | 6137
2026-01-13 08:33 | LEGACY DESGIN AMD 002 | CO |  | 0 |  | 2243.34 | 0 |  | 2470487
2026-01-09 08:07 | CUSTOM FENCE CO 001 | CO |  | 0 |  | 280910.4 | 0 |  | 2575292
2026-01-28 | JOHN STAHELI GAX300FC2026012765055 242982-JJYS NO CLIMB SECURITY FENCING -CASTLE COUNTY YTH CENTER | HH |  | 0 | 584.5 | 584.5 | 0 |  |  | 6139
2026-02-03 | JVA15026F0000403 Transfer ARPA Funds to budget for distribution | TR | 416340.38 | 416340.38 |  | 0 | 416340.38 |  |  | 3805
2026-02-24 | GEM ENGINEERING GAX300FC2026022366359 PO 232108-FINAL JJYS NO CLIMB SECURITY FENCING - SOUTHWEST | HH |  | 0 | 152.6 | 152.6 | 0 |  |  | 6139
2026-03-11 | JOHN STAHELI GAX300FC2026031067106 PO 243807-JJYS NO CLIMB FENCE SLATE CANYON-T & I DECEMBER 2025 | HH |  | 0 | 2494.6 | 2494.6 | 0 |  |  | 6139
2026-03-11 | JOHN STAHELI GAX300FC2026031067107 PO 232114-FINAL JJYS NO CLIMB FENCE SLATE CANYON T & I | HH |  | 0 | 2639.29 | 2639.29 | 0 |  |  | 6139
2026-03-10 | JOHN STAHELI GAX300FC2026030967018 PO 232111-JJYS NO CLIMB FENCING CASTLE COUNTY | HH |  | 0 | 49 | 49 | 0 |  |  | 6139
2026-03-17 | Legacy Design Group, LLC GAX300FC2026031667443 CONTRACT 2470487- JJYS NO CLIMB SECURITY FENCING | HH |  | 0 | 3247.92 | 0 | 0 |  | 2470487 | 6137
2026-05-07 | JVA15026F0000592 Transfer ARPA Funds to budget for distribution | HH | 607665.43 | 607665.43 |  | 0 | 607665.43 |  |  | 3805
2026-03-10 | JJYS AGENCY COMMITMENT #1 - 25264430 IDT30026C30000077 | HH | 155462 | 155462 |  | 0 | 155462 |  |  | 4761
2026-03-10 | JJYS AGENCY COMMITMENT #1 - 25264430 IDT30026C30000077 | HH | -155462 | -155462 |  | 0 | -155462 |  |  | 4761
2026-03-10 | JJYS AGENCY COMMITMENT #2 - 25264430 IDT30026C30000077 | HH | 199754.48 | 199754.48 |  | 0 | 199754.48 |  |  | 4761
2026-03-10 | JJYS AGENCY COMMITMENT #2 - 25264430 IDT30026C30000077 | HH | -199754.48 | -199754.48 |  | 0 | -199754.48 |  |  | 4761
2026-03-10 | JJYS AGENCY COMMITMENT #3 - 25264430 IDT30026C30000077 | HH | 3250.89 | 3250.89 |  | 0 | 3250.89 |  |  | 4761
2026-03-10 | JJYS AGENCY COMMITMENT #3 - 25264430 IDT30026C30000077 | HH | -3250.89 | -3250.89 |  | 0 | -3250.89 |  |  | 4761
2026-06-16 | HARRIS MOUNTAIN WEST, LLC DBA HARRIS GAX300FC2026061271264 INVOICE SR000117161 | EG |  | 0 | 10886.12 | 10886.12 | 0 |  |  | 6400
2026-06-16 | CUSTOM FENCE GAX300FC2026061271427 CONTRACT 2575292 PAYAPP#3B-JJYS NO CLIMB SECURITY FENCING - SLATE CANYON PROVO | EG |  | 0 | 169376.23 | 0 | 0 |  | 2575292 | 6400
13/26 | ITA 250 26*2803 | EG | 325872.54 | 325872.54 |  | 0 | 325872.54 |  |  | 4761
2026-06-12 11:38 | CUSTOM FENCE CO 002 | CO |  | 0 |  | -30623.77 | 0 |  | 2575292
13/26 | IDT30026C30000086 REDUCED MGT FEE 25264430 | HH |  | 0 | -8314.87 | -8314.87 | 0 |  |  | 6865
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 25264430
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency