## PROJECT
RESERVES:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR | 0
| FUNDING |  | GFFY2021 |  |  |  | DESIGN | 9665
| STATE RISK NUMBER |  | 00624 |  |  |  | INSPECTION | 897
| PROJECT TITLE |  | USDC RECREATION BLDG HIGH VOLTAGE SWITCH GEAR REPLACMENT - DESIGN |  |  |  | INSURANCE | 2385
| PROJECT # |  | 21279410 | CLOSED
| CODING BLOCK |  | 3000-300-3344-FXA-21279410 |  |  | 0 | TOTAL | 12947 | -12947
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
YR | CURRENT TOTALS |  | 2111168.33 | 0 | 2111168.33 | 2111168.33 | 0 | 0 |  |  | 0 | 0
[11 empty] | 0 | 0
| 1000-200-4755-KFC-7520-FSDC |  |  | 0 |  | 0 | 0
FY'21 |  |  |  | 0 |  | 0 | 0
2020-11-20 | IET TRNSF FY'21 CAP IMPR FUNDS FROM 21247300 | DF | 150000 | 150000 |  |  | 150000 |  |  | 4667
2021-04-14 | THOMAS & KOLKMAN ENGINEERING COMPANY, INC. - CONTRACT | N/A |  | 0 |  | 95000 | 0 |  | 2171125
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'22 |  |  |  | 0 |  | 0 | 0
2021-08-01 | IET TRNSF FY'22 CAP IMPR FUNDS FROM 22397300 | DF | 1739570 | 1739570 |  | 0 | 1739570 |  |  | 4667
2021-08-01 | IET TRNSF BUDGETED CONTINGENCY TO 21138300 | DF | -131948 | -131948 |  | 0 | -131948 |  |  | 4663
2021-08-01 | IET TRNSF LEGAL BUDGET TO 21257300 | DF |  | 0 | 1590 | 1590 | 0 |  |  | 6138
2021-10-18 | SKYLINE ELECTRIC COMPANY - CONTRACT | N/A |  | 0 |  | 1625455 | 0 |  | 2275159
2021-10-13 | SHUMS CODA ASSOCIATES INC - CONTRACT | N/A |  | 0 |  | 15000 | 0 |  | 2270253 |  | THE BID CAME IN OVER BUDGET WITH ALL THE ALTERNATES. I WOULD LIKE TO AWARD THE BASE BID WITH THE ALTERNATES. IF WE USE THE REMAINING FUNDS FROM THE CONSTRUCTION AND DESIGN WE ONLY NEED A COUPLE THOUSAND DOLLARS TO COVER THE DIFFERENCE. DARRELL APPROVED OF ME PROCEEDING AND HE WILL COVER THE DIFFERENCE.
2021-12-13 | SKYLINE ELEC GAX FC202112131932 | DF |  | 0 | 226081 | 0 | 0 |  | 2275199 | 6400
2021-12-13 | ZIONS/SKYLINE RTNG GAX FC202112131933 | DF |  | 0 | 11899 | 0 | 0 |  | 2275199 | 6400
2022-01-03 | SHUMS CODA GAX FC202112302238 | DF |  | 0 | 129.74 | 0 | 0 |  | 2270253 | 6139
2022-01-03 | IET TRNSF FUNDS FROM CONTG RESERVE 21138300 FOR CO 001 | DF | 27515 | 27515 |  | 0 | 27515 |  |  | 4664
2022-01-01 | SKYLINE ELECTRIC CO - CO 001 | CO |  | 0 |  | 27515 | 0 |  | 2275159
2022-01-27 | SHUMS CODA ASSOC GAX FC202201272728 | DF |  | 0 | 129.74 | 0 | 0 |  | 2270253 | 6139
2022-01-31 | SKYLINE ELEC GAX FC202201312790 | DF |  | 0 | 151914.7 | 0 | 0 |  | 2275159 | 6400
2022-01-31 | ZIONS/SKYLINE RTNG GAX FC202201312791 | DF |  | 0 | 7995.51 | 0 | 0 |  | 2275159 | 6400
2022-03-07 | SKYLINE ELEC GAX FC202203073472 | DF |  | 0 | 187625 | 0 | 0 |  | 2275159 | 6400
2022-03-07 | ZIONS/SKYLINE RTNG GAX FC202203073473 | DF |  | 0 | 9875 | 0 | 0 |  | 2275159 | 6400
2022-03-29 | SKYLINE ELEC GAX FC202203293892 | DF |  | 0 | 190000 | 0 | 0 |  | 2275159 | 6400
2022-03-29 | ZIONS/SKYLINE RTNG GAX FC202203293893 | DF |  | 0 | 10000 | 0 | 0 |  | 2275159 | 6400
2022-04-01 | SHUMS CODA GAX FC202204013980 | DF |  | 0 | 743.05 | 0 | 0 |  | 2270253 | 6139
2022-04-01 | IET TRNSF FUNDS FROM CONTG RESERVE 21138300 FOR CO 002 | DF | 7947.96 | 7947.96 |  | 0 | 7947.96 |  |  | 4664 |  | USDC FUNDING CHANGE ORDER FOR NEW GENERATOR $72,582.89
2022-04-08 | ITA 200 22*510 SHARE OF CO 002 | DF | 72582.89 | 72582.89 |  |  | 72582.89 |  |  | 4737 |  | Fund: 1000
2022-04-08 | SKYLINE ELEC CO 002 | CO |  | 0 |  | 80530.85 | 0 |  | 2275159 |  |  | Dept: 200
2022-04-27 | SKYLINE ELEC GAX FC202204274498 | DF |  | 0 | 87875 | 0 | 0 |  | 2275159 | 6400 |  | Unit: 4755
2022-04-27 | SKYLINE ELEC GAX FC202204274499 | DF |  | 0 | 4625 | 0 | 0 |  | 2275159 | 6400 |  | Appr: KFC
2022-05-03 | SHUMS CODA GAX FC202205034590 | DF |  | 0 | 318.21 | 0 | 0 |  | 2270253 | 6139 |  | Activity: FSDC
2022-06-06 | SHUMS CODA ASSOC GAX FC202206065507 | NP |  | 0 | 1220.95 | 0 | 0 |  | 2270253 | 6139
2022-06-06 | SKYLINE ELEC GAX FC202206065561 | NP |  | 0 | 47975 | 0 | 0 |  | 2275159 | 6400
2022-06-06 | ZIONS/SKYLINE RTNG GAX FC202206065562 | NP |  | 0 | 2525 | 0 | 0 |  | 2275159 | 6400
2022-06-22 | THOMAS & KOLKMAN ENG GAX FC202206226017 | NP |  | 0 | 80750 | 0 | 0 |  | 2171125 | 6137
2022-06-30 | SKYLINE ELEC CO GAX FC202206286302 | NP |  | 0 | 85975 | 0 | 0 |  | 2275159 | 6400
2022-06-30 | ZIONS/SKYLINE ELEC RTNG GAX FC202206286303 | NP |  | 0 | 4525 | 0 | 0 |  | 2275159 | 6400
13/22 | SHUMS CODA ASSOC GAX 22C9*670 | NP |  | 0 | 875.34 | 0 | 0 |  | 2270253 | 6139
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'23 |  |  |  | 0 |  | 0 | 0
2022-08-01 | SKYLINE ELEC GAX FC202208016578 | DF |  | 0 | 274550 | 0 | 0 |  | 2275159 | 6400
2022-08-01 | ZIONS/SKYLINE RTNG GAX FC202208016579 | DF |  | 0 | 14450 | 0 | 0 |  | 2275159 | 6400
2022-08-29 | SKYLINE ELEC GAX FC202208297561 | DF |  | 0 | 51775 | 0 | 0 |  | 2275159 | 6400
2022-08-29 | ZIONS/SKYLINE RTNG GAX FC202208297562 | DF |  | 0 | 2725 | 0 | 0 |  | 2275159 | 6400
2022-08-29 | IET TRNSF FUNDS FROM CONTG RESERVE 21138300 FOR CO 003 | DF | 11380.45 | 11380.45 |  | 0 | 11380.45 |  |  | 4664
2022-08-31 | SKYLINE ELEC CO 003 | CO |  | 0 |  | 11380.45 | 0 |  | 2275159
2022-09-01 | IET TRNSF FUNDS FROM CONTG RESERVE 21138300 FOR CO 004 | DF | 22287.87 | 22287.87 |  | 0 | 22287.87 |  |  | 4664
2022-09-19 | ROCKY MTN POWER GAX FC202209198418 | DF |  | 0 | 7630 | 7630 | 0 |  |  | 6400
2022-09-20 | SKYLINE ELEC CO 004 | CO |  | 0 |  | 22287.87 | 0 |  | 2275159
2022-09-27 | SKYLINE ELEC GAX FC20220928869 | DF |  | 0 | 91086.43 | 0 | 0 |  | 2275159 | 6400
2022-09-27 | ZIONS/SKYLINE RTNG GAX FC202209278870 | DF |  | 0 | 4794.02 | 0 | 0 |  | 2275159 | 6400
2022-10-01 | IET TRNSF FUNDS FROM CONTG RESERVE 21138300 FOR CO 005 | DF | 21024.89 | 21024.89 |  | 0 | 21024.89 |  |  | 4664
2022-10-26 | SKYLINE ELEC CO 005 | CO |  | 0 |  | 21024.89 | 0 |  | 2275159
2022-10-27 | SKYLINE ELEC GAX FC2022102710186 | DF |  | 0 | 47500 | 0 | 0 |  | 2275159 | 6400
2022-10-27 | ZIONS/SKYLINE RTNG GAX FC2022102710187 | DF |  | 0 | 2500 | 0 | 0 |  | 2275159 | 6400
2022-12-05 | SKYLINE ELEC GAX FC2022120511796 | DF |  | 0 | 66265.45 | 0 | 0 |  | 2275159 | 6400
2022-12-05 | ZIONS/SKYLINE RTNG GAX FC2022120511797 | DF |  | 0 | 3487.66 | 0 | 0 |  | 2275159 | 6400
2022-12-19 | SHUMS CODA GAX FC2022121912500 | DF |  | 0 | 94.91 | 0 | 0 |  | 2270253 | 6139
2022-12-29 | SKYLINE ELEC GAX FC2022122912961 | DF |  | 0 | 20425 | 0 | 0 |  | 2275159 | 6400
2022-12-29 | ZIONS/SKYLINE RTNG GAX FC2022122912962 | DF |  | 0 | 1075 | 0 | 0 |  | 2275159 | 6400
2023-02-08 | SKYLINE ELEC GAX300FC2023020814721 | DF |  | 0 | 23750 | 0 | 0 |  | 2275159 | 6400
2023-02-08 | ZIONS/SKYLINE RTNG GAX300FC2023020814722 | DF |  | 0 | 1250 | 0 | 0 |  | 2275159 | 6400
2023-02-22 | SKYLINE ELEC CO 006 | CO |  | 0 |  | 128478.7 | 0 |  | 2275159
2023-02-22 | IDT30023C3000058-MOVE FUNDING FROM 23166410 TO 21279410 | DF | -136109 | -136109 |  | 0 | -136109 |  |  | 4672
2023-03-06 | SHUMS CODA GAX FC2023030615854 | DF |  | 0 | 130.72 | 0 | 0 |  | 2270253 | 6139
2023-02-22 | IDT30023C3000062-TRNSF FUNDS FROM CONTG RESERVE 21138300 FOR CO 006 | DF | 28654.39 | 28654.39 |  | 0 | 28654.39 |  |  | 4672
2023-04-21 | SKYLINE ELEC GAX FCX2023042117817 | DF |  | 0 | 23750 | 0 | 0 |  | 2275159 | 6400
2023-04-21 | ZIONS/SKYLINE RTNG GAX FC2023042117818 | DF |  | 0 | 1250 | 0 | 0 |  | 2275159 | 6400
2023-04-26 | SHUMS CODA ASSOC GAX FC2023042618007 | DF |  | 0 | 208.72 | 0 | 0 |  | 2270253 | 6139
2023-04-26 | SKYLINE ELEC GAX FC2023042618019 | DF |  | 0 | 23750 | 0 | 0 |  | 2275159 | 6400
2023-04-26 | ZIONS/SKYLIN E RTNG GAX FC2023042618020 | DF |  | 0 | 1250 | 0 | 0 |  | 2275159 | 6400
2023-06-05 | SKYLINE ELEC GAX FC2023060519975 | DF |  | 0 | 9500 | 0 | 0 |  | 2275159 | 6400
2023-06-05 | ZIONS/SKYLINE RTNG GAX FC2023060519976 | DF |  | 0 | 500 | 0 | 0 |  | 2275159 | 6400
2023-05-10 | SKYLINE ELEC CO 007 | CO |  | 0 |  | 11617.14 | 0 |  | 2275159
2023-06-28 | THOMAS & KOLKMAN ENG GAX FC023062821154 | DF |  | 0 | 9500 | 0 | 0 |  | 2171125 | 6137
2023-06-29 | SHUMS CODA GAX FC2023062921260 | DF |  | 0 | 176.61 | 0 | 0 |  | 2270253 | 6139
13/23 | SHUMS CODA GAX FC2023071322319 |  |  | 0 | 71.81 | 0 | 0 |  | 2270253 | 6139
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'24 |  |  |  | 0 |  | 0 | 0
2023-08-15 | CMB CONSULTANTS GAX F23*059 | DF |  | 0 | 17983.31 | 17983.31 | 0 |  |  | 6400
2023-08-15 | SKYLINE ELEC GAX F23*060 | DF |  | 0 | 946.49 | 0 | 0 |  | 2275159 | 6400
2023-08-23 | SKYLINE ELEC GAX F23*082 | DF |  | 0 | 17983.31 | 0 | 0 |  | 2275159 | 6400
2023-09-06 | IET150240224900003222 TECH HOURLY RATE | DF |  | 0 | 1716.27 | 1716.27 | 0 |  |  | 6360
2023-09-06 | IET150240224900005310 COMM PARTS | DF |  | 0 | 313.78 | 313.78 | 0 |  |  | 6374
2023-09-01 | CR 24M5*022 WRONG VNDR PD ORIG CK#14438432 | DF |  | 0 | -17983.31 | -17983.31 | 0 |  |  | 6400
2023-10-17 | SKYLINE ELEC GAX FC2023101726396 | DF |  | 0 | 107269.37 | 0 | 0 |  | 2275159 | 6400
2023-10-17 | ZIONS/SKYLINE RTNG GAX FC2023101726397 | DF |  | 0 | 5645.76 | 0 | 0 |  | 2275159 | 6400
2023-10-22 | ITA 300 24*020 IRRIGATION REPAIRS | DF |  | 0 | 2560 | 2560 | 0 |  |  | 6400
2023-11-07 | SHUMS CODA GAX FC2023110727330 | DF |  | 0 | 915.17 | 0 | 0 |  | 2270253 | 6139
2023-12-14 | ITA 24*042 MATERIAL | DF |  | 0 | 2051.72 | 2051.72 | 0 |  |  | 6400
2023-12-14 | ITA 24*042 LABOR | DF |  | 0 | 1391.04 | 1391.04 | 0 |  |  | 6400
2023-12-14 | ITA 24*044 LABOR | DF |  | 0 | 2718.48 | 2718.48 | 0 |  |  | 6400
2024-01-23 | THOMAS & KOLKMAN AMD 001 | CO |  | 0 |  | 12500 | 0 |  | 2171125
2024-02-08 | ENVIRO ABATEMENT GAX FC2024020831609 | DF |  | 0 | 49688 | 49688 | 0 |  |  | 6404
2024-03-13 | ITA 24*085 COFC INS | DF |  | 0 | 1625.46 | 1625.46 | 0 |  |  | 6263
2024-03-15 | R&R ENVIRO GAX FC2024031533192 | DF |  | 0 | 4806.33 | 4806.33 | 0 |  |  | 6404
2024-05-02 | SKYLINE ELEC CO 008 | CO |  | 0 |  | -5944.62 | 0 |  | 2275159
2024-05-20 | SKYLINE ELEC GAX FC2024052036421 | DF |  | 0 | 91177.75 | 0 | 0 |  | 2275159 | 6400
2024-05-20 | ZIONS/SKYLINE RTNG GAX FC2024052036422 | DF |  | 0 | 4798.83 | 0 | 0 |  | 2275159 | 6400
2024-05-22 | SHUMS CODA GAX FC2024052236590 | DF |  | 0 | 217 | 0 | 0 |  | 2270253 | 6139
2024-05-22 | SHUMS CODA AMD 001 | CO |  | 0 |  | -9768.03 | 0 |  | 2270253
13/24 | THOMAS & KILKMAN ENG GAX FC2024070339272 |  |  | 0 | 17250 | 0 | 0 |  | 2171125 | 6137
FY'25
2024-11-15 | PROJ CLOSE PROJ RES FROM 21137300 TO 21279410 | DF | 36708.91 | 36708.91 |  | 0 | 36708.91 |  |  | 4666
2024-11-15 | PROJ CLOSE INSPECTIONS FROM 21279410 TO 20473300 | DF | -10665.03 | -10665.03 |  | 0 | -10665.03 |  |  | 4667
2025-01-17 | REV IDT 23C3*58 FROM 23166410 TO 21279410 | EH | 136109 | 136109 |  | 0 | 136109 |  |  | 4672
2025-01-17 | MOVE FUNDING FROM 23166410 TO 21279410 | EH | 136109 | 136109 |  | 0 | 136109 |  |  | 4672
|  |  |  | 0 |  | 0 | 0
| PROJECT CLOSED |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 21279410
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency