## PROJECT
RESERVES:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR/HAZ MAT | -5.8208e-10 |  |  |  |  | 2070009 | 293230 | TRUE
| FUNDING |  | HEF USU |  |  |  | DESIGN | -2.0464e-10 |  |  |  |  | 2070246 | 1736844.23 | TRUE
| STATE RISK NUMBER | [5 empty] | USU MOU | 0 |  |  |  |  | 2075072 | 33113092.66 | TRUE
| PROJECT TITLE |  | USU MOUNTAIN VIEW RESIDENCE HALL REPLACEMENT |  |  |  | INSPECTION/INSURANCE/DFCM MNGT/COMMISSIONING | 324894.92 |  |  |  |  | 2070293 | 62800 | TRUE
| PROJECT # |  | 20067770 | CLOSED |  |  | CONTINGENCY/LEGAL/OTHER | 1065453.83 |  |  |  |  | 2070294 | 178417.24 | TRUE
| CODING BLOCK |  | 3000-300-3401-FWA-20067770 |  |  | -2473.88 | TOTAL | 1390348.75 | -1387874.87 |  |  |  | 2075294 | 2594778.77 | TRUE
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ |  |  | 2070260 | 95806.57 | TRUE
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV | 2075197 | 0 | TRUE
38243125.73
YR | CURRENT TOTALS |  | 38243125.73 | 0 | 38243125.73 | 38240651.85 | 2473.88 | 38243125.73 |  |  | 38243125.73
0
|  |  |  | 0 |  | 0 | 0
FY'20 |  |  |  | 0 |  | 0 | 0 | [8 empty] | 2070009 | 293230
2019-07-01 | METHOD STUDIO - PROGRAMMING | N/A |  | 0 |  | 292130 | 0 |  | 2070009 | [6 empty] | 2070246 | 1736844.23
2019-07-29 | METHOD STUDIO GAX 20C5-028 | DF |  | 0 | 73032.5 | 0 | 0 |  | 2070009 | 6864 | [5 empty] | 2075072 | 33113092.66
2019-08-22 | METHOD STUDIO GAX 20C9-51 | DF |  | 0 | 116852 | 0 | 0 |  | 2070009 | 6864 | [5 empty] | 2070293 | 62800
2019-09-03 | FED EXPRESS CO GOVT SALES GAX 20C5-3 | DF |  | 0 | 6.85 | 6.85 | 0 |  |  | 6811 | [5 empty] | 2070294 | 178417.24
2019-09-03 | FED EXPRESS CO GOVT SALES GMA 20C5-3 | DF |  | 0 | 8.27 | 8.27 | 0 |  |  | 6811 | [5 empty] | 2075294 | 2594778.77
2019-09-03 | FED EXPRESS CO GOVT SALES GMA 20C5-3 | N/A |  | 0 | 6.85 | 6.85 | 0 |  |  | 6811 | [5 empty] | 2070260 | 95806.57
2019-08-28 | METHOD STUDIO AMD 001 | CO |  | 0 |  | 1100 | 0 |  | 2070009 | [6 empty] | 2075197 | 0
2019-09-25 | METHOD STUDIO GAE 20C5-570 | DF |  | 0 | 88739 | 0 | 0 |  | 2070009 | 6864 | [5 empty] | 2075294 | 2594778.77
2019-09-25 | IET USU ESTIMATED REVENUE | DF | 41600000 | 41600000 |  | 0 | 41600000 |  |  | 4761
2019-10-30 | RE 20C3-74 BILL $278,645.47 | N/A |  | 0 |  | 0 | 0 |  |  |  | 278645.47
2019-11-01 | METHOD STUDIO GAX 20C5-1090 | DF |  | 0 | 14606.5 | 0 | 0 |  | 2070009 | 6864
2019-11-15 | IDT 20C3*008 PRJ MGR FEE | DF |  | 0 | 97588 | 97588 | 0 |  |  | 6865
2019-12-03 | CR 20M2-060 RE 20C3-074 | N/A |  | 0 |  | 0 | 0 | 278645.47
2019-12-16 | RE 20C3*115 BILL $112,194.50 | N/A |  | 0 |  | 0 | 0 |  |  |  | 112194.5
2020-01-02 | TOTAL BUILDING COMMISSIONING GAX 20C8*154 | DF |  | 0 | 8932 | 8932 | 0 |  |  | 6849
2020-01-02 | FEDEX GOVT SALES GMA 20C5*030 | DF |  | 0 | 14.24 | 14.24 | 0 |  |  | 6879
2019-12-19 | METHOD STUDIO CONTRACT | CO |  | 0 |  | 1715890 | 0 |  | 2070246
2020-01-14 | RE 20C3*159 BILL $8,946.24 | N/A |  | 0 |  | 0 | 0 |  |  |  | 8946.24
2019-09-05 | JACOBSEN CONSTRUCTION CONTRACT | N/A |  | 0 |  | 90000 | 0 |  | 2075072
2020-01-22 | METHOD STUDIO GAX 20C7*385 | DF |  | 0 | 137666.5 | 0 | 0 |  | 2070246 | 6861
2020-01-22 | METHOD STUDIO GAX 20C7*386 | DF |  | 0 | 137666.5 | 0 | 0 |  | 2070246 | 6861
2020-01-22 | METHOD STUDIO GAX 20C7*388 | DF |  | 0 | 85294.5 | 0 | 0 |  | 2070246 | 6861
2020-01-22 | METHOD STUDIO GAX 20C7*387 | DF |  | 0 | 151139 | 0 | 0 |  | 2070246 | 6861
2020-02-01 | COFC INSURANCE ITA 300-2*037 | DF |  | 0 | 17874.51 | 17874.51 | 0 |  |  | 6872
2020-01-27 | CR 20M2-078 RE 20C3-139 | N/A |  | 0 |  | 0 | 0 | 112194.5
2020-02-18 | RE 20C3*200 BILL $529,641.01 | N/A |  | 0 |  | 0 | 0 |  |  |  | 529641.01
2020-01-27 | ARCHITECTURAL TESTING CONTRACT | N/A |  | 0 |  | 62800 | 0 |  | 2070293
2020-02-03 | NEDERLAND REGRIDGERATION CONTRACT | N/A |  | 0 |  | 180900 | 0 |  | 2070294
2020-02-20 | METHOD STUDIO GAX 20C5*2065 | DF |  | 0 | 85294.5 | 0 | 0 |  | 2070246 | 6861
2020-03-03 | TOTAL BLDG COMMISSIONING GAX 20C7*642 | DF |  | 0 | 3542 | 3542 | 0 |  |  | 6849
2020-02-24 | CR 20M2-088 RE 20C3-159 | N/A |  | 0 |  | 0 | 0 | 8946.24
2020-03-10 | RE 20C3*232 BILL 88,836.50 | N/A |  | 0 |  | 0 | 0 |  |  |  | 88836.5
2020-03-19 | ARCHITECTURAL TESTING GAX 20C5*2219 | DF |  | 0 | 1200 | 0 | 0 |  | 2070293 | 6849
2020-03-24 | METHOD STUDIO GAX 20C5*2257 | DF |  | 0 | 204706 | 0 | 0 |  | 2070246 | 6861
2020-03-30 | CR 20M2-103 RE 20C3-200 | N/A |  | 0 |  | 0 | 0 | 529641.01
2020-02-01 | USU AMA | N/A |  | 0 |  | 5202261 | 0 |  | 2075294
2020-04-13 | RE 20C3*263 BILL $205,906.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 205906
2020-04-13 | IET INCREASE USU ESTIMATED REVENUE | DF | 785212 | 785212 |  | 0 | 785212 |  |  | 4761
2020-04-21 | METHOD STUDIO GAX 20C8*487 | DF |  | 0 | 204706.8 | 0 | 0 |  | 2070246 | 6861
2020-04-21 | ARCHITECTURAL TESTING GAX 20C8*481 | DF |  | 0 | 380 | 0 | 0 |  | 2070293 | 6849
2020-04-28 | NEDERLAND REF A/C & HEATING GAX 20C5*2719 | DF |  | 0 | 14426.54 | 0 | 0 |  | 2070294 | 6849
2020-04-28 | SUNRISE ENGINEERING, INC. - CONTRACT | N/A |  | 0 |  | 216303.1 | 0 |  | 2070260
2020-05-13 | RE 20C3*303 BILL $219,513.34 | N/A |  | 0 |  | 0 | 0 |  |  |  | 219513.34
2020-05-11 | WC3 GAX 20C5*975 | DF |  | 0 | 110 | 110 | 0 |  |  | 6861
2020-05-27 | METHOD STUDIO GAX 20C5*3133 | DF |  | 0 | 239734.4 | 0 | 0 |  | 2070246 | 6861
2020-04-20 | CR 20M2-109 RE 20C3-232 | N/A |  | 0 |  | 0 | 0 | 88836.5
2020-05-22 | CR 20M2-117 RE 20C3-263 | N/A |  | 0 |  | 0 | 0 | 205906
2020-06-02 | ARCHITECTURAL TESTING GAX 20C5*3248 | DF |  | 0 | 570 | 0 | 0 |  | 2070293 | 6849
2020-06-02 | ARCHITECTURAL TESTING GAX 20C5*3249 | DF |  | 0 | 4560 | 0 | 0 |  | 2070293 | 6849
2020-06-02 | NEDERLAND REF A/C & HEAT GAX 20C5*3250 | DF |  | 0 | 780 | 0 | 0 |  | 2070294 | 6849
2020-06-12 | RE 20C3*341 BILL $245,754.40 | N/A |  | 0 |  | 0 | 0 |  |  |  | 245754.4
2020-06-18 | CR 20M2-123 RE 20C3-303 | N/A |  | 0 |  | 0 | 0 | 219513.34
2019-09-03 | FED EXPRESS CO GOVT SALES GMA 20C5-3 (listed twice) | N/A |  | 0 | -6.85 | -6.85 | 0 |  |  | 6811
2020-06-25 | METHOD STUDIO GAX 20C5*3687 | PG |  | 0 | 35288.79 | 0 | 0 |  | 2070246 | 6861
2020-07-01 | NEDERLAND REF A/C & HEAT GAX 20C5*3757 | PG |  | 0 | 3399.5 | 0 | 0 |  | 2070294 | 6849
13/20 | JACOBSEN CONSTRUCTION CO 001 | CO |  | 0 |  | 955504 | 0 |  | 2075072
13/20 | TOTAL BUILDING COMMISSIONING GAX 20C7*1007 | PG |  | 0 | 2002 | 2002 | 0 |  |  | 6849
13/20 | RE 20C3*385 BILL $40,683.44 | N/A |  | 0 |  | 0 | 0 |  |  |  | 40683.44
13/20 | NEDERLAND REF A/C & HEAT GAX 20C7*1084 | PG |  | 0 | 6695.91 | 0 | 0 |  | 2070294 | 6849
13/20 | ARCHITECTURAL TESTING GAX 20C7*1081 | PG |  | 0 | 4845 | 0 | 0 |  | 2070293 | 6849
13/20 | WC3 GAX 20C5*3879 | PG |  | 0 | 3630 | 3630 | 0 |  |  | 6861
2020-06-30 | CR 20M2-126 RE 20C3-341 | N/A |  | 0 |  | 0 | 0 | 245754.4
13/20 | JACOBSEN CONSTRUCTION GAX 20C8*724 | PG |  | 0 | 318153.74 | 0 | 0 |  | 2075072 | 6811
13/20 | ZIONS/JACOBSEN CONST RTNG GAX 20C8*725 | PG |  | 0 | 16744.95 | 0 | 0 |  | 2075072 | 6811
13/20 | SUNRISE ENGINEERING GAX 20C7*1037 | PG |  | 0 | 3574.65 | 0 | 0 |  | 2070260 | 6873
13/20 | NEDERLAND REF A/C & HEAT GAX 20C5*3906 | PG |  | 0 | 330 | 0 | 0 |  | 2070294 | 6849
2020-03-24 | LINE 48 METHOD STUDIO GAX 20C5*2257 TO CORRECT AMT | PG |  | 0 | 0.8 | 0 | 0 |  | 2070246 | 6861
13/20 | USU CONTROLLER'S OFFC GAX 20C5*3960 | PG |  | 0 | 843 | 0 | 0 |  | 2075294 | 6824
13/20 | RE 20C3*430 BILL $354,818.05 | N/A |  | 0 |  | 0 | 0 |  |  |  | 354818.05
|  |  |  | 0 |  | 0 | 0
FY'21 |  |  |  | 0 |  | 0 | 0
2020-08-11 | WC3 GAX 21C5*135 | DF |  | 0 | 220 | 220 | 0 |  |  | 6861
2020-08-19 | ZIONS/JACOBSEN CONST RTNG GAX 21C5*217 | DF |  | 0 | 8676.02 | 0 | 0 |  | 2075072 | 6811
2020-08-19 | JACOBSEN CONST GAX 21C5*218 | DF |  | 0 | 164844.35 | 0 | 0 |  | 2075072 | 6811
2020-08-24 | SUNRISE ENGINEERING GAX 21C5*253 | DF |  | 0 | 3958.95 | 0 | 0 |  | 2070260 | 6873
2020-08-25 | METHOD STUDIO GAX 21C5*262 | DF |  | 0 | 110289.85 | 0 | 0 |  | 2070246 | 6861
2020-07-31 | CR 21M2*008 RE 20C3-385 | N/A |  | 0 |  | 0 | 0 | 40683.44
2020-08-18 | CR 21M2-014 RE 20C3-430 | N/A |  | 0 |  | 0 | 0 | 354818.05
2020-09-11 | RE 21C3*020 BILL $287,989.17 | N/A |  | 0 |  | 0 | 0 |  |  |  | 287989.17
2020-09-23 | NEDERLAND REF A/C & HEAT CORP GAX 21C8*083 | DF |  | 0 | 900.92 | 0 | 0 |  | 2070294 | 6849
2020-09-28 | SUNRISE ENGINEERING GAX 21C5*474 | DF |  | 0 | 533.31 | 0 | 0 |  | 2070260 | 6873
2020-09-28 | IDT30021C3000001 NSF PROJECT MANAGER FEES | DF |  | 0 | 97588 | 97588 | 0 |  |  | 6865
2020-10-20 | IDT REVERSE DUPLICATE PRJ MANAGER FEES CHARGE | DF |  | 0 | -97588 | -97588 | 0 |  |  | 6865
2020-10-05 | METHOD STUDIO GAX 21C7*212 | DF |  | 0 | 11332 | 0 | 0 |  | 2070246 | 6861
2020-10-14 | RE 21C3*54 BILL $12,766.23 | N/A |  | 0 |  | 0 | 0 |  |  |  | 12766.23
2020-10-16 | GREEN BUSINESS CERTIFICATION GAX 21C7*252 | DF |  | 0 | 1500 | 1500 | 0 |  |  | 6811
2020-10-26 | JACOBSEN CONSTRUCTION CO 002 | CO |  | 0 |  | 31062088.39 | 0 |  | 2075072
2020-10-28 | METHOD STUDIO GA 21C8*110 | DF |  | 0 | 11361.23 | 0 | 0 |  | 2070246 | 6861
2020-10-29 | ZIONS/JACOBSEN CONST RTNG GAX 21C7*361 | DF |  | 0 | 28314.48 | 0 | 0 |  | 2075072 | 6811
2020-10-29 | JACOBSEN CONST GAX 21C7*362 | DF |  | 0 | 537975 | 0 | 0 |  | 2075072 | 6811
2020-11-05 | ZIONS/JACOBSEN CONST RTNG GAX 21C7*399 | DF |  | 0 | 45989.71 | 0 | 0 |  | 2075072 | 6811
2020-11-05 | JACOBSEN CONST GAX 21C7*400 | DF |  | 0 | 873804.35 | 0 | 0 |  | 2075072 | 6811
2020-11-13 | SUNRISE ENG GAX 21C7*452 | DF |  | 0 | 2063.72 | 0 | 0 |  | 2070260 | 6873
2020-11-13 | ZIONS/JACOBSEN CONST RTNG GAX 21C7*460 | DF |  | 0 | 43345.07 | 0 | 0 |  | 2075072 | 6811
2020-11-13 | JACOBSEN CONST GAX 21C7*461 | DF |  | 0 | 823556.04 | 0 | 0 |  | 2075072 | 6811
2020-11-20 | RE 21C3*88 BILL $2,367,909.60 | N/A |  | 0 |  | 0 | 0 |  |  |  | 2367909.6
2020-11-24 | SUNRISE ENG GAX 21C5*826 | DF |  | 0 | 9840.46 | 0 | 0 |  | 2070260 | 6873
2020-11-27 | METHOD STUDIO GAX 21C5*874 | DF |  | 0 | 11361.23 | 0 | 0 |  | 2070246 | 6861
2020-11-18 | CR 21M2*043 RE 21C3*054 | N/A |  | 0 |  | 0 | 0 | 12766.23
2020-10-23 | CR 21M2*035 RE 21C3*020 | N/A |  | 0 |  | 0 | 0 | 287989.17
2020-12-01 | NEDERLAND REF A/C & HEAT GAX 21C5*925 | DF |  | 0 | 2631.84 | 0 | 0 |  | 2070294 | 6849
2020-12-01 | NEDERLAND REF A/C & HEAT GAX 21C5*926 | DF |  | 0 | 3033.92 | 0 | 0 |  | 2070294 | 6849
2020-12-14 | RE 21C3*120 BILL $26,867.45 | N/A |  | 0 |  | 0 | 0 |  |  |  | 26867.45
2020-12-19 | SUNRISE ENG GAX 21C7*702 | DF |  | 0 | 10020.08 | 0 | 0 |  | 2070260 | 6873
2020-12-22 | USU GAX 21C7*728 | DF |  | 0 | 62622.32 | 0 | 0 |  | 2075294 | 6824
2020-12-29 | METHOD STUDIO GAX 21C5*1157 | DF |  | 0 | 13313.73 | 0 | 0 |  | 2070246 | 6861
2020-12-30 | CR 21M2*052 RE 21C3*088 | N/A |  | 0 |  | 0 | 0 | 2367909.6 |  | 4760
2021-01-15 | RE 21C3*153 BILL $85,956.13 | N/A |  | 0 |  | 0 | 0 |  |  |  | 85956.13
2021-01-15 | NEDERLAND REF A/C & HEAT CORP GAX 21C8*330 | DF |  | 0 | 4776.92 | 0 | 0 |  | 2070294 | 6849
2021-01-15 | NEDERLAND REF A/C & HEAT CORP GAX 21C8*331 | DF |  | 0 | 8848.44 | 0 | 0 |  | 2070294 | 6849
2021-01-25 | JACOBSEN CONST GAX 21C8*387 | DF |  | 0 | 1249357.19 | 0 | 0 |  | 2075072 | 6811
2021-01-25 | ZIONS/JACOBSEN CONST RTNG GAX 21C8*388 | DF |  | 0 | 65755.66 | 0 | 0 |  | 2075072 | 6811
2021-01-27 | METHOD STUDIO GAX 21C8*416 | DF |  | 0 | 12873.73 | 0 | 0 |  | 2070246 | 6861
2021-01-25 | JACOBSEN CONST GAX 21C8*385 | DF |  | 0 | 1011638.77 | 0 | 0 |  | 2075072 | 6811
2021-01-25 | ZIONS/JACOBSEN RTNG GAX 21C8*386 | DF |  | 0 | 53244.15 | 0 | 0 |  | 2075072 | 6811
2021-01-28 | CR 21M2*060 RE 21C3*120 | N/A |  | 0 |  | 0 | 0 | 26867.45 |  | 4760
2021-02-11 | RE 21C3*190 BILL $2,406,494.86 | N/A |  | 0 |  | 0 | 0 |  |  |  | 2406494.86
2021-02-09 | ZIONS/JACOBSEN CONST RTNG GAX 21C5*1492 | DF |  | 0 | 99599.8 | 0 | 0 |  | 2075072 | 6811
2021-02-09 | JACOBSEN CONST GAX 21C5*1493 | DF |  | 0 | 1892396.11 | 0 | 0 |  | 2075072 | 6811
2021-02-23 | JACOBSEN CONST CO 003 | CO |  | 0 |  | 712387.35 | 0 |  | 2075072
2021-02-24 | USU GAX 21C7*1034 | DF |  | 0 | 36416.66 | 0 | 0 |  | 2075294 | 6824
2021-02-26 | ARCHITECTURAL TESTING GAX 21C7*1042 | DF |  | 0 | 2255 | 0 | 0 |  | 2070293 | 6849
2021-02-26 | ARCHITECTURAL TESTING GAX 21C7*1043 | DF |  | 0 | 1110 | 0 | 0 |  | 2070293 | 6849
2021-02-25 | SUNRISE ENG GAX 21C8*505 | DF |  | 0 | 7617.21 | 0 | 0 |  | 2070260 | 6873
2021-02-26 | CR 21M2*067 RE 21C3*153 | N/A |  | 0 |  | 0 | 0 | 85956.13 |  | 4760
2021-03-12 | JACOBSEN CONST GAX 21C8*535 | DF |  | 0 | 1788888.59 | 0 | 0 |  | 2075072 | 6811
2021-03-12 | ZONS/JACOBSEN CONST RTNG GAX 21C8*536 | DF |  | 0 | 94152.03 | 0 | 0 |  | 2075072 | 6811
2021-03-16 | RE 21C3*229 BILL $3,922,435.40 | N/A |  | 0 |  | 0 | 0 |  |  |  | 3922435.4
2021-03-22 | USU CO 001 | CO |  | 0 |  | 150000 | 0 |  | 2075294
2021-03-19 | CR 21M5*004 RE 21C3*190 | N/A |  | 0 |  | 0 | 0 | 2406494.86 |  | 4760
2021-03-22 | USU CONTROLLER'S OFFC GAX 21C7*1210 | DF |  | 0 | 18208.33 | 0 | 0 |  | 2075294 | 6824
2021-03-23 | SUNRISE ENG GAX 21C7*1231 | DF |  | 0 | 6907.89 | 0 | 0 |  | 2070260 | 6873
2021-03-25 | METHOD STUDIO GAX 21C5*1819 | DF |  | 0 | 12373.73 | 0 | 0 |  | 2070246 | 6861
2021-03-30 | ARCHITECTURAL TESTING GAX 21C5*1841 | DF |  | 0 | 1235 | 0 | 0 |  | 2070293 | 6849
2021-03-30 | ARCHITECTURAL TESTING GAX 21C5*1842 | DF |  | 0 | 4250 | 0 | 0 |  | 2070293 | 6849
2021-03-30 | NEDERLAND REF A/C & HEATING GAX 21C5*1843 | DF |  | 0 | 5609.82 | 0 | 0 |  | 2070294 | 6849
2021-03-30 | NEDERLAND REF A/C & HEATING GAX 21C5*1844 | DF |  | 0 | 5963.05 | 0 | 0 |  | 2070294 | 6849
2021-03-31 | SUNRISE ENG GAX 21C7*1250 | DF |  | 0 | 7692.96 | 0 | 0 |  | 2070260 | 6873
2021-04-16 | RE 21C3*265 BILL $62,240.78 | N/A |  | 0 |  | 0 | 0 |  |  |  | 62240.78
2021-04-15 | ZIONS/JACOBSEN CONST RTNG GAX 21C5*1971 | DF |  | 0 | 70253.37 | 0 | 0 |  | 2075072 | 6811
2021-04-15 | JACOBSEN CONST GAX 21C5*1972 | DF |  | 0 | 1334814.19 | 0 | 0 |  | 2075072 | 6811
2021-04-22 | METHOD STUDIO GAX 21C5*2044 | DF |  | 0 | 11361.23 | 0 | 0 |  | 2070246 | 6861
2021-04-23 | SUNRISE ENG GAX 21C5*2053 | DF |  | 0 | 6500.55 | 0 | 0 |  | 2070260 | 6873
2021-04-30 | JACOBSEN CONST CO 004 | CO |  | 0 |  | -71804.56 | 0 |  | 2075072
2021-04-28 | CR21M2*077 RE 21C3*229 | N/A |  | 0 |  | 0 | 0 | 3922435.4 |  | 4760
2021-05-13 | ZIONS/JACOBSEN CONST RTNG GAX 21C5*2220 | DF |  | 0 | 96532.13 | 0 | 0 |  | 2075072 | 6811
2021-05-13 | JACOBSEN CONST GAX 21C5*2221 | DF |  | 0 | 1834110.44 | 0 | 0 |  | 2075072 | 6811
2021-05-19 | RE 21C3*298 BILL 3,353,571.91 | N/A |  | 0 |  | 0 | 0 |  |  |  | 3353571.91
2021-05-21 | CR 21M2*085 RE 21C3*265 | N/A |  | 0 |  | 0 | 0 | 62240.78 |  | 4760
2021-05-24 | METHOD STUDIO GAX 21C9*182 | DF |  | 0 | 11361.23 | 0 | 0 |  | 2070246 | 6861
2021-05-25 | UTAH STATE UNIV GAX 21C7*1556 | DF |  | 0 | 36475.66 | 0 | 0 |  | 2075294 | 6824
2021-06-01 | NEDERLAND REF A/C & HEAT GAX 21C9*224 | DF |  | 0 | 9728.42 | 0 | 0 |  | 2070294 | 6849
2021-06-01 | NEDERLAND REF A/C & HEAT GAX 21C9*225 | DF |  | 0 | 6494.45 | 0 | 0 |  | 2070294 | 6849
2021-06-01 | ARCHITECTURAL TESTING GAX 21C9*228 | DF |  | 0 | 8850 | 0 | 0 |  | 2070293 | 6849
2021-06-08 | METHOD STUDIO AMD 001 | CO |  | 0 |  | 3000 | 0 |  | 2070246
2021-06-08 | SUNRISE ENG GAX 21C9*318 | NP |  | 0 | 4520.16 | 0 | 0 |  | 2070260 | 6873
2021-06-14 | RE 21C3*330 BILL $77,429.92 | N/A |  | 0 |  | 0 | 0 |  |  |  | 77429.92
2021-06-21 | METHOD STUDIO GAX 21C9*483 | NP |  | 0 | 14361.23 | 0 | 0 |  | 2070246 | 6861
2021-06-29 | USU GAX 21C5*2397 | NP |  | 0 | 18208.33 | 0 | 0 |  | 2075294 | 6824
13/21 | NEDERLAND REF A/C & HEATING GAX 21C9*747 | NP |  | 0 | 4652.57 | 0 | 0 |  | 2070294 | 6849
13/21 | NEDERLAND REF A/C & HEATING GAX 21C9*748 | NP |  | 0 | 6558.96 | 0 | 0 |  | 2070294 | 6849
13/21 | NEDERLAND REF A/C & HEATING GAX 21C9*757 | NP |  | 0 | 778.5 | 0 | 0 |  | 2070294 | 6849
13/21 | SUNRISE ENG GAX 21C9*765 | NP |  | 0 | 6344.59 | 0 | 0 |  | 2070260 | 6873
13/21 | ZIONS/JACOBSEN CONST RTNG GAX 21C7*1794 | NP |  | 0 | 118153.59 | 0 | 0 |  | 2075072 | 6811
13/21 | JACOBSEN CONST GAX 21C7*1795 | NP |  | 0 | 2244918.25 | 0 | 0 |  | 2075072 | 6811
13/21 | ZIONS/JACOBSEN CONST RTNG GAX 21C7*1796 | NP |  | 0 | 99376.4 | 0 | 0 |  | 2075072 | 6811
13/21 | JACOBSEN CONST GAX 21C7*1797 | NP |  | 0 | 1888151.45 | 0 | 0 |  | 2075072 | 6811
2021-06-23 | CR 21M2*095 RE 21C3*298 | N/A |  | 0 |  | 0 | 0 | 3353571.91 |  | 4760
2021-06-30 | CR 21M2*097 RE 21C3*330 | N/A |  | 0 |  | 0 | 0 | 77429.92 |  | 4760
13/21 | RE 21C3*369 BILL $4,401,503.87 | N/A |  | 0 |  | 0 | 0 |  |  |  | 4401503.87
13/21 | SUNRISE ENG GAX 21C9*872 | NP |  | 0 | 5126.03 | 0 | 0 |  | 2070260 | 6873
13/21 | USU GAX 21C5*2505 | NP |  | 0 | 18208.33 | 0 | 0 |  | 2075294 | 6824
13/21 | ARCHITECTURAL TESTING GAX 2C7*1895 | NP |  | 0 | 3875 | 0 | 0 |  | 2070293 | 6849
13/21 | RE 21C3*402 BILL $27,209.36 | N/A |  | 0 |  | 0 | 0 |  |  |  | 27209.36
|  |  |  | 0 |  | 0 | 0
FY'22 |  |  |  | 0 |  | 0 | 0
2021-07-20 | METHOD STUDIO GAX 22C9*014 | DF |  | 0 | 11361.23 | 0 | 0 |  | 2070246 | 6861
2021-08-10 | CMT ENG LABS GAX 22C9*085 | DF |  | 0 | 300 | 300 | 0 |  |  | 6861
2021-08-20 | ZIONS/JACOBSEN CONST RTNG GAX 22C5*125 | DF |  | 0 | 120679.79 | 0 | 0 |  | 2075072 | 6811
2021-08-20 | JACOBSEN CONST GAX 22C5*126 | DF |  | 0 | 2292915.95 | 0 | 0 |  | 2075072 | 6811
2021-08-12 | CR 22M2*010 RE 21C3*402 | N/A |  | 0 |  | 0 | 0 | 27209.36 |  | 4760
2021-08-12 | CR 22M2*010 RE 21C3*369 | N/A |  | 0 |  | 0 | 0 | 4401503.87 |  | 4760
2021-08-25 | METHOD STUDIO GAX 22C9*145 | DF |  | 0 | 13847.48 | 0 | 0 |  | 2070246 | 6861
2021-09-01 | ARCHITECTURAL TESTING GAX 22C7*078 | DF |  | 0 | 1200 | 0 | 0 |  | 2070293 | 6849
2021-09-02 | USU GAX 22C5*177 | DF |  | 0 | 57626.87 | 0 | 0 |  | 2075294 | 6824
2021-09-10 | NEDERLAND REF A/C & HEAT CORP GAX 22C5*106 | DF |  | 0 | 3550.95 | 0 | 0 |  | 2070294 | 6849
2021-09-10 | ZIONS/JACOBSEN CONST RTNG GAX 22C7*091 | DF |  | 0 | 73753.55 | 0 | 0 |  | 2075072 | 6811
2021-09-10 | JACOBSEN CONST GAX 22C7*092 | DF |  | 0 | 1401316.88 | 0 | 0 |  | 2075072 | 6811
2021-09-14 | RE 22C3*20 BILL $3,976,552.70 | N/A |  | 0 |  | 0 | 0 |  |  |  | 3976552.7
2021-09-23 | JACOBSEN CONST CO 005 | CO |  | 0 |  | -116000 | 0 |  | 2075072
2021-09-29 | ARCHI TESTING GAX FC20210928236 | DF |  | 0 | 1200 | 0 | 0 |  | 2070293 | 6849
2021-09-29 | METHOD STUDIO GAX FC20210928276 | DF |  | 0 | 11361.23 | 0 | 0 |  | 2070246 | 6861
2021-10-01 | SUNRISE ENG GAX FC20210930370 | DF |  | 0 | 4841.98 | 0 | 0 |  | 2070260 | 6873
2021-10-18 | RE 22C3*47 BILL $17,403.03 | N/A |  | 0 |  | 0 | 0 |  |  |  | 17403.03
2021-10-04 | SUNRISE ENG GAX FC20211004475 | DF |  | 0 | 3164.84 | 0 | 0 |  | 2070260 | 6873
2021-10-26 | METHOD STUDIO GAX FC20211026934 | DF |  | 0 | 11361.23 | 0 | 0 |  | 2070246 | 6861
2021-11-05 | USU GAX FC202111051184 | DF |  | 0 | 73036.21 | 0 | 0 |  | 2075294 | 6824
2021-11-08 | SUNRISE ENG GAX FC202111081210 | DF |  | 0 | 494.95 | 0 | 0 |  | 2070260 | 6873
2021-11-09 | JACOBSEN CONST GAX FC202111091329 | DF |  | 0 | 1612920.79 | 0 | 0 |  | 2075072 | 6811
2021-11-09 | ZIONS/JACOBSEN CONST RTNG GAX FC202111091330 | DF |  | 0 | 84890.57 | 0 | 0 |  | 2075072 | 6811
2021-10-25 | CR 22M2*027 RE 22C3*020 PARTIAL PMT | N/A |  | 0 |  | 0 | 0 | 397652.7 |  | 4760
2021-11-11 | JACOBSEN CONST GAX FC202111111372 | DF |  | 0 | 1506328.15 | 0 | 0 |  | 2075072 | 6811
2021-11-11 | ZIONS/JACOBSEN RTNG GAX FC20211111373 | DF |  | 0 | 79280.43 | 0 | 0 |  | 2075072 | 6811
2021-11-15 | RE 22C3*080 BILL $3,371,477.17 | N/A |  | 0 |  | 0 | 0 |  |  |  | 3371477.17
2021-11-15 | ARCHITECTURAL TESTING GAX FC202111151387 | DF |  | 0 | 4880 | 0 | 0 |  | 2070293 | 6849
2021-11-15 | NEDERLAND A/C & HEAT GAX FC202111151388 | DF |  | 0 | 4151.34 | 0 | 0 |  | 2070294 | 6849
2021-11-17 | NEDERLAND A/C & HEAT GAX FC202111171463 | DF |  | 0 | 8208.86 | 0 | 0 |  | 2070294 | 6849
2021-11-23 | NEDERLAND REF A/C GAX FC202111231534 | DF |  | 0 | 3656.2 | 0 | 0 |  | 2070294 | 6849
2021-11-23 | METHOD STUDIO GAX FC202111231535 | DF |  | 0 | 11361.23 | 0 | 0 |  | 2070246 | 6861
2021-11-24 | ARCHITECTURAL TEST GAX FC2021FC202111241556 | DF |  | 0 | 3700 | 0 | 0 |  | 2070293 | 6849
2021-11-29 | WC3 GAX 22C5*259 | DF |  | 0 | 330 | 330 | 0 |  |  | 6861
2021-11-24 | CR 22M2*034 RE 22C3*020 PARTIAL PMT | N/A |  | 0 |  | 0 | 0 | 3578900 |  | 4760
2021-11-23 | CR 22M2*033 RE 22C3*047 | N/A |  | 0 |  | 0 | 0 | 17403.03 |  | 460
2021-12-03 | SUNRISE ENG GAX FC202112031700 | DF |  | 0 | 1124.73 | 0 | 0 |  | 2070260 | 6873
2021-11-01 | JACOBSEN CONSTR CO INC - CO 006 | CO |  | 0 |  | 437494.99 | 0 |  | 2075072
2021-12-20 | RE 22C3*113 BILL $37,412.36 | N/A |  | 0 |  | 0 | 0 |  |  |  | 37412.36
2021-12-20 | WC3 GAX 22C5*281 | DF |  | 0 | 220 | 220 | 0 |  |  | 6861
2021-12-21 | METHOD STUDIO GAX FC202112212057 | DF |  | 0 | 11361.23 | 0 | 0 |  | 2070246 | 6861
2021-12-22 | USU GAX FC202112222118 | DF |  | 0 | 257275.49 | 0 | 0 |  | 2075294 | 6824
2022-01-03 | ARCHITECTURAL TESTING GAX FC202112302207 | DF |  | 0 | 1200 | 0 | 0 |  | 2070293 | 6849
2022-01-03 | NEDERLAND REF A/C & HEAT GAX FC202112302211 | DF |  | 0 | 4798.9 | 0 | 0 |  | 2070294 | 6849
2021-12-22 | CR 22M2*041 RE 22C3*080 | N/A |  | 0 |  | 0 | 0 | 3371477.17 |  | 4760
2022-01-06 | JACOBSEN CONST GAX FC202201062337 | DF |  | 0 | 1230477.51 | 0 | 0 |  | 2075072 | 6811
2022-01-06 | ZONS/JACOBSEN RTNG GAX FC202201062338 | DF |  | 0 | 64761.97 | 0 | 0 |  | 2075072 | 6811
2022-01-07 | SUNRISE ENG GAX FC202201072370 | DF |  | 0 | 572.85 | 0 | 0 |  | 2070260 | 6873
2022-01-12 | METHOD STUDIO GAX FC202201122469 | DF |  | 0 | 11361.23 | 0 | 0 |  | 2070246 | 6861
2022-01-18 | RE 22C3*149 BILL $1,582,029.18 | N/A |  | 0 |  | 0 | 0 |  |  |  | 1582029.18
2022-01-18 | JACOBSEN CONST GAX FC20220118253 | DF |  | 0 | 1337091.67 | 0 | 0 |  | 2075072 | 6811
2022-01-18 | ZIONS/JACOBSEN RTNG GAX FC202201182544 | DF |  | 0 | 70373.24 | 0 | 0 |  | 2075072 | 6811
2022-01-25 | SUNRISE ENG GAX FC202201252648 | DF |  | 0 | 926.79 | 0 | 0 |  | 2070260 | 6873
2022-01-31 | USU GAX FC202201312796 | DF |  | 0 | 18468.33 | 0 | 0 |  | 2075294 | 6824
2022-01-27 | CR 22M5*003 RE 22C3*113 | N/A |  | 0 |  | 0 | 0 | 37412.36 |  | 4760
2022-02-02 | ARCHITECTURAL TESTING GAX FC202202022848 | DF |  | 0 | 451 | 0 | 0 |  | 2070293 | 6849
2022-02-09 | JACOBSEN CONST GAX FC202202093008 | DF |  | 0 | 922925.54 | 0 | 0 |  | 2075072 | 6811
2022-02-09 | ZIONS/JACOBSEN RTNG GAX FC202202093009 | DF |  | 0 | 48575.03 | 0 | 0 |  | 2075072 | 6811
2022-02-18 | RE 22C3*178 BILL $2,398,811.60 | N/A |  | 0 |  | 0 | 0 |  |  |  | 2398811.6
2022-02-18 | SUNRISE ENG GAX FC202202183153 | DF |  | 0 | 692.79 | 0 | 0 |  | 2070260 | 6873
2022-02-25 | METHOD STUDIO GAX FC202202253251 | DF |  | 0 | 11361.23 | 0 | 0 |  | 2070246 | 6861
2022-02-28 | USU GAX FC202202283272 | DF |  | 0 | 116623.79 | 0 | 0 |  | 2075294 | 6824
2022-03-02 | CR 22M5*014 RE 22C3*149 | N/A |  | 0 |  | 0 | 0 | 1582029.18 |  | 4760
2022-03-07 | NEDERLAND REF A/C GAX FC202203073433 | DF |  | 0 | 7133.67 | 0 | 0 |  | 2070294 | 6849
2022-03-07 | ARCHI TESTING GAX FC20220307335 | DF |  | 0 | 1395 | 0 | 0 |  | 2070293 | 6849
2022-03-09 | NEDERLAND REF A/C GAX FC202203093552 | DF |  | 0 | 9236.22 | 0 | 0 |  | 2070294 | 6849
2022-03-11 | RE 22C3*207 BILL $146,442.70 | N/A |  | 0 |  | 0 | 0 |  |  |  | 146442.7
2022-03-16 | JACOBSEN CONST GAX FC202203163645 | DF |  | 0 | 1311258.38 | 0 | 0 |  | 2075072 | 6811
2022-03-16 | ZINOS/JACOBSEN RTNG GAX FC202203163646 | DF |  | 0 | 69013.6 | 0 | 0 |  | 2075072 | 6811
2022-03-22 | METHOD STUDIO GAX FC202203223738 | DF |  | 0 | 11361.23 | 0 | 0 |  | 2070246 | 6861
2022-03-24 | CR 22M5*025 RE 22C3*178 | N/A |  | 0 |  | 0 | 0 | 2398811.6 |  | 4760
2022-04-04 | SUNRISE ENG GAX FC202204043997 | DF |  | 0 | 671.82 | 0 | 0 |  | 2070260 | 6873
2022-04-06 | JACOBSEN CONST GAX FC202204064079 | DF |  | 0 | 963403.12 | 0 | 0 |  | 2075072 | 6811
2022-04-06 | ZIONS/JACOBSEN RTNG GAX FC202204064080 | DF |  | 0 | 50705.44 | 0 | 0 |  | 2075072 | 6811
2022-04-11 | RE 22C3*242 BILL $2,406,413.59 | N/A |  | 0 |  | 0 | 0 |  |  |  | 2406413.59
2022-04-08 | JACOBSEN CONST CO 007 | CO |  | 0 |  | 45128.92 | 0 |  | 2075072
2022-04-21 | SUNRISE ENG GAX FC202204214335 | DF |  | 0 | 1841.81 | 0 | 0 |  | 2070260 | 6873
2022-04-25 | METHOD STUDIO GAX FC202204254449 | DF |  | 0 | 11361.23 | 0 | 0 |  | 2070246 | 6861
2022-05-04 | USU GAX FC202205044676 | DF |  | 0 | 113868.53 | 0 | 0 |  | 2075294 | 6824
2022-05-10 | RE 22C3*278 BILL $127,071.57 | N/A |  | 0 |  | 0 | 0 |  |  |  | 127071.57
2022-05-12 | JACOBSEN CONST GAX FC202205124947 | DF |  | 0 | 873080.39 | 0 | 0 |  | 2075072 | 6811
2022-05-12 | ZIONS/JACOBSEN CONST RTNG GAX FC202205124948 | DF |  | 0 | 45951.6 | 0 | 0 |  | 2075072 | 6811
2022-05-16 | SUNRISE ENG GAX FC202205165009 | DF |  | 0 | 1451.5 | 0 | 0 |  | 2070260 | 6873
2022-05-16 | METHOD STUDIO GAX FC202205165004 | DF |  | 0 | 11361.73 | 0 | 0 |  | 2070246 | 6861
2022-05-12 | CR 22M5*052 RE 22C3*207 | N/A |  | 0 |  | 0 | 0 | 146442.7 |  | 4760
2022-05-25 | ARCHI TESTING GAX FC202205255237 | DF |  | 0 | 1200 | 0 | 0 |  | 2070293 | 6849
2022-05-25 | NEDERLAND REF A/C GAX FC202205255238 | DF |  | 0 | 5640.89 | 0 | 0 |  | 2070294 | 6849
2022-05-31 | NEDERLAND REF A/C GAX FC202205315360 | DF |  | 0 | 6911.45 | 0 | 0 |  | 2070294 | 6849
2022-05-20 | CR 22M5*057 RE 22C3*242 | N/A |  | 0 |  | 0 | 0 | 2406413.59 |  | 4760
2022-06-06 | NEDERLAND REF A/C & HEAT GAX FC202206065542 | NP |  | 0 | 4765.79 | 0 | 0 |  | 2070294 | 6849
2022-06-14 | RE 22C3*312 BILL $950,363.35 | N/A |  | 0 |  | 0 | 0 |  |  |  | 950363.35
2022-06-23 | METHOD STUDIO GAX FC202206236094 | NP |  | 0 | 11361.23 | 0 | 0 |  | 2070246 | 6861
2022-06-30 | SUNRISE ENG GAX 22C9*504 | NP |  | 0 | 1384.79 | 0 | 0 |  | 2070260 | 6873
13/22 | RE 22C3*347 BILL $12,746.20 | N/A |  | 0 |  | 0 | 0 |  |  |  | 12746.2
13/22 | SUNRISE ENG GAX 22C9*616 | NP |  | 0 | 2949.75 | 0 | 0 |  | 2070260 | 6873
13/22 | JACOBSEN CONST GAX 22C9*631 | NP |  | 0 | 535802.51 | 0 | 0 |  | 2075072 | 6811
13/22 | ZIONS/JACOBSEN RTNG GAX 22C9*632 | NP |  | 0 | 28200.15 | 0 | 0 |  | 2075072 | 6811
2022-06-23 | CR 22M5*072 RE 22C3*278 | N/A |  | 0 |  | 0 | 0 | 127071.57 |  | 4760
13/22 | JACOBSEN CONST GAX 22C7*217 | NP |  | 0 | 748036.92 | 0 | 0 |  | 2075072 | 6811
13/22 | ZIONS/JACOB SEN RTHG GAX 22C7*218 | NP |  | 0 | 39370.37 | 0 | 0 |  | 2075072 | 6811
13/22 | USU GAX 22C9*791 | NP |  | 0 | 67829.35 | 0 | 0 |  | 2075294 | 6824
13/22 | RE 22C3*382 BILL $1,422,189.05 | N/A |  | 0 |  | 0 | 0 |  |  |  | 1422189.05
|  |  |  | 0 |  | 0 | 0
FY'23 |  |  |  | 0 |  | 0 | 0
2022-08-10 | USU GAX F22*029 | DF |  | 0 | 17063.35 | 0 | 0 |  | 2075197 | 6824
2022-08-10 | ARCHITECTURAL TESTING GAX F22*031 | DF |  | 0 | 7300 | 0 | 0 |  | 2070293 | 6849
2022-07-08 | CR 23M5*001 RE 22C3*312 | N/A |  | 0 |  | 0 | 0 | 950363.35 |  | 4760
2022-07-29 | CR 23M5*009 RE 22C3*347 | N/A |  | 0 |  | 0 | 0 | 12746.2 |  | 4760
2022-08-04 | CR 23M5*011 RE 22C3*382 | N/A |  | 0 |  | 0 | 0 | 1422189.05 |  | 4760
2022-08-17 | METHOD STUDIO GAX FC202208177158 | DF |  | 0 | 11361.23 | 0 | 0 |  | 2070246 | 6861
2022-08-17 | JACOBSEN CONST GAX FC202208177177 | DF |  | 0 | 306807.44 | 0 | 0 |  | 2075072 | 6811
2022-08-17 | ZIONS/JACOBSEN RTNG GAX FC202208177178 | DF |  | 0 | 16147.76 | 0 | 0 |  | 2075072 | 6811
2022-08-30 | SUNRISE ENG GAX FC202208307584 | DF |  | 0 | 987.41 | 0 | 0 |  | 2070260 | 6873
2022-08-31 | SUNRISE ENG AMD 001 | CO |  | 0 |  | -120496.53 | 0 |  | 2070260
2022-09-12 | USU GAX FC202209128010 | DF |  | 0 | 666618.37 | 0 | 0 |  | 2075294 | 6824
2022-09-15 | RE 23C3*24 BILL $1,026,285.56 MOD TO $1,009,222.21 PER LINE 313 | N/A |  | 0 |  | 0 | 0 |  |  |  | 1009222.21
2022-09-19 | JACOBSEN CONST GAX FC202209198520 | DF |  | 0 | 206311.88 | 0 | 0 |  | 2075072 | 6811
2022-09-19 | ZIONS/JACOBSEN RTNG GAX FC202209198521 | DF |  | 0 | 10858.52 | 0 | 0 |  | 2075072 | 6811
2022-08-10 | USU GAX F22*029 XFER TO PROJECT 20070070 | DF |  | 0 | -17063.35 | 0 | 0 |  | 2075197 | 6824
2022-09-21 | METHOD STUDIO GAX FC202209218630 | DF |  | 0 | 11361.23 | 0 | 0 |  | 2070246 | 6861
2022-09-26 | NEDERLAND REF A/C & HEAT GAX FC202209268793 | DF |  | 0 | 21426.74 | 0 | 0 |  | 2070294 | 6849
2022-09-27 | NEDERLAND REF A/C & HEAT GAX FC202209278833 | DF |  | 0 | 15800.35 | 0 | 0 |  | 2070294 | 6849
2022-10-05 | JACOBSEN CONST CO 008 | CO |  | 0 |  | 40935.72 | 0 |  | 2075072
2022-10-18 | RE 23C3*65 BILL $265,758.72 | N/A |  | 0 |  | 0 | 0 |  |  |  | 265758.72
2022-10-08 | METHOD STUDIO GAX FC202210189714 | DF |  | 0 | 11361.23 | 0 | 0 |  | 2070246 | 6861
2022-10-21 | USU GAX FC202210219910 | DF |  | 0 | 134846.71 | 0 | 0 |  | 2075294 | 6824
2022-10-21 | USU GAX FC202210219911 | DF |  | 0 | 229240.55 | 0 | 0 |  | 2075294 | 6824
2022-10-21 | CR 23M5*039 RE 23C3*024 | N/A |  | 0 |  | 0 | 0 | 1009222.21 |  | 4760
2022-11-15 | NEDERLAND REF A/C AMD 001 | CO |  | 0 |  | 2465 | 0 |  | 2070294
2022-11-18 | RE 23C3*103 BILL $375,448.49 | N/A |  | 0 |  | 0 | 0 |  |  |  | 375448.49
2022-11-21 | METHOD STUDIO GAX FC2022112111254 | DF |  | 0 | 6500 | 0 | 0 |  | 2070246 | 6861
2022-11-29 | CR 23M5*051 RE 23C3*065 | N/A |  | 0 |  | 0 | 0 | 265758.72 |  | 4760
2022-12-12 | USU GAX FC2022121212252 | DF |  | 0 | 25860.88 | 0 | 0 |  | 2075294 | 6824 |  | COMMITMENTS CHECKED TO THIS POINT
2022-12-16 | RE 23C3*139 BILL $32,360.88 | N/A |  | 0 |  | 0 | 0 |  |  |  | 32360.88
2022-12-19 | JACOBSEN CONST GAX FC2022121912544 | DF |  | 0 | 58004.81 | 0 | 0 |  | 2075072 | 6811
2022-12-23 | JACOBSEN CONST GAX FC2022122312831 | DF |  | 0 | 64507.44 | 0 | 0 |  | 2075072 | 6811
2022-12-23 | ZIONS/JACOBSEN RTNG GAX FC2022122312832 | DF |  | 0 | 3395.13 | 0 | 0 |  | 2075072 | 6811
2023-01-12 | METHOD STUDIO AMD 002 | CO |  | 0 |  | 2295 | 0 |  | 2070246
2023-01-13 | RE 23C3*169 BILL $125,907.38 | N/A |  | 0 |  | 0 | 0 |  |  |  | 125907.38
2023-01-13 | USU GAX FC2023011313590 | DF |  | 0 | 411392.28 | 0 | 0 |  | 2075294 | 6824
2023-01-23 | METHOD STUDIO GAX FC2023012313902 | DF |  | 0 | 8795 | 0 | 0 |  | 2070246 | 6861
2023-02-10 | USU GAX FC2023020914822 | DF |  | 0 | 1827.6 | 0 | 0 |  | 2075294 | 6824
2023-02-28 | RE 23C3*206 BILL $422,014.88 | N/A |  | 0 |  | 0 | 0 |  |  |  | 422014.88
2023-02-23 | METHOD STUDIO GAX FC2023022315446 | DF |  | 0 | 6500 | 0 | 0 |  | 2070246 | 6861
2023-01-24 | CR 23M5*072 RE 23C3*139 | N/A |  | 0 |  | 0 | 0 | 32360.88 |  | 4760
2023-01-31 | CR 23M5*075 RE 23C3*103 | N/A |  | 0 |  | 0 | 0 | 375448.49 |  | 4760
2023-02-28 | CR 23M5*084 RE 23C3*169 | N/A |  | 0 |  | 0 | 0 | 125907.38 |  | 4760
2023-03-22 | JACOBSEN CONST GAX FC2023032216546 | DF |  | 0 | 97412.26 | 0 | 0 |  | 2075072 | 6811
2023-03-22 | ZIONS/JACOBSEN RTNG GAX FC2023032216547 | DF |  | 0 | 5126.96 | 0 | 0 |  | 2075072 | 6811
2023-03-24 | METHOD STUDIO GAX FC2023032416656 | DF |  | 0 | 5155.25 | 0 | 0 |  | 2070246 | 6861
2023-04-12 | RE 23C3*241 BILL $114,194.47 | N/A |  | 0 |  | 0 | 0 |  |  |  | 114194.47
2023-04-14 | USU GAX FX2023041417538 | DF |  | 0 | 220208.91 | 0 | 0 |  | 2075294 | 6824
2023-04-21 | METHOD STUDIO GAX F2023042117804 | DF |  | 0 | 7409.8 | 0 | 0 |  | 2070246 | 6861
2023-04-12 | CR 23M5*115 RE 23C3*206 | N/A |  | 0 |  | 0 | 0 | 422014.88 |  | 4760
2023-03-26 | METHOD STUDIO AMD 003 | CO |  | 0 |  | 3193.18 | 0 |  | 2070246
2023-05-18 | RE 23C3*277 BILL $227,618.71 | N/A |  | 0 |  | 0 | 0 |  |  |  | 227618.71
2023-05-24 | CR 23M5*131 RE 23C3*241 | N/A |  | 0 |  | 0 | 0 | 114194.47 |  | 4760
2023-06-07 | ARCHI TESTING GAX FC2023060620011 | DF |  | 0 | 3559 | 0 | 0 |  | 2070293 | 6849
2023-06-15 | RE 23C3*311 BILL $3,559.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 3559
2023-06-20 | ARCHI TESTING GAX FC2023061620722 | DF |  | 0 | 3585 | 0 | 0 |  | 2070293 | 6849
2023-06-30 | RE 23C3*339 BILL $3,585.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 3585
2023-06-23 | CR 23M5*146 RE 23C3*277 | N/A |  | 0 |  | 0 | 0 | 227618.71 |  | 4760
13/23 | USU GAX FC2023071322370 | TR |  | 0 | 9072.27 | 0 | 0 |  | 2075294 | 6824
13/23 | RE 23C3*389 BILL $9,072.27 | N/A |  | 0 |  | 0 | 0 |  |  |  | 9072.27
|  |  |  | 0 |  | 0 | 0
FY'24 |  |  |  | 0 |  | 0 | 0
2023-07-05 | CR 23M5*148 RE 23C3*311 | N/A |  | 0 |  | 0 | 0 | 3559 |  | 4760
2023-07-28 | CR 24M5*007 RE 23C3*339 | N/A |  | 0 |  | 0 | 0 | 3585 |  | 4760
2023-08-17 | CR 24M5*015 RE 23C3*389 | N/A |  | 0 |  | 0 | 0 | 9072.27 |  | 4760
2023-08-29 | METHOD STUDIO GAX FC2023082924197 | DF |  | 0 | 18092 | 0 | 0 |  | 2070246 | 6861
2023-09-13 | RE 24C3*22 BILL $18,092.00 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 18092
2023-10-02 | METHOD STUDIO GAX FC2023100225692 | DF |  | 0 | 3500 | 0 | 0 |  | 2070246 | 6861
2023-10-18 | RE 24C3*57 BILL $3,500.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 3500
2023-10-30 | CR 24M5*044 RE 24C3*022 | N/A |  | 0 |  | 0 | 0 | 18092 |  | 4760
2023-11-29 | CR 24M5*056 RE 24C3*057 | N/A |  | 0 |  | 0 | 0 | 3500 |  | 4760
2024-02-20 | JACOBSEN CONST CO 009 | CO |  | 0 |  | -42642.15 | 0 |  | 2075072
2024-05-07 | TOTAL BLDG COMM GAX FC2024050735796 | DF |  | 0 | 924 | 924 | 0 |  |  | 6849
2024-05-20 | RE 24C3*262 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 924
2024-06-28 | CR 24M5*126 RE 24C3*262 | N/A |  | 0 |  | 0 | 0 | 924 |  | 4760
|  |  |  | 0 |  | 0 | 0
FY'25 |  |  |  | 0 |  | 0 | 0
2024-08-06 | IDT 25C3*001 XFER LEGAL FEES TO 21257300 | DF |  | 0 | 16863 | 16863 | 0 |  |  | 6870
2024-09-30 | RE 25C3*27 | N/A |  | 0 |  | 0 | 0 |  |  |  | 16863
2024-10-31 | CR 25M5*042 RE 25C3*027 | N/A |  | 0 |  | 0 | 0 | 16863 |  | 4760
2025-01-21 | GREEN BUSINESS CERT GAX300FC2025012148362 | EH |  | 0 | 8783.97 | 8783.97 | 0 |  |  | 6849
2025-01-23 | JACOBSEN CONST GAX300FC2025012348577 | EH |  | 0 | 30661.08 | 0 | 0 |  | 2075072 | 6811
2025-02-05 | RE 25C3*174 | N/A |  | 0 |  |  | 0 |  |  | 4760 | 39445.05
2025-03-18 15:23 | USU MOUNTAIN VIEW RESIDENCE HALL REPLACEMENT CR30025M5000087 | TR |  | 0 |  | 0 | 0 | 39445.05 |  | 4760
2025-04-08 | GREEN BUSINESS CERTIFICATION INC GAX300FC2025040851971 | HH |  | 0 | 2833.54 | 2833.54 | 0 |  |  | 6811
2025-05-08 | RE 25C3*262 | N/A |  | 0 |  |  | 0 |  |  | 4760 | 2833.54
2025-06-10 | CR30025M5000127 | N/A |  | 0 |  | 0 | 0 | 2833.54 |  | 4760
2022-05-10 | CR 22M5*072 RE 22C3*278 | N/A |  | 0 |  | 0 | 0 | 127071.57 |  | 4760
|  |  |  | 0 |  | 0 | 0
FY'26 |  |  |  | 0 |  | 0 | 0
2026-02-07 | METHOD STUDIO GAX300FC2026020665756 CONTRACT 2070246-USU MOUNTAIN VIEW RESIDENCE HALL REPLACEMNT | HH |  | 0 | 6500 | 0 | 0 |  | 2070246 | 6861
2026-02-04 | USU CO 002 | CO |  | 0 |  | -2757482.23 | 0 |  | 2075294
2026-03-05 | RE 26C3*248 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 6500
2023-07-17 | METHOD STUDIO AMD 004 | CO |  | 0 |  | 19620 | 0 |  | 2070246
2026-02-18 | METHOD STUDIO AMD 005 | CO |  | 0 |  | -7153.95 | 0 |  | 2070246
2026-02-19 | NEDERLAND REF A/C AMD 001 | CO |  | 0 |  | -2473.88 | 0 |  | 2070294
2026-03-20 | IDT USU ESTIMATED REVENUE - 20067770 CLOSEOUT BALANCE | TR | -4142086.27 | -4142086.27 |  | 0 | -4142086.27
2026-03-03 | NEDERLAND REF A/C AMD 002 | CO |  | 0 |  | -2473.88 | 0 |  | 2070294
2026-04-18 | USU CONTROLLERS OFFICE ATTN GLEN SCHMIDT CR30026M5000074 20067770 USU MOUNTAIN VIEW RESIDENCE HALL REPLACEMENT | HH |  | 0 |  | 0 | 0 | 6500 |  | 4760
2026-07-31 | IDT30026000000316 CHANGING REVENUE_SOURCE TO 4658 |  | 6500 | 6500 |  | 0 | 6500 |  |  | 4658
2026-07-31 | IDT30026000000316 CHANGING REVENUE_SOURCE TO 4658 |  | -6500 | -6500 |  | 0 | -6500 |  |  | 4760
2026-07-31 | IDT30026000000316 CHANGING REVENUE_SOURCE TO 4658 |  | -6500 | -6500 |  | 0 | -6500 |  |  | 4658
2026-07-31 | IDT30026000000316 CHANGING REVENUE_SOURCE TO 4658 |  | 6500 | 6500 |  | 0 | 6500 |  |  | 4760
2026-07-31 | IDT30026000000321 CHANGING REVENUE_SOURCE TO 4658 |  | 6500 | 6500 |  | 0 | 6500 |  |  | 4658
2026-07-31 | IDT30026000000321 CHANGING REVENUE_SOURCE TO 4658 |  | -6500 | -6500 |  | 0 | -6500 |  |  | 4760
|  |  |  | 0 |  | 0 | 0
FY'27 |  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0
0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 20067770
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency