## PROJECT
RESERVES:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR | 0
| FUNDING |  | HEF USU |  |  |  | DESIGN | 0
| STATE RISK NUMBER | [5 empty] | FFE/INFO TECH/MOVING | 0 | AMA
| PROJECT TITLE |  | USU NEW INFORMATION TECHNOLOGY SERVICES BUILDING |  |  |  | INSPECTION/INSURANCE/DFCM MANAGEMENT | 50742
| PROJECT # |  | 20070770 | CLOSED |  |  | CONTINGENCY/LEGAL/COMMISSIONING /USER FEES | 56390.09 | AMA
| CODING BLOCK |  | 3000-300-3401-FWA-20070770 |  |  | 0 | TOTAL | 107132.09 | -107132.09
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
12009082.08
YR | CURRENT TOTALS |  | 12009082.08 | 0 | 12009082.08 | 12009082.08 | 0 | 12009082.84 |  |  | 12009082.08
0
|  |  |  | 0 |  | 0 | 0
FY'19 |  |  |  | 0 |  | 0 | 0
13/19 | FEDEX GMA 19C2-001 | PG |  | 0 | 15.24 | 15.24 | 0 |  |  | 6879
13-19 | IET USU EST REV | DW | 7700000 | 7700000 |  | 0 | 7700000 |  |  | 4761
13/19 | RE 19C3-413 BILL $15.24 | N/A |  | 0 |  | 0 | 0 |  |  |  | 15.24
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'20 |  |  |  | 0 |  | 0 | 0
2019-08-02 | CR 20M2-013 RE 19C3-413 | N/A |  | 0 |  | 0 | 0 | 15.24
2019-09-03 | FED EXPRESS CO GOVT SALES GMA 20C5-3 | DF |  | 0 | 7.27 | 7.27 | 0 |  |  | 6811
2019-09-03 | FED EXPRESS CO GOVT SALES GMA 20C5-3 | DF |  | 0 | 6.85 | 6.85 | 0 |  |  | 6811
2019-09-24 | RE 20C3 *28 BILL $14.12 | N/A |  | 0 |  | 0 | 0 |  |  |  | 14.12
2019-09-24 | MHTN ARCHITECTS INC - PROGRMAMING | N/A |  | 0 |  | 68250 | 0 |  | 2070018
2019-11-04 | MHTN ARCHITECTS GAX 20C5-1142 | DF |  | 0 | 62950 | 0 | 0 |  | 2070018 | 6864
2019-11-04 | IET INCREASED USU EST REV | DF | 3519560 | 3519560 |  | 0 | 3519560 |  |  | 4761
2019-10-24 | CR 20M2-045 RE 20C3-028 | N/A |  | 0 |  | 0 | 0 | 14.12
2019-11-05 | IDT 20C3*008 PRJ MGR FEE | DF |  | 0 | 50000 | 50000 | 0 |  |  | 6865
2019-11-19 | MHTN ARCHITECTS AMD 001 | CO |  | 0 |  | 23482 | 0 |  | 2070018
2019-12-16 | RE 20C3*120 BILL $112,950.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 112950
2020-01-02 | MHTN ARCHITECTS GAX 20C7*045 | DF |  | 0 | 23482 | 0 | 0 |  | 2070018 | 6864
2019-12-05 | MHTN ARCHITECTS CONTRACT | CO |  | 0 |  | 545379 | 0 |  | 2070245
2020-01-14 | RE 20C3*160 BILL $23,482.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 23482
2019-08-27 | BIG D CONSTRUCTION CONTRACT | N/A |  | 0 |  | 25000 | 0 |  | 2075071
2019-11-01 | USU AMA FOR FFE, IT, MNGT FEE, ETC | N/A |  | 0 |  | 1869891 | 0 |  | 2075197
2020-01-29 | MHTN ARCHITECTS GAX 20C5*1908 | DF |  | 0 | 57697.56 |  | 0 |  | 20780245 | 6861
2020-02-01 | COFC INSURANCE ITA 300 2-037 | PG |  | 0 | 4292.08 | 4292.08 | 0 |  |  | 6872
2020-01-27 | CR 20M2-078 RE 20C3-120 | N/A |  | 0 |  | 0 | 0 | 112950
2020-02-14 | MHTN ARCHITECTS GAX 20C7*539 | DF |  | 0 | 5300 | 0 | 0 |  | 2070018 | 6861
2020-02-18 | RE 20C3*201 BILL $9,592.08 | N/A |  | 0 |  | 0 | 0 |  |  |  | 9592.08
2020-02-03 | NEW VISION CONSTRUCTION CONTRACT | N/A |  | 0 |  | 53500 | 0 |  | 2070297
2020-03-03 | MHTN ARCHITECTS GAX 20C8*298 | DF |  | 0 | 48081.3 | 0 | 0 |  | 2070245 | 6861
2020-02-24 | CR 20M2-088 RE 20C3-160 | N/A |  | 0 |  | 0 | 0 | 23482
2020-03-10 | RE 20C3* 233 BILL 48,081.30 | N/A |  | 0 |  | 0 | 0 |  |  |  | 48081.3
2020-03-19 | CR 20M2-101 RE 20C3-201 | N/A |  | 0 |  | 0 | 0 | 9592.08
2020-04-13 | RE 20C3*264 BILL $57,697.56 | N/A |  | 0 |  | 0 | 0 |  |  |  | 57697.56
2020-04-21 | MHTN ARCHITECTS INC GAX 20C8*476 | DF |  | 0 | 72121.95 | 0 | 0 |  | 2070245 | 6861
2020-04-23 | MHTN ARCHITECTS INC GAX 20C5*2676 | DF |  | 0 | 38465.04 | 0 | 0 |  | 2070245 | 6861
2020-04-20 | CR 20M2-108 RE 20C3-233 | N/A |  | 0 |  | 0 | 0 | 48081.3
2020-05-13 | RE 20C3*304 BILL $110,586.99 | N/A |  | 0 |  | 0 | 0 |  |  |  | 110586.99
2020-05-28 | MHTN ARCHITECTS GAX 20C5*3197 | DF |  | 0 | 48081.3 | 0 | 0 |  | 2070245 | 6861
2020-05-22 | CR 20M2-117 RE 20C3-264 | N/A |  | 0 |  | 0 | 0 | 57697.56
2020-06-12 | RE 20C3*342 BILL 48,081.30 | N/A |  | 0 |  | 0 | 0 |  |  |  | 48081.3
2020-06-16 | MHTN ARCHITECTS GAX 20C5*3512 | PG |  | 0 | 96162.6 | 0 | 0 |  | 2070245 | 6861
2020-06-18 | CR 20M2-123 RE 20C3-304 | N/A |  | 0 |  | 0 | 0 | 110586.99
13/20 | MHTN ARCHITECTS INC GAX 20SC5*3774 | PG |  | 0 | 12020.33 | 0 | 0 |  | 2070245 | 6861
13/20 | RE 20C3*386 BILL $108,182.93 | N/A |  | 0 |  | 0 | 0 |  |  |  | 108182.93
13/20 | UTAH NEW VISION CONST GAX 20C8*759 | PG |  | 0 | 3000 | 0 | 0 |  | 2070297 | 6849
13/20 | WC3 GAX 20C5*3879 | PG |  | 0 | 880 | 880 | 0 |  |  | 6861
2020-06-30 | CR 20M2-126 RE 20C3-342 | N/A |  | 0 |  | 0 | 0 | 48081.3
13-20 | IET INCREASED USU EST REV | NP | 957881 | 957881 |  | 0 | 957881 |  |  | 4761
13/20 | RE 20C3*431 BILL $3,880.00 FINAL FY20 (ERROR) | N/A |  | 0 |  | 0 | 0 |  |  |  | 0
13/20 | RE 20C3*447 BILL $3,880.00 FINAL FY20 CORRECTION | N/A |  | 0 |  | 0 | 0 |  |  |  | 3880
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'21 |  |  |  | 0 |  | 0 | 0
2020-08-19 | MHTN ARCHITECTS GAX 21C5*214 | DF |  | 0 | 37742.82 | 0 | 0 |  | 2070245 | 6861
2020-09-01 | BIG D CONSTRUCTION CORP CO 001 | CO |  | 0 |  | 8963548 | 0 |  | 2075071
2020-07-31 | CR 21M2-008 RE 20C3-386 | N/A |  | 0 |  | 0 | 0 | 108182.93
2020-08-18 | CR 21M2-014 RE 20C3-447 | N/A |  | 0 |  | 0 | 0 | 3880
2020-09-11 | RE 21C3*021 BILL $37,742.82 | N/A |  | 0 |  | 0 | 0 |  |  |  | 37742.82
2020-08-27 | CONSOLIDATED ENGINEERING LABS - CONTRACT | N/A |  | 0 |  | 80897 | 0 |  | 2070180
2020-10-05 | MHTN ARCHITECTS GAX 21C7*203 | DF |  | 0 | 7212.19 | 0 | 0 |  | 2070245 | 6861
2020-10-14 | RE 21C3*55 BILL $7,212.19 | N/A |  | 0 |  | 0 | 0 |  |  |  | 7212.19
2020-10-14 | MHTN ARCHITECTS GAX 21C5*591 | DF |  | 0 | 6731.38 | 0 | 0 |  | 2070245 | 6861
2020-10-15 | ZIONS/BIG D CONST RTNG GAX 21C5*597 | DF |  | 0 | 10452.75 | 0 | 0 |  | 2075071 | 6811
1902-10-11 | BIG D CONST CORP GAX 21C5*598 | DF |  | 0 | 198602.25 | 0 | 0 |  | 2075071 | 6811
2020-10-15 | ZIONS/BIG D CONST RTNG GAX 21C5*595 | DF |  | 0 | 7111.2 | 0 | 0 |  | 2075071 | 6811
2020-10-15 | BIG D CONST CORP GAX 21C5*596 | DF |  | 0 | 135112.85 | 0 | 0 |  | 2075071 | 6811
2020-10-23 | GREEN BUSINESS CERTIFICATION GAX F20*094 | DF |  | 0 | 1500 | 1500 | 0 |  |  | 6811
2020-10-23 | UTAH STATE UNIV GAX 21C7*322 | DF |  | 0 | 530.5 | 0 | 0 |  | 2075197 | 6811
2020-11-06 | QUALITY ASSUR ENG GAX 21C5*709 | DF |  | 0 | 824.23 | 0 | 0 |  | 2070180 | 6873
2020-11-19 | MHTN ARCHITECTS GAX 21C7*492 | DF |  | 0 | 5769.76 | 0 | 0 |  | 2070245 | 6861
2020-11-20 | RE 21C3*89 BILL $366,634.92 | N/A |  | 0 |  | 0 | 0 |  |  |  | 366634.92
2020-11-27 | ZIONS/BIG D CONST RTNG GAX 21C5*879 | DF |  | 0 | 40838.99 | 0 | 0 |  | 2075071 | 6811
2020-11-27 | BIG D CONST GAX 21C5*880 | DF |  | 0 | 775940.86 | 0 | 0 |  | 2075071 | 6811
2020-11-18 | CR 21M2*43 RE 21C3*055 | N/A |  | 0 |  | 0 | 0 | 7212.19
2020-10-23 | CR 21M2*035 RE 21C3*021 | N/A |  | 0 |  | 0 | 0 | 37742.82
2020-12-02 | UTAH NEW VISION CONST GAX 21C5*947 | DF |  | 0 | 10000 | 0 | 0 |  | 2070297 | 6849
2020-12-14 | RE 21C3*121 BILL $826,779.85 | N/A |  | 0 |  | 0 | 0 |  |  |  | 826779.85
2020-12-18 | MHTN ARCHITECTS AMD 001 | CO |  | 0 |  | 4875 | 0 |  | 2070245
2020-12-18 | ZIONS/BIG D CONST RTNG GAX 21C7*673 | DF |  | 0 | 23177.69 | 0 | 0 |  | 2075071 | 6811
2020-12-18 | BIG D CONST GAX 21C7*674 | DF |  | 0 | 440376.02 | 0 | 0 |  | 2075071 | 6811
2020-12-22 | MHTN ARCHITECTS GAX 21C8*272 | DF |  | 0 | 9239.75 | 0 | 0 |  | 2070245 | 6861
2020-12-22 | USU GAX 21C7*727 | DF |  | 0 | 39125.74 | 0 | 0 |  | 2075197 | 6811
2020-12-30 | CR 21M2*052 RE 21C3*089 | N/A |  | 0 |  | 0 | 0 | 366634.92 |  | 4760
2021-01-15 | RE 21C3*154 BILL $511,919.20 | N/A |  | 0 |  | 0 | 0 |  |  |  | 511919.2
2021-01-12 | MHTN ARCHITECTS GAX 21C5*1268 | DF |  | 0 | 5769.76 | 0 | 0 |  | 2070245 | 6861
2021-01-13 | BIG D CONST CO 002 | CO |  | 0 |  | 866.44 | 0 |  | 2075071
2021-01-15 | BIG D CONST GAX 21C8*327 | DF |  | 0 | 429618.5 | 0 | 0 |  | 2075071 | 6811
2021-01-15 | ZIONS/BIG D CONST RTNG GAX 21C8*328 | DF |  | 0 | 22611.5 | 0 | 0 |  | 2075071 | 6811
2021-01-16 | UTAH NEW VISION CONST GAX 21C7*835 | DF |  | 0 | 13000 | 0 | 0 |  | 2070297 | 6849
2021-01-16 | UTAH NEW VISION CONST GAX 21C7*839 | DF |  | 0 | 1000 | 0 | 0 |  | 2070297 | 6849
2021-01-22 | QUALITY ASSUR ENG GAX 21C7*873 | DF |  | 0 | 5340.1 | 0 | 0 |  | 2070180 | 6873
2021-01-26 | UT ST FIRE MARSHALS OFFC GAX 21C5*1359 | DF |  | 0 | 1303.1 | 1303.1 | 0 |  |  | 6861
2021-01-28 | CR 21M2*60 RE 21C3*121 | N/A |  | 0 |  | 0 | 0 | 826779.85 |  | 4760
2021-02-11 | RE 21C3*191 BILL $478,642.96 | N/A |  | 0 |  | 0 | 0 |  |  |  | 478642.96
2021-02-18 | MHTN ARCHITECTS GAX 21C8*466 | DF |  | 0 | 10644.76 | 0 | 0 |  | 2070245 | 6861
2021-02-18 | MHTN ARCHITECTS GAX 21C8*467 | DF |  | 0 | 11983.1 | 0 | 0 |  | 2070304 | 6861
2021-02-11 | BIG D CONST GAX 21C8*450 | DF |  | 0 | 246927 | 0 | 0 |  | 2075071 | 6811
2021-02-11 | ZIONS/BIG D RTNG GAX 21C8*451 | DF |  | 0 | 12996.16 | 0 | 0 |  | 2075071 | 6811
2021-02-22 | USU GAX 21C7*1000 | DF |  | 0 | 36291.74 | 0 | 0 |  | 2075197 | 6811
2021-03-10 | UTAH NEW VISION CONST GAX 21C8*527 | DF |  | 0 | 5000 | 0 | 0 |  | 2070297 | 6849
2021-03-12 | BIG D CONST GAX 21C8*533 | DF |  | 0 | 444562.57 | 0 | 0 |  | 2075071 | 6811
2021-03-12 | ZIONS/BIG D CONST RTNG GAX 21C8*534 | DF |  | 0 | 23398.03 | 0 | 0 |  | 2075071 | 6811
2021-03-01 | IET TRNSF MHTN PMT TO CORRECT PRJ 20149770 | DF |  | 0 | -11983.1 | 0 | 0 |  | 2070304
2021-03-16 | RE 21C3*230 BILL $779,820.26 | N/A |  | 0 |  | 0 | 0 |  |  |  | 779820.26
2021-03-18 | MHTN ARCHI GAX 21C5*1760 | DF |  | 0 | 5769.75 | 0 | 0 |  | 2070245 | 6861
2021-03-19 | CR 21M5*004 RE 21C3*191 | N/A |  | 0 |  | 0 | 0 | 478642.96 |  | 4760
2021-03-10 | CR 21M2*069 RE 21C3*154 | N/A |  | 0 |  | 0 | 0 | 511919.2 |  | 4760
2021-03-19 | USU CONTROLLER'S OFFC GAX 21C5*1764 | DF |  | 0 | 14576.87 | 0 | 0 |  | 2075197 | 6811
2021-04-16 | RE 21C3*266 BILL $20,346.62 | N/A |  | 0 |  | 0 | 0 |  |  |  | 20346.62
2021-04-16 | BIG D CONST CO 003 | CO |  | 0 |  | 16537.14 | 0 |  | 2075071
2021-04-22 | ZIONS/BIG D CONST RTNG GAX 21C5*2034 | DF |  | 0 | 42799.73 | 0 | 0 |  | 2075071 | 6811
2021-04-22 | BIG D CONST GAX 21C5*2035 | DF |  | 0 | 813194.96 | 0 | 0 |  | 2075071 | 6811
2021-04-21 | MHTN ARCHITECTS GAX 21C9*046 | DF |  | 0 | 5769.76 | 0 | 0 |  | 2070245 | 6861
2021-04-28 | CR 21M2*077 RE 21C3*230 | N/A |  | 0 |  | 0 | 0 | 779820.26 |  | 4760
2021-05-13 | QUALITY ASSUR ENG GAX 21C7*1497 | DF |  | 0 | 3401.44 | 0 | 0 |  | 2070180 | 6873
2021-05-13 | QUALITY ASSUR ENG GAX 21C7*1498 | DF |  | 0 | 2548.84 | 0 | 0 |  | 2070180 | 6873
2021-05-13 | QUALITY ASSUR ENG GAX 21C7*1499 | DF |  | 0 | 795.28 | 0 | 0 |  | 2070180 | 6873
2021-05-17 | MHTN ARCHITECTS GAX 21C5*2049 | DF |  | 0 | 5769.75 | 0 | 0 |  | 2070245 | 6861
2021-05-19 | RE 21C3*299 BILL $874,279.76 | N/A |  | 0 |  | 0 | 0 |  |  |  | 874279
2021-05-19 | QUALITY ASSUR ENG GAX 21C7*1525 | DF |  | 0 | 5930.02 | 0 | 0 |  | 2070180 | 6873
2021-05-19 | QUALITY ASSUR ENG GAX 21C7*1523 | DF |  | 0 | 856.33 | 0 | 0 |  | 2070180 | 6873
2021-05-19 | QUALITY ASSUR ENG GAX 21C7*1524 | DF |  | 0 | 3371.62 | 0 | 0 |  | 2070180 | 6873
2021-05-02 | CR 21M2*085 RE 21C3*266 | N/A |  | 0 |  | 0 | 0 | 20346.62 |  | 4760
2021-05-24 | ZIONS/BIG D CONST RTNG GAX 21C5*2252 | DF |  | 0 | 26895.83 | 0 | 0 |  | 2075071 | 6811
2021-05-24 | BIG D CONST GAX 21C5*2253 | DF |  | 0 | 511020.85 | 0 | 0 |  | 2075071 | 6811
2021-05-24 | UTAH STATE UNIV GAX 21C7*1547 | DF |  | 0 | 53125.74 | 0 | 0 |  | 2075197 | 6811
2021-06-14 | RE 21C3*331 BILL $601,201.15 | N/A |  | 0 |  | 0 | 0 |  |  |  | 601201.15
2021-06-14 | MHTN ARCHI GAX 21C9*420 | NP |  | 0 | 5769.76 | 0 | 0 |  | 2070245 | 6861
2021-06-15 | ZIONS/BIG D CONST RTNG GAX 21C5*2346 | NP |  | 0 | 35788.54 | 0 | 0 |  | 2075071 | 6811
2021-06-15 | BIG D CONST GAX 21C5*2347 | NP |  | 0 | 679982.33 | 0 | 0 |  | 2075071 | 6811
2021-06-22 | MHTN ARCHITECTS GAX 21C9*494 | NP |  | 0 | 5769.76 | 0 | 0 |  | 2070245 | 6861
2021-06-28 | USU GAX 21C5*2396 | NP |  | 0 | 35060.87 | 0 | 0 |  | 2075197 | 6811
13/21 | UT NEW VISION CONST GAX 21C9*761 | NP |  | 0 | 759.71 | 0 | 0 |  | 2070297 | 6849
13/21 | QUALITY ASSUR ENG GAX 21C9*762 | NP |  | 0 | 4661.64 | 0 | 0 |  | 2070180 | 6873
13/21 | QUALITY ASSUR ENG GAX 21C9*763 | NP |  | 0 | 1746.36 | 0 | 0 |  | 2070180 | 6873
2021-06-23 | CR 21M2*095 RE 21C3*299 | N/A |  | 0 |  | 0 | 0 | 874279.76 |  | 4760
2021-06-30 | CR 21M2*097 RE 21C3*331 | N/A |  | 0 |  | 0 | 0 | 601201.15 |  | 4760
13/21 | ZIONS/BIG D CONST RTNG GAX 21C7*1834 | NP |  | 0 | 44382.29 | 0 | 0 |  | 2075071 | 6811
13/21 | BIG D CONST GAX 21C5*1835 | NP |  | 0 | 843263.49 | 0 | 0 |  | 2075071 | 6811
13/21 | RE 21C3*370 BILL $1,657,184.75 | N/A |  | 0 |  | 0 | 0 |  |  |  | 1657184.75
13/21 | QUALITY ASSUR ENG GAX 21C9*866 | NP |  | 0 | 2788.98 | 0 | 0 |  | 2070180 | 6873
13/21 | QUALITY ASSUR ENG GAX 21C9*867 | NP |  | 0 | 3541.38 | 0 | 0 |  | 2070180 | 6873
13/21 | QUALITY ASSUR ENG GAX 21C9*870 | NP |  | 0 | 3306.64 | 0 | 0 |  | 2070180 | 6873
13/21 | UT ST FIRE MRSHLS OFFC GAX 21C5*2489 | NP |  | 0 | 1233.23 | 1233.23 | 0 |  |  | 6861
13/21 | QUALITY ASSUR ENG GAX 21C9*865 | NP |  | 0 | 2871.48 | 0 | 0 |  | 2070180 | 6873
13/21 | USU CONTROLLER'S OFFC GAX 21C5*2504 | NP |  | 0 | 14576.87 | 0 | 0 |  | 2075197 | 6811
13/21 | RE 21C3*403 BILL $28,318.58 | N/A |  | 0 |  | 0 | 0 |  |  |  | 28318.58
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'22 |  |  |  | 0 |  | 0 | 0
2021-08-09 | BIG D CONST CO 004 | CO |  | 0 |  | 0 | 0 |  | 2075071
2021-08-10 | BIG D CONST CO 005 | CO |  | 0 |  | 115279.16 | 0 |  | 2075071
2021-08-18 | ZIONS/BIG D CONST RTNG GAX 22C5*107 | DF |  | 0 | 34892.07 | 0 | 0 |  | 2075071 | 6811
2021-08-18 | BIG D CONST GAX 22C5*108 | DF |  | 0 | 662949.35 | 0 | 0 |  | 2075071 | 6811
2021-08-12 | CR 22M2*010 RE 21C3*370 | N/A |  | 0 |  | 0 | 0 | 1657184.75 |  | 4760
2021-08-12 | CR 22M2*010 RE 21C3*403 | N/A |  | 0 |  | 0 | 0 | 28318.58 |  | 4760
2021-08-23 | MHTN ARCHITECTS GAX 22C7*059 | DF |  | 0 | 5769.75 | 0 | 0 |  | 2070245 | 6861
2021-09-01 | USU CONTROLLERS OFFICE GAX 22C7*086 | DF |  | 0 | 44674.37 | 0 | 0 |  | 2075197 | 6811
2021-09-14 | RE 22C3*21 BILL $748,285.54 | N/A |  | 0 |  | 0 | 0 |  |  |  | 748285.54
2021-09-27 | ZIONS/BIG D CONST RTNG FC20210924119 | DF |  | 0 | 42873.92 | 0 | 0 |  | 2075071 | 6811
2021-09-27 | BIG D CONST FC20210924118 | DF |  | 0 | 814604.39 | 0 | 0 |  | 2075071 | 6811
2021-09-28 | UT NEW VISION GAX FC20210927157 | DF |  | 0 | 5511.15 | 0 | 0 |  | 2070297 | 6849
2021-10-06 | BIG D CONST CO 006 | CO |  | 0 |  | 38367.88 | 0 |  | 2075071
2021-09-29 | QUAL ASSUR ENG GAX FC20210928267 | DF |  | 0 | 3964.4 | 0 | 0 |  | 2070180 | 6873
2021-09-27 | MHTN ARCHI GAX FC20210924107 | DF |  | 0 | 5769.76 | 0 | 0 |  | 2070245 | 6861
2021-10-18 | RE 22C3* BILL $872,723.62 | N/A |  | 0 |  | 0 | 0 |  |  |  | 872723.62
2021-10-13 | MHTN ARCHI GAX FC20211013706 | DF |  | 0 | 14444.75 | 0 | 0 |  | 2070245 | 6861
2021-10-20 | BIG D CONST GAX FC20211020827 | DF |  | 0 | 511251.17 | 0 | 0 |  | 2075071 | 6811
2021-10-20 | ZIONS/BIG D CONST RTNG GAX FC20211020828 | DF |  | 0 | 26907.96 | 0 | 0 |  | 2075071 | 6861
2021-11-08 | QUALITY ASURANCE GAX FC202111081243 | DF |  | 0 | 2381.2 | 0 | 0 |  | 2070180 | 6873
2021-11-08 | MHTN ARCHI GAX FC202111081244 | DF |  | 0 | 8756.36 | 0 | 0 |  | 2070245 | 6861
2021-10-25 | CR 22M2*027 RE 22C3*021 | N/A |  | 0 |  | 0 | 0 | 748285.54 |  | 4760
2021-11-11 | GREEN BUSS GAX FC202111111362 | DF |  | 0 | 2740 | 2740 | 0 |  |  | 6861
2021-11-15 | RE 22C3*81 BILL $566,481.44 | N/A |  | 0 |  | 0 | 0 |  |  |  | 566481.44
2021-11-23 | BIG D CONST GAX FC202111231549 | DF |  | 0 | 489292.06 | 0 | 0 |  | 2075071 | 6811
2021-11-23 | ZIONS/BIG D CONST RTNG GAX FC202111231550 | DF |  | 0 | 26149.74 | 0 | 0 |  | 2075071 | 6811
2021-11-29 | WC3 GAX 22C5*259 | DF |  | 0 | 220 | 220 | 0 |  |  | 6861
2021-12-01 | USU CONTROLLERS OFFICE - CO 001 | CO |  | 0 |  | 45250 | 0 |  | 2075197
2021-12-08 | QUALITY ASSUR GAX FC202112081811 | DF |  | 0 | 3127.42 | 0 | 0 |  | 2070180 | 6873
2021-11-03 | USU GAX FC202111031130 | DF |  | 0 | 33494.29 | 0 | 0 |  | 2075197 | 6811
2021-11-03 | QUALITY ASSUR GAX FC202111031092 | DF |  | 0 | 2943.84 | 0 | 0 |  | 2070180 | 6873
2021-12-14 | BIG D CONST GAX FC202112141971 | DF |  | 0 | 194339.81 | 0 | 0 |  | 2075071 | 6811
2021-12-14 | ZIONS/BIG D RTNG GAX FC202112141972 | DF |  | 0 | 10228.41 | 0 | 0 |  | 2075071 | 6811
2021-12-20 | RE 22C3*114 BILL $759,795.57 | N/A |  | 0 |  | 0 | 0 |  |  |  | 759795.57
2021-12-21 | MHTN ARCHI GAX FC202112212044 | DF |  | 0 | 14889.9 | 0 | 0 |  | 2070245 | 6861
2021-12-21 | USU GAX FC202112212070 | DF |  | 0 | 160136.28 | 0 | 0 |  | 2075197 | 6811
2022-12-29 | UT NEW VISION GAX FC202112292188 | DF |  | 0 | 3929.14 | 0 | 0 |  | 2070297 | 6849
2022-12-22 | CR 22M2*041 RE 22C3*081 | N/A |  | 0 |  | 0 | 0 | 566481.44 |  | 4760
2022-01-06 | BIG D CONST CO 007 | CO |  | 0 |  | 42201.6 | 0 |  | 2075071
2022-01-18 | RE 22C3* 150 BILL $178,955.32 | N/A |  | 0 |  | 0 | 0 |  |  |  | 178955.32
2022-01-18 | MHTN ARCHI GAX FC202201182524 | DF |  | 0 | 4808.13 | 0 | 0 |  | 2070245 | 6861
2022-01-26 | BIG D CONST GAX FC202201262709 | DF |  | 0 | 125304.3 | 0 | 0 |  | 2075071 | 6811
2022-01-27 | ZIONS/BIG D RTNG GAX FC202201262710 | DF |  | 0 | 6594.96 | 0 | 0 |  | 2075071 | 6811
2022-01-26 | USU GAX FC202201262711 | DF |  | 0 | 557305.29 | 0 | 0 |  | 2075197 | 6811
2022-01-27 | CR 22M5*003 RE 22C3*114 | N/A |  | 0 |  | 0 | 0 | 759795.57 |  | 4760
2022-02-07 | QUAL ASSUR ENG GAX FC202202072926 | DF |  | 0 | 1030.48 | 0 | 0 |  | 2070180 | 6873
2022-02-09 | BIG D CONST CO 008 | CO |  | 0 |  | 73688.16 | 0 |  | 2075071
2022-02-18 | RE 22C3*179 BILL $695,043.16 | N/A |  | 0 |  | 0 | 0 |  |  |  | 695043.16
2022-02-17 | QUALITY ASUR GAX FC202202173130 | DF |  | 0 | 398.24 | 0 | 0 |  | 2070180 | 6873
2022-02-25 | USU GAX FC202202253259 | DF |  | 0 | 27511.14 | 0 | 0 |  | 2075197 | 6811
2022-02-23 | QUALITY ASSUR ENG AMD 001 | CO |  | 0 |  | -25067.08 | 0 |  | 2070180
2022-03-02 | CR 22M5*014 RE 22C3*150 | N/A |  | 0 |  | 0 | 0 | 178955.32 |  | 4760
2022-03-11 | RE 22C3*208 BILL $27,909.38 | N/A |  | 0 |  | 0 | 0 |  |  |  | 27909.38
2022-03-22 | BIG D CONST GAX FC202203223776 | DF |  | 0 | 115326.52 | 0 | 0 |  | 2075071 | 6811
2022-03-22 | ZIONS/BIG D RTNG GAX FC202203223777 | DF |  | 0 | 6069.82 | 0 | 0 |  | 2075071 | 6811
2022-03-24 | CR 22M5*025 RE 22C3*179 | N/A |  | 0 |  | 0 | 0 | 695043.16 |  | 4760
2022-04-11 | RE 22C3*243 BILL $121,396.34 | N/A |  | 0 |  | 0 | 0 |  |  |  | 121396.34
2022-04-12 | BIG D CONST GAX FC202204124154 | DF |  | 0 | 12290.33 | 0 | 0 |  | 2075071 | 6811
2022-04-14 | BIG D CONST CO 009 | CO |  | 0 |  | -11032.65 | 0 |  | 2075071
2022-04-21 | BIG D CONST CO 010 | CO |  | 0 |  | 25535.38 | 0 |  | 2075071
2022-04-25 | USU GAX FC202204254457 | DF |  | 0 | 125333.65 | 0 | 0 |  | 2075197 | 6811
2022-05-10 | RE 22C3*279 BILL $137,623.98 | N/A |  | 0 |  | 0 | 0 |  |  |  | 137623.98
2022-05-12 | CR 22M5*052 RE 22C3*208 | N/A |  | 0 |  | 0 | 0 | 27909.38 |  | 4760
2022-05-20 | CR 22M5*057 RE 22C3*243 | N/A |  | 0 |  | 0 | 0 | 121396.34 |  | 4760
2022-06-09 | BIG D CONST CO 011 | CO |  | 0 |  | 51663.11 | 0 |  | 2075071
2022-06-30 | USU GAX FC202206236128 | NP |  | 0 | 344820.56 | 0 | 0 |  | 2075197 | 6811
13/22 | RE 22C3*348 BILL $344,820.56 | N/A |  | 0 |  | 0 | 0 |  |  |  | 344820.56
2022-06-23 | CR 22M5*072 RE 22C3*279 | N/A |  | 0 |  | 0 | 0 | 137623.98 |  | 4760
13/22 | USU GAX 22C9*788 | NP |  | 0 | 191713.94 | 0 | 0 |  | 2075197 | 6811
13/22 | RE 22C3*383 BILL $191,713.94 | N/A |  | 0 |  | 0 | 0 |  |  |  | 191713.94
2021-11-01 | CR 22M2*034 RE 22C3*048 |  |  | 0 |  | 0 | 0 | 872723.62
|  |  |  | 0 |  | 0 | 0
FY'23 |  |  |  | 0 |  | 0 | 0
2022-08-04 | CR 23M5*011 RE 22C3*383 | N/A |  | 0 |  | 0 | 0 | 191713.94 |  | 4760
2022-08-04 | CR 23M5*011 RE 22C3*348 | N/A |  | 0 |  | 0 | 0 | 344820.56 |  | 4760
2022-08-30 | USU GAX FC202208037606 | DF |  | 0 | 3988.31 | 0 | 0 |  | 2075197 | 6811
2022-09-15 | RE 23C3*25 BILL $3,988.31 PD $21,051.66 | N/A |  | 0 |  | 0 | 0 |  |  |  | 3988.31
2022-08-10 | USU GAX F22*029 XFER FROM 20067770 | DF |  | 0 | 17063.35 | 0 | 0 |  | 2075197 | 6824
2022-10-18 | RE 23C3*66 BILL $17,063.35 | N/A |  | 0 |  | 0 | 0 |  |  |  | 17063.35
2022-10-21 | USU GAX FC202210219908 | DF |  | 0 | 40871.21 | 0 | 0 |  | 20751197 | 6811
2022-10-21 | CR 23M5*039 RE 23C3*025 OVERPAID | N/A |  | 0 |  | 0 | 0 | 21051.66 |  | 4760 |  | Overpaid by $17,063.35 (Amount of RE 66)
2022-10-28 | UT NEW VISION GAX FC2022102810232 | DF |  | 0 | 1300 | 0 | 0 |  | 2070297 | 6849
2022-11-18 | RE 23C3*104 BILL $42,171.21 | N/A |  | 0 |  | 0 | 0 |  |  |  | 42171.21
2022-11-29 | CR 23M5*051 RE 23C3*066 | N/A |  | 0 |  | 0 | 0 | 17063.35 |  | 4760
2022-12-09 | USU GAX FC2022120912163 | DF |  | 0 | 2885.4 | 0 | 0 |  | 2075197 | 6811 |  | RESERVES CHECKED TO THIS POINT
2022-12-16 | RE 23C3*140 BILL $2,885.40 | N/A |  | 0 |  | 0 | 0 |  |  |  | 2885.4
2023-01-12 | USU GAX FC2023011213556 | DF |  | 0 | 1586.05 | 0 | 0 |  | 2075197 | 6811
2023-02-10 | USU GAX FC2023020914819 | DF |  | 0 | 923.16 | 0 | 0 |  | 2075197 | 6811
2023-02-28 | RE 23C3*207 BILL $2,509.21 | N/A |  | 0 |  | 0 | 0 |  |  |  | 2509.21 |  | 12026146.19
2023-02-28 | BIG D CONST GAX FC2023022815682 | DF |  | 0 | 341723.76 | 0 | 0 |  | 2075071 | 6811 |  |  | -17064.11
2023-01-24 | CR 23M5*072 RE 23C3*140 | N/A |  | 0 |  | 0 | 0 | 2885.4 |  | 4760
2023-01-31 | CR 23M5*075 RE 23C3*104 | N/A |  | 0 |  | 0 | 0 | 42171.21 |  | 4760
2023-03-21 | GREEN BUSINESS CERTIFICATION GAX FC2023032116447 | DF |  | 0 | 910 | 910 | 0 |  |  | 6849
2023-03-30 | USU GAX FC2023033016885 | DF |  | 0 | 2020 | 0 | 0 |  | 2075197 | 6811
2023-04-10 | CR 23M5*112 RE 23C3*207 | N/A |  | 0 |  | 0 | 0 | 2509.21 |  | 4760
2023-04-12 | RE 23C3*242 BILL $344,653.76 | N/A |  | 0 |  | 0 | 0 |  |  |  | 344653.76
2023-04-14 | USU GAX FC2023041417545 | DF |  | 0 | 39456 | 0 | 0 |  | 2075197 | 6811
2023-03-23 | BIG D CONST CO 012 | CO |  | 0 |  | 66396.32 | 0 |  | 2075071
2023-05-18 | RE 23C3*278 BILL $39,456.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 39456
2023-05-24 | CR 23M5*131 RE 23C3*242 | N/A |  | 0 |  | 0 | 0 | 344653.76 |  | 4760
2023-06-06 | USU GAX FC2023060620026 | DF |  | 0 | 986.99 | 0 | 0 |  | 2075197 | 6811
2023-06-15 | RE 23C3*312 BILL $986.99 | N/A |  | 0 |  | 0 | 0 |  |  |  | 986.99
13/23 | MHTN ARCHI GAX FC2023070621678 | DF |  | 0 | 4808.13 | 0 | 0 |  | 2070245 | 6861
2023-06-23 | CR 23M5*146 RE 23C3*278 | N/A |  | 0 |  | 0 | 0 | 39456 |  | 4760
13/23 | RE 23C3* 361 BILL $4,808.13 | N/A |  | 0 |  | 0 | 0 |  |  |  | 4808.13
13/23 | BIG D CONST GAX FC2023072722951 |  |  | 0 | 178197.58 | 0 | 0 |  | 2075071 | 6811
13/23 | RE 23C3*390 BILL $178,197.58 | N/A |  | 0 |  | 0 | 0 |  |  |  | 178197.58
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'24 |  |  |  | 0 |  | 0 | 0
2023-08-15 | USU GAX FC2023081523669 | DF |  | 0 | 3699 | 0 | 0 |  | 2075197 | 6811
2023-07-05 | CR 23M5*148 RE 23C3*312 | N/A |  | 0 |  | 0 | 0 | 986.99 |  | 4760
2023-07-28 | CR 24M5*007 RE 23C3*361 | N/A |  | 0 |  | 0 | 0 | 4808.13 |  | 4760
2023-08-17 | CR 24M5*015 RE 23C3*390 | N/A |  | 0 |  | 0 | 0 | 178197.58 |  | 4760
2023-09-13 | RE 24C3*23 BILL $3,699.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 3699
2023-09-13 | USU GAX FC2023091324930 | DF |  | 0 | 1608 | 0 | 0 |  | 2075197 | 6811
2023-10-18 | RE 24C3*58 BILL $1,608.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 1608
2023-10-30 | USU GAX FC2023103026925 | DF |  | 0 | 2225.53 | 0 | 0 |  | 2075197 | 6811
2023-10-30 | CR 24M5*044 RE 24C3*023 | N/A |  | 0 |  | 0 | 0 | 3699 |  | 4760
2023-11-02 | USU CO 002 |  |  |  |  | -119550.15 |  |  | 2075197
2023-11-15 | RE 24C3*87 BILL $2,225.53 | N/A |  | 0 |  | 0 | 0 |  |  |  | 2225.53
2023-11-21 | USU CONTROLLERS GAX FC2023112127953 | DF |  | 0 | 1017 | 1017 | 0 |  |  | 6811
2023-11-29 | CR 24M5*056 RE 24C3*058 | N/A |  | 0 |  | 0 | 0 | 1608 |  | 4760
2024-12-22 | CR 24M5*067 RE 24C3*087 | N/A |  | 0 |  | 0 | 0 | 2225.53 |  | 4760
2024-01-05 | MHTN ARCHI GAX FC2024010529949 | DF |  | 0 | 6417.94 | 0 | 0 |  | 2070245 | 6861
2024-01-18 | RE 24C3*143 BILL $7,434.94 | N/A |  | 0 |  | 0 | 0 |  |  |  | 7434.94
2024-02-29 | DFCM MGMT FEES TO 24425300 FROM 20070770 | DF | -19443 | -19443 |  | 0 | -19443 |  |  | 6865
2024-02-23 | CR 24M5*085 RE 24C3*143 | N/A |  | 0 |  | 0 | 0 | 7434.94 |  | 4760
2024-06-04 | UTAH NEW VISION AMD 001 | CO |  | 0 |  | -10000 | 0 |  | 2070297
13/24 | DECREASE USU EST REVENUE | TR | -148915.92 | -148915.92 |  | 0 | -148915.92 |  |  | 4760
2022-09-15 | RE 23C3*25 BILL $3,988.31 PD $21,051.66 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 17063.35
2022-09-15 | CREDIT: RE 23C3*25 OVERAGE | N/A |  | 0 |  | 0 | 0 | -17063.35 |  | 4760 | -17063.35
PROJECT CLOSED

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 20070770
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency