## PROJECT
[7 empty] | RESERVES: |  |  |  | FUNDING |  |  | CONTINGENCY
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR | 19360963.25 | CO 001, 002, AMA SHARE |  | STATE | 18641136 | 77.29% | 548570.9663
| FUNDING |  | EFFY2022, HEFUSU |  |  |  | DESIGN | 17505.91 |  |  | Risk | 52950.21 | 0.2195% | 159643.816
| STATE RISK NUMBER |  | 00000 |  |  |  | FFE/INFO TECH/ARTS/MOVING | 0 | AMA SHARE |  | USU | 5424899 | 22.49% | 708214.7823
| PROJECT TITLE |  | USU MEHDI HERAVI GLOBAL TEACHING AND LEARNING CENTER |  |  |  | INSPECTION/INSURANCE /DFCM MNGT/COMMISSIONING | 295502.96 |  |  | TOTALS | 24118985.21
| PROJECT # |  | 22214770 | OPEN |  |  | USU CONTINGENCY/OTHER COSTS/USER FEES | 161478 | AMA SHARE
| CODING BLOCK |  | 3000-300-3345-FWB-22214770 |  |  | 26168.51 | TOTAL | 19835450.12 | -19018240.55
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
5235204.4145
YR | CURRENT TOTALS |  | 24118985.21 | 843378.08 | 23275607.13 | 23301775.64 | 817209.57 | 5292361.52 |  |  | 5292361.5233 | 0
[11 empty] | -57157.1088 | -5292361.5233
|  |  |  | 0 |  | 0 | 0
FY'22 |  |  |  | 0 |  | 0 | 0
2021-10-01 | IDT PRJ MANAGER FEES | DF |  | 0 | 20000 | 20000 | 0 |  |  | 6865
2021-10-01 | IET TRNSF FY'22 CAP DEV FUNDS FROM 22397300 | DF | 14500000 | 14500000 |  | 0 | 14500000 |  |  | 4667
2021-10-01 | IET TRNSF STATE'S SHARE OF BUDGETED CONTINGENCY TO 14317300 | DF | -605395 | -605395 |  | 0 | -605395 |  |  | 4663
2021-10-01 | IET TRNSF LEGAL BUDGET TO 21257300 | DF |  | 0 | 6975 | 6975 | 0 |  |  | 6870
2021-10-01 | IET USU EST REV | DF | 2500000 | 2500000 |  | 0 | 2500000 |  |  | 4761
2021-09-01 | METHOD STUDIO - PROGRAMMING | N/A |  | 0 |  | 108075 | 0 |  | 2270145
2021-10-28 | METHOD STUDIO GAX FC20211028976 | DF |  | 0 | 64487.5 | 0 | 0 |  | 2270145 | 6873
2021-10-01 | METHOD STUDIO GAX FC202111011045 | DF |  | 0 | 32780 | 0 | 0 |  | 2270145 | 6873
2021-11-17 | R&O CONSTRUCTION CO - CONTRACT | N/A |  | 0 |  | 50000 | 0 |  | 2270303
2021-12-09 | METHOD STUDIO GAX FX202112091845 | DF |  | 0 | 5403.75 | 0 | 0 |  | 2270145 | 6873
2021-12-20 | RE 22C3*116 BILL $19,065.63 | N/A |  | 0 |  | 0 | 0 |  |  |  | 19065.63
2021-12-28 | METHOD STUDIO GAX FC202112282159 | DF |  | 0 | 5403.75 | 0 | 0 |  | 2270145 | 6873
2022-01-18 | RE 22C3*152 BILL $794.66 | N/A |  | 0 |  | 0 | 0 |  |  |  | 794.66
2022-01-27 | CR 22M5*003 RE 22C3*116 | N/A |  | 0 |  | 0 | 0 | 19065.63 |  | 4760
2022-02-25 | CR 22M5*013 RE 22C3*152 | N/A |  | 0 |  | 0 | 0 | 794.66 |  | 4760
2022-04-01 | IET INCREASE USU EST REV FOR ADDITIONAL DESIGN | DF | 27062 | 27062 |  | 0 | 27062 |  |  | 4761
2022-04-22 | METHOD STUDIO, INC - CONTRACT | N/A |  | 0 |  | 1061057 | 0 |  | 2270497
2022-05-12 | RE 22C3*281 BILL $183.08 - CXL | N/A |  | 0 |  | 0 | 0 |  |  |  | 0.00 |  | *RE was recalculating previous payments made at old rate of 14.51 vs. new rate of 14.84
2022-05-12 | METHOD STUDIO GAX FC202205124931 | DF |  | 0 | 183859.05 | 0 | 0 |  | 2270497 | 6861
2022-05-18 | METHOD STUDIO GAX FC202205185106 | DF |  | 0 | 101614.7 | 0 | 0 |  | 2270497 | 6861
2022-06-14 | RE 22C3*314 BILL $42,368.43 | N/A |  | 0 |  | 0 | 0 |  |  |  | 42368.43
2022-06-14 | IET INCREASE USU EST REV FOR ADDITIONAL PARKING LOT | NP | 397837 | 397837 |  | 0 | 397837 |  |  | 4761
2022-06-22 | WC3 GAX 22C5*404 PLAN REVIEW APR 2022 | NP |  | 0 | 330 | 330 | 0 |  |  | 6861
13/22 | RE 22C3*350 BILL $8,231.63 | N/A |  | 0 |  | 0 | 0 |  |  |  | 8231.63
13/22 | UT ST FIRE MARSHAL GAX 22C5*490 | NP |  | 0 | 840.09 | 840.09 | 0 |  |  | 6861
2022-06-24 | METHOD STUDIO GAX FC202206246176 | NP |  | 0 | 203229.4 | 0 | 0 |  | 2270497 | 6861
2022-06-24 | R&O CONST GAX FC202206246163 | NP |  | 0 | 37500 | 0 | 0 |  | 2270303 | 6811
2022-06-29 | CR 22M5*076 RE 22C3*314 | N/A |  | 0 |  | 0 | 0 | 42368.43 |  | 4760
13/22 | WC3 GAX 22C5*553 | NP |  | 0 | 110 | 110 | 0 |  |  | 6861
13/22 | R*O CONSTRUCTION CO - CONTRACT | N/A |  | 0 |  | 16956.78 | 0 |  | 2275419
13/22 | RE 22C3*385 BILL $40,567.71 | N/A |  | 0 |  | 0 | 0 |  |  |  | 40567.71
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'23 |  |  |  | 0 |  | 0 | 0
2022-07-21 | METHOD STUDIO GAX FC202207216406 | DF |  | 0 | 142260.58 | 0 | 0 |  | 2270497 | 6861
2022-08-11 | R&O CONST GAX FC202208116960 | DF |  | 0 | 6250 | 0 | 0 |  | 2270303 | 6811
2022-07-29 | CR 23M5*009 RE 22C3*350 | N/A |  | 0 |  | 0 | 0 | 8231.63 |  | 4760
2022-08-04 | CR 23M5*011 RE 22C3*385 | N/A |  | 0 |  | 0 | 0 | 40567.71 |  | 4760
2022-08-17 | METHIS STUDIO GAX FC202208177159 | DF |  | 0 | 121937.64 | 0 | 0 |  | 2270497 | 6861
2022-09-01 | ITA 23*001 XFER FOR USU MEHDI HERAVI ARTS PROJ 158 | DF |  | 0 | 136772 | 136772 | 0 |  |  | 6284
2022-09-15 | RE 23C3*27 BILL $68,354.94 | N/A |  | 0 |  | 0 | 0 |  |  |  | 68354.94
2022-09-19 | METHOD STUDIO GAX FC202209198510 | DF |  | 0 | 20322.94 | 0 | 0 |  | 2270497 | 6861
2022-09-19 | TOTAL BUILDING COMMISSIONING INC dba TBCX, INC - CONTRACT | N/A |  | 0 |  | 11880 | 0 |  | 2370065
2022-10-18 | RE 23C3* 68 BILL $3,411.36 | N/A |  | 0 |  | 0 | 0 |  |  |  | 3411.36
2022-10-18 | METHOD STUDIO GAX FC202210189686 | DF |  | 0 | 20322.94 | 0 | 0 |  | 2270497 | 6861
2022-10-27 | R&O CONSTRUCTION CO 001 | CO |  | 0 |  | 389475.95 | 0 |  | 2275419
2022-10-21 | CR 23M5*039 RE 23C3*027 | N/A |  | 0 |  | 0 | 0 | 68354.94 |  | 4760
2022-11-02 | R&O CONST GAX FC2022110210362 | DF |  | 0 | 318996.35 | 0 | 0 |  | 2275419 | 6811
2022-11-02 | ZIONS/R&O RTNG GAX FC2022110210363 | DF |  |  | 16789.28 | 0 | 0 |  | 2275419 | 6811
2022-11-03 | ITA 23*013 COFC INSURANCE | DF |  | 0 | 13500 | 13500 | 0 |  |  | 6872
2022-11-03 | IDT TRNSF PRJ RESERVE FUNDS 22405300 PER JIM | DF | 1400000 | 1400000 |  | 0 | 1400000 |  |  | 4666
2022-11-07 | WC3 GAX 23C*029 PLAN REVIEW SEPT 2022 | DF |  | 0 | 660 | 660 | 0 |  |  | 6861
2022-11-08 | R&O CONST GAX FC2022110810758 | DF |  | 0 | 36643.11 | 0 | 0 |  | 2275419 | 6811
2022-11-08 | ZIONS/R&O RTNG GAX FC2022110810759 | DF |  | 0 | 1928.59 | 0 | 0 |  | 2275419 | 6811
2022-11-18 | RE 23C3*106 BILL $68,626.88 | N/A |  | 0 |  | 0 | 0 |  |  |  | 68626.88
2022-12-02 | R&O CONST CO 002 | CO |  | 0 |  | 465745.02 | 0 |  | 2275419
2022-11-29 | CR 23M5*051 RE 23C3*068 | N/A |  | 0 |  | 0 | 0 | 3411.36 |  | 4760
2022-12-20 | UTAH STATE UNIVERSITY CONTROLLERS OFFICE - CONTRACT | N/A |  | 0 |  | 1156700 | 0 |  | 2375321
2022-12-16 | TOTAL BLDG GAX FC2022121612422 | DF |  | 0 | 2019.6 | 0 | 0 |  | 2370065 | 6849
2022-12-16 | IET INCREASE USU EST REV FOR CONSTR CONTRACT | DF | 2500000 | 2500000 |  | 0 | 2500000 |  |  | 4761
2022-12-16 | IDT TRNSF PRJ RESERVE FUNDS 15014300 PER JIM | DF | 2500000 | 2500000 |  | 0 | 2500000 |  |  | 4666
2022-12-16 | IET CORRECT STATE'S SHARE OF BUDGETED CONTINGENCY TO 23355300 | DF | 57236 | 57236 |  | 0 | 57236 |  |  | 4663
2022-12-21 | METHOD STUDIO GAX FC2022122112683 | DF |  | 0 | 38105.51 | 0 | 0 |  | 2270497 | 6861
2022-12-23 | WC3 GAX FC20221223128804 | DF |  | 0 | 1107.26 | 1107.26 | 0 |  |  | 6873
2023-01-05 | R&O CONST GAX FC2023010513188 | DF |  | 0 | 143702.48 | 0 | 0 |  | 2275419 | 6811
2023-01-05 | ZIONS/R&O CONST RTNG GAX FC2023010513189 | DF |  | 0 | 7563.29 | 0 | 0 |  | 2275419 | 6811
2023-01-06 | TOTAL BLDG GAX FC2023010613284 | DF |  | 0 | 5940 | 0 | 0 |  | 2370065 | 6849
2023-01-06 | R&O CONST GAX FC2023010613302 | DF |  | 0 | 12860.34 | 0 | 0 |  | 2275419 | 6811
2023-01-06 | ZIONS/R&O CONST RTNG GAX FC2023010613303 | DF |  | 0 | 676.86 | 0 | 0 |  | 2275419 | 6811
2023-01-11 | WC3 GTAX FC2023011113437 | DF |  | 0 | 829.86 | 829.86 | 0 |  |  | 6873
2023-01-11 | WC3 GAX FC2023011113438 | DF |  | 0 | 275.92 | 275.92 | 0 |  |  | 6873
2023-01-13 | RE 23C3*170 BILL $138,215.38 | N/A |  | 0 |  | 0 | 0 |  |  |  | 138215.38
2023-01-12 | R&O CONST GAX FC2023011213536 | DF |  | 0 | 6250 | 0 | 0 |  | 2270303 | 6811
2023-01-23 | METHOD STUDIO GAX FC2023012313903 | DF |  | 0 | 12701.84 | 0 | 0 |  | 2270497 | 6861
2023-11-29 | WC3 GAX 23C5*063 PLAN REVIEW OCT 2022 | DF |  | 0 | 220 | 220 | 0 |  |  | 6861
2023-02-28 | RE 23C3*209 BILL $4,365.41 | N/A |  | 0 |  | 0 | 0 |  |  |  | 4365.41
2023-02-21 | METHOD STUDIO GAX FC2023021715225 | DF |  | 0 | 11177.62 | 0 | 0 |  | 2270497 | 6861
2023-01-31 | CR 23M5*075 RE 23C3*106 | N/A |  | 0 |  | 0 | 0 | 68626.88 |  | 4760
2023-02-28 | CR 23M5*084 RE 23C3*170 | N/A |  | 0 |  | 0 | 0 | 138215.38 |  | 4760
2023-03-21 | METHOD STUDIO - GAX FC2023032116507 | DF |  | 0 | 11177.62 | 0 | 0 |  | 2270497 | 6861
2023-04-10 | CR 23M5*112 RE 23C3*209 | N/A |  | 0 |  | 0 | 0 | 4365.41 |  | 4760
2023-04-12 | RE 23C3*244 BILL $5,090.26 | N/A |  | 0 |  | 0 | 0 |  |  |  | 5090.26
2023-04-19 | METHOD STUDIO GAX FX2023041917623 | DF |  | 0 | 24650.62 | 0 | 0 |  | 2270497 | 6861
2023-02-06 | R&O CONST CO 003 | CO |  | 0 |  | 19033401 | 0 |  | 2275419
2023-05-15 | WC3 GAX FX2023051518927 | DF |  | 0 | 1238.91 | 1238.91 | 0 |  |  | 6873
2023-05-18 | RE 23C3*279 BILL $5,895.01 | N/A |  | 0 |  | 0 | 0 |  |  |  | 5895.01
2023-05-18 | METHOD STUDIO GAX FC2023051819135 | DF |  | 0 | 11177.62 | 0 | 0 |  | 2270497 | 6861
2023-05-18 | R&O CONST GAX FC2023051819141 | DF |  | 0 | 767685.11 | 0 | 0 |  | 2275419 | 6811
2023-05-18 | ZIONS/R&O RTNG GAX FC2023051819142 | DF |  | 0 | 40404.48 | 0 | 0 |  | 2275419 | 6811
2023-05-18 | CR 23M5*130 RE 23C3*244 | N/A |  | 0 |  | 0 | 0 | 5090.26 |  | 4760
2023-05-01 | R&O CONST CO 004 | CO |  | 0 |  | 44133.62 | 0 |  | 2275419
2023-05-31 | TOTAL BLDG COMM GAX FC2023053119674 | DF |  | 0 | 2040.4 | 0 | 0 |  | 2370065 | 6849
2023-06-01 | R&O CONST GAX FC2023060119742 | DF |  | 0 | 967920.77 | 0 | 0 |  | 2275419 | 6811
2023-06-01 | ZIONS/R&O CONST RTNG GAX FC2023060119743 | DF |  | 0 | 50943.2 | 0 | 0 |  | 2275419 | 6811
2023-06-09 | CMB CONSULTANTS LC dba UNVC | N/A |  | 0 |  | 36500 | 0 |  | 2370531
2023-06-15 | RE 23C3*314 BILL $419,004.71 | N/A |  | 0 |  | 0 | 0 |  |  |  | 419004.71
2023-06-20 | R&O CONST GAX FC2023062020771 | DF |  | 0 | 613710.22 | 0 | 0 |  | 2275419 | 6811
2023-06-20 | ZiONS/R&O CONST RTNG GAX FC2023062020772 | DF |  | 0 | 32300.54 | 0 | 0 |  | 2275419 | 6811
2023-06-22 | METHOD STUDIO GAX FC2023062220832 | DF |  | 0 | 11177.62 | 0 | 0 |  | 2270497 | 6861
2023-06-26 | WC3 GAX FC2023062620942 | DF |  | 0 | 1350.76 | 1350.76 | 0 |  |  | 6873
2023-06-30 | RE 23C3*340 BILL $149,948.52 | N/A |  | 0 |  | 0 | 0 |  |  |  | 149948.52
13/23 | WC3 PLAN REVIEW GAX 23C5*573 | DF |  | 0 | 330 | 330 | 0 |  |  | 6861
2023-06-23 | CR 23M5*146 RE 23C3*279 | N/A |  | 0 |  | 0 | 0
13/23 | R&O CONST GAX FC2023071021977 |  |  | 0 | 539042.03 | 0 | 0 | 5895.01 | 2275419 | 6811
13/23 | ZIONS/R&O RTNG GAX FC2023071021978 |  |  | 0 | 28370.63 | 0 | 0 |  | 2275419 | 6811
13/23 | RE 23C3*362 BILL $129,274.28 | N/A |  | 0 |  | 0 | 0 |  |  |  | 129274.28
13/23 | USU GAX FC2023071422477 |  |  | 0 | 3988.95 | 0 | 0 |  | 2375321 | 6811
13/23 | METHO STUDIO GAX FC2023072022720 |  |  | 0 | 11177.62 | 0 | 0 |  | 2270497 | 6861
13/23 | RE 23C3*392 BILL $3,453.41 | N/A |  | 0 |  | 0 | 0 |  |  |  | 3453.41
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'24 |  |  |  | 0 |  | 0 | 0
2023-08-04 | R&O CONST GAX FC2023080423274 | DF |  | 0 | 715572.99 | 0 | 0 |  | 2275419 | 6811
2023-08-04 | ZIONS/R&O RTNG GAX FC2023080423275 | DF |  | 0 | 37661.74 | 0 | 0 |  | 2275419 | 6811
2023-08-15 | USU GAX FC2023081523667 | DF |  | 0 | 315 | 0 | 0 |  | 2375321 | 6811
2023-07-05 | CR 23M5*148 RE 23C3*314 | N/A |  | 0 |  | 0 | 0 | 419004.71 |  | 4760
2023-07-28 | CR 24M5*007 RE 23C3*340 | N/A |  | 0 |  | 0 | 0 | 149948.52 |  | 4760
2023-07-28 | CR 24M5*007 RE 23C3*362 | N/A |  | 0 |  | 0 | 0 | 129274.28 |  | 4760
2023-07-14 | SUNRISE ENGINEERING INC - CONTRACT | N/A |  | 0 |  | 148698.5 | 0 |  | 2470020
2023-08-17 | CR 24M5*015 RE 23C3*392 | N/A |  | 0 |  | 0 | 0 | 3453.41 |  | 4737
2023-08-23 | CMB CONSULTANTS GAX F23*085 | DF |  | 0 | 1032.76 | 0 | 0 |  | 2370531 | 6849
2023-08-31 | SUNRISE ENG GAX FC2023083124350 | DF |  | 0 | 685.66 | 0 | 0 |  | 2470020 | 6873
2023-08-31 | SUNRISE ENG GAX FC2023083124351 | DF |  | 0 | 4354.4 | 0 | 0 |  | 2470020 | 6873
2023-09-01 | SUNRISE ENG GAX FC2023090124422 | DF |  | 0 | 2166.67 | 0 | 0 |  | 2470020 | 6873
2023-09-13 | RE 24C3*25 BILL $173,458.43 | N/A |  | 0 |  | 0 | 0 |  |  |  | 173458.43
2023-09-13 | USU GAX FC2023091324931 | DF |  | 0 | 7037.78 | 0 | 0 |  | 2375321 | 6811
2023-09-13 | R&O CONST GAX FC2023091324934 | DF |  | 0 | 563172.27 | 0 | 0 |  | 2275419 | 6811
2023-09-13 | ZIONS/R&O RTNG GAX FC2023091324935 | DF |  | 0 | 29640.65 | 0 | 0 |  | 2275419 | 6811
2023-09-19 | METHOD STUDIO GAX FC2023091925209 | DF |  | 0 | 11177.62 | 0 | 0 |  | 2270497 | 6861
2023-07-02 | R&O CONST CO 005 | CO |  | 0 |  | -31457.27 | 0 |  | 2275419
2023-09-13 | R&O CONST CO 006 | CO |  | 0 |  | -15896.8 | 0 |  | 2275419
2023-10-02 | SUNRISE ENG GAX FC2023100225683 | DF |  | 0 | 3712.66 | 0 | 0 |  | 2470020 | 6873
2023-10-03 | WC3 PLAN REVIEW AUG 2023 GAX 24C5*047 | DF |  | 0 | 250 | 250 | 0 |  |  | 6861
2023-10-18 | RE 24C3*59 BILL $140,032.66 | N/A |  | 0 |  | 0 | 0 |  |  |  | 140032.66
2023-10-17 | METHOD STUDIO GAX FC2023101726382 | DF |  | 0 | 11177.62 | 0 | 0 |  | 2270497 | 6861
2023-10-18 | WC3 PLAN REVIEW GAX 24C5*074 | DF |  | 0 | 500 | 500 | 0 |  |  | 6861
2023-10-23 | R&O CONST GAX FC2023102326610 | DF |  | 0 | 766035.44 | 0 | 0 |  | 2275419 | 6811
2023-10-23 | ZIONS/R&O RTNG GAX FC2023102326611 | DF |  | 0 | 40317.65 | 0 | 0 |  | 2275419 | 6811
2023-10-25 | METHOD STUDIO GAX FC2023102526774 | DF |  | 0 | 11177.62 | 0 | 0 |  | 2270497 | 6861
2023-10-23 | R&O CONST CO 007 | CO |  | 0 |  | 8161.22 | 0 |  | 2275419
2023-10-30 | USU GAX FC2023103026926 | DF |  | 0 | 1224 | 0 | 0 |  | 2375321 | 6811
2023-10-31 | SUNRISE ENG GAX FC2023103126971 | DF |  | 0 | 1723.55 | 0 | 0 |  | 2470020 | 6873
2023-10-30 | CR 24M5*044 RE 24C3*025 | N/A |  | 0 |  | 0 | 0 | 173458.43 |  | 4760
2023-11-08 | CMB CONSULTANTS GAX FC2023110827428 | DF |  | 0 | 1035.63 | 0 | 0 |  | 2370531 | 6849
2023-11-15 | RE 24C3*88 BILL $189,716.64 | N/A |  | 0 |  | 0 | 0 |  |  |  | 189716.64
2023-11-15 | R&O CONST GAX FC2023111527756 | DF |  | 0 | 719425.78 | 0 | 0 |  | 2275419 | 6811
2023-11-15 | ZIONS/R&O RTNG GAX FC2023111527757 | DF |  | 0 | 37864.52 | 0 | 0 |  | 2275419 | 6811
2023-11-30 | TRNSF TO 22214770 FROM 23273770 USU DEL TO CLOSE | DF | 183900 | 183900 |  | 0 | 183900 |  |  | 4737
2023-11-21 | METHOD STUDIO GAX FC2023112127966 | DF |  | 0 | 11177.62 | 0 | 0 |  | 2270497 | 6861
2023-11-21 | R&O CONST CO 008 | CO |  | 0 |  | -18786.5 | 0 |  | 2275419
2023-11-17 | USU GAX FC2023111727853 | DF |  | 0 | 2448 | 0 | 0 |  | 2375321 | 6811
2023-11-24 | WC3 PLAN REVIEW OCT 2023 GAX 24C5*108 | DF |  | 0 | 125 | 125 | 0 |  |  | 6861
2023-11-27 | SUNRISE ENG GAX FC2023112728167 | DF |  | 0 | 4294.9 | 0 | 0 |  | 2470020 | 6873
2023-11-29 | CR 24M5*056 RE 24C3*059 | N/A |  | 0 |  | 0 | 0 | 140032.66 |  | 4760
2023-12-12 | CMB CONSULTANTS GAX FC2023121228967 | DF |  | 0 | 2637.06 | 0 | 0 |  | 2370531 | 6849
2023-12-12 | R&O CONST GAX FC2023121228996 | DF |  | 0 | 440943.75 | 0 | 0 |  | 2275419 | 6811
2023-12-12 | ZIONS/R&O RTNG GAX FC2023121228997 | DF |  | 0 | 23207.57 | 0 | 0 |  | 2275419 | 6811
2023-12-15 | RE 24C3*115 BILL $282,830.09 | N/A |  | 0 |  | 0 | 0 |  |  |  | 282830.09
2023-12-19 | METHOD STUDIO GAX FC2023121929271 | DF |  | 0 | 11177.62 | 0 | 0 |  | 2270497 | 6861
2023-12-26 | USU GAX FC2023122629503 | DF |  | 0 | 16497.33 | 0 | 0 |  | 2375321 | 6811
2024-12-22 | CR 24M5*067 RE 24C3*088 | N/A |  | 0 |  | 0 | 0 | 189716.64 |  | 4760
2024-01-08 | SUNRISE ENG GAX FC2024010830017 | DF |  | 0 | 2848.16 | 0 | 0 |  | 2470020 | 6873
2024-01-09 | R&O CONST CO 009 | CO |  | 0 |  | 40532.53 | 0 |  | 2275419
2024-01-18 | RE 24C3*145 BILL $6,950.07 | N/A |  | 0 |  | 0 | 0 |  |  |  | 6950.07
2024-01-24 | METHOD STUDIO GAX FC2024012430815 | DF |  | 0 | 11177.62 | 0 | 0 |  | 2270497 | 6861
2024-01-24 | R&O CONST GAX FC2024012430829 | DF |  | 0 | 655553.59 | 0 | 0 |  | 2275419 | 6811
2024-01-24 | ZIONS/R&O RTNG GAX FC2024012430830 | DF |  | 0 | 34502.82 | 0 | 0 |  | 2275419 | 6811
2024-01-24 | USU GAX FC2024012430831 | DF |  | 0 | 2183.96 | 0 | 0 |  | 2375321 | 6811
2024-02-01 | SUNRISE ENG GAX FC2024020131282 | DF |  | 0 | 2307.62 | 0 | 0 |  | 2470020 | 6873
2024-01-16 | CMB CONSULTANTS GAX FC2024011630409 | DF |  | 0 | 3737.94 | 0 | 0 |  | 2370531 | 6849
2024-02-13 | RE 24C3*169 BILL $161,543.94 | N/A |  | 0 |  | 0 | 0 |  |  |  | 161543.94
2024-02-13 | CMB CONSULTANTS GAX FC2024021331799 | DF |  | 0 | 2038.79 | 0 | 0 |  | 2370531 | 6849
2024-02-13 | USU GAX FC2024021331823 | DF |  | 0 | 14612 | 0 | 0 |  | 2375321 | 6811
2024-02-07 | CR 24M5*077 RE 24C3*115 | N/A |  | 0 |  | 0 | 0 | 282830.09 |  | 4760
2024-02-21 | R & O CONSTR.GAXFC2024022132256 | DF |  | 0 | 885518.79 | 0 | 0 |  | 2275419 | 6811
2024-02-21 | ZIONS R & O CONSTR.GAXFC2024022132257 | DF |  | 0 | 46606.25 | 0 | 0 |  | 2275419 | 6811
2024-02-24 | SUNRISE ENGINEERING GAXFC2024022732456 | DF |  | 0 | 3448.77 | 0 | 0 |  | 2470020 | 6873
2024-02-24 | METHOD STUDIO GAXFC2024022732462 | DF |  | 0 | 11177.62 | 0 | 0 |  | 2270497 | 6861
2024-02-29 | TRNSF TO 22214770 FROM 21139300 DEV CONT CO 010 R&O | DF | 12966.08 | 12966.08 |  | 0 | 12966.08 |  |  | 4664
2024-02-27 | R&O CONST CO 010 | CO |  | 0 |  | 8549.11 | 0 |  | 2275419
2024-02-23 | CR 24M5*085 RE 24C3*145 | N/A |  | 0 |  | 0 | 0 | 6950.07 |  | 4760
2024-03-12 | CMB CONSULTANTS GAX FC2024031233000 | DF |  | 0 | 5039.61 | 0 | 0 |  | 2370531 | 6849
2024-03-13 | USU GAX FC2024031333100 | DF |  | 0 | 2108 | 0 | 0 |  | 2375321 | 6811
2024-03-14 | R&O CONST GAX FC2024031433154 | DF |  | 0 | 1212693 | 0 | 0 |  | 2275419 | 6811
2024-03-14 | ZIONS/R&O RTNG GAX FC2024031433155 | DF |  | 0 | 63825.95 | 0 | 0 |  | 2275419 | 6811
2024-03-15 | RE 24C3* 202 | N/A |  | 0 |  | 0 | 0 |  |  |  | 511654.69
2024-03-20 | METHOD STUDIO GAX FC2024032033448 | DF |  | 0 | 11177.62 | 0 | 0 |  | 2270497 | 6861
2024-03-27 | SUNRISE ENG GAX FC2024032733793 | DF |  | 0 | 1437.9 | 0 | 0 |  | 2470020 | 6873
2024-03-29 | CR 24M5*096 RE 24C3*169 | N/A |  | 0 |  | 0 | 0 | 161543.94 |  | 4760
2024-04-09 | CMB CONSULTANTS GAX FC2024040934489 | DF |  | 0 | 4040.35 | 0 | 0 |  | 2370531 | 6849
2024-04-10 | R&O CONST GAX FC2024041034573 | DF |  | 0 | 1555022.53 | 0 | 0 |  | 2275419 | 6811
2024-04-10 | ZIONS/R&O RTNG GAX FC2024041034574 | DF |  | 0 | 81843.29 | 0 | 0 |  | 2275419 | 6811
2024-04-11 | USU GAX FC2024041134666 | DF |  | 0 | 340 | 0 | 0 |  | 2375321 | 6811
2024-04-18 | RE 24C3*232 was $376,582.19 | N/A |  | 0 |  | 0 | 0 |  |  |  | 375164.16
2024-04-19 | METHOD STUDIO GAX FC2024041935009 | DF |  | 0 | 11177.62 | 0 | 0 |  | 2270497 | 6861
2024-04-16 | R&O CONST CO 011 | CO |  | 0 |  | 38064.1 | 0 |  | 2275419
2024-05-07 | SUNRISE ENG GAX FC2024050735804 | DF |  | 0 | 1008.16 | 0 | 0 |  | 2470020 | 6873
2024-05-13 | R&O CONST GAX FC2024051336092 | DF |  | 0 | 1484309.75 | 0 | 0 |  | 2275419 | 6811
2024-05-13 | ZIONS/R&O RTNG GAX FC2024051336093 | DF |  | 0 | 78121.57 | 0 | 0 |  | 2275419 | 6811
2024-05-15 | CMB CONSULTANTS GAX FC2024051536198 | DF |  | 0 | 3041.18 | 0 | 0 |  | 2370531 | 6849
2024-05-20 | RE 24C3*263 | N/A |  | 0 |  | 0 | 0 |  |  |  | 359230.78
2024-05-22 | SUNRISE ENG GAX FC2024052136512 | DF |  | 0 | 851.52 | 0 | 0 |  | 2470020 | 6873
2024-05-22 | METHOD STUDIO GAX FC2024052136523 | DF |  | 0 | 11177.62 | 0 | 0 |  | 2270497 | 6861 |  |  |  | 0
2024-05-09 | CR 24M5*110 RE 24C3*202 | N/A |  | 0 |  | 0 | 0 | 511654.69 |  | 4760
2024-05-31 | CR 24M5*114 RE 24C3*232 | N/A |  | 0 |  | 0 | 0 | 375164.16 |  | 4760
2024-06-11 | R&O CONST CO 012 | CO |  | 0 |  | 12484.55 | 0 |  | 2275419
2024-06-13 | CMB CONSULTANTS GAX FC2024061437975 |  |  | 0 | 7041.96 | 0 | 0 |  | 2370531 | 6849
2024-06-19 | RE 24C3*297 |  |  | 0 |  | 0 | 0 |  |  |  | 4342.46
2024-06-19 | R&O CONST GAX FC2024061938123 |  |  | 0 | 1485816.99 | 0 | 0 |  | 2275419 | 6811
2024-06-19 | ZIONS/R&O RTNG GAX FC2024061938124 |  |  | 0 | 78200.89 | 0 | 0 |  | 2275419 | 6811
2024-06-27 | METHOD STUDIO GAX FC2024062738742 |  |  | 0 | 12193.76 | 0 | 0 |  | 2270497 | 6861
13/24 | SUNRISE ENG GAX FC2024070138984 |  |  | 0 | 632.8 | 0 | 0 |  | 2470020 | 6873
13/24 | RE 24C3*330 | N/A |  | 0 |  | 0 | 0 |  |  |  | 359045.46
13/24 | TRNFR TO 22214770 FROM 21139300 DEV CONTG FFE BUDG |  | 584530 | 584530 |  | 0 | 584530 |  |  | 4663
13/24 | R&O CONST GAX FC2024071640014 |  |  | 0 | 1307161.99 | 0 | 0 |  | 2275419 | 6811
13/24 | ZIONS/R&O RTNG GAX FC2024071640015 |  |  | 0 | 68798 | 0 | 0 |  | 2275419 | 6811
13/24 | SUNRISE ENG GAX FC2024071840128 |  |  | 0 | 346.05 | 0 | 0 |  | 2470020 | 6873
13/24 | ZIONS/SUNRISE RTNG GAX FC2024071840129 |  |  | 0 | 699.16 | 0 | 0 |  | 2470020 | 6874
13/24 | RE 24C3*346 |  |  | 0 |  | 0 | 0 |  |  |  | 313542.32
2024-06-28 | CR 24M5*126 RE 24C3*263 | N/A |  | 0 |  | 0 | 0 | 359230.78 |  | 4760
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'25 |  |  |  | 0 |  | 0 | 0
2024-07-31 | USU GAX F24*013 | DF |  | 0 | 67300.61 | 0 | 0 |  | 2375321 | 6811
2024-08-16 | USU GAX FC2024081641193 | DF |  | 0 | 5000 | 0 | 0 |  | 2375321 | 6811
2024-08-19 | METHOD STUDIO GAX FC2024081941260 | DF |  | 0 | 4064.59 | 0 | 0 |  | 2270497 | 6861
2024-08-12 | CR 25M5*016 RE 24C3*330 | N/A |  | 0 |  | 0 | 0 | 359045.46 |  | 4760
2024-08-29 | R&O CONST GAX FC2024082941731 | DF |  | 0 | 1417977.7 | 0 | 0 |  | 2275419 | 6811
2024-08-29 | ZIONS/R&O RTNG GAX FC2024082941732 | DF |  | 0 | 74630.41 | 0 | 0 |  | 2275419 | 6811
2024-09-04 | SUNRISE ENG GAX FC2024090441919 | DF |  | 0 | 798.16 | 0 | 0 |  | 2470020 | 6873
2024-09-19 | METHOD STUDIO GAX FC2024081941260 | DF |  | 0 | 4064.59 | 0 | 0 |  | 2270497 | 6861
2024-10-02 | WC3 PLAN REVIEW GAX 25C5*041 | DF |  | 0 | 125 | 125 | 0 |  |  | 6873
2024-09-23 | SUNRISE ENG GAX FC2024092342892 | DF |  | 0 | 1167.54 | 0 | 0 |  | 2470020 | 6873
2024-09-27 | R&O CONST GAX FC2024092743164 | DF |  | 0 | 1014188.47 | 0 | 0 |  | 2275419 | 6811
2024-09-27 | ZIONS/R&O RTNG GAX FC2024092743165 | DF |  | 0 | 53378.34 | 0 | 0 |  | 2275419 | 6811
2024-09-17 | USU GAX FC2024091742639 | DF |  | 0 | 8138.67 | 0 | 0 |  | 2375321 | 6811
2024-09-12 | METHOD STUDIO GAX FC2024091242365 | DF |  | 0 | 2032.29 | 0 | 0 |  | 2270497 | 6861
2024-09-12 | CMB CONSULTANTS GAX FC2024091242379 |  |  | 0 | 2544.21 | 0 | 0 |  | 2370531 | 6849
2024-10-08 | RE 25C3*29 WAS $247,351.91 | N/A |  | 0 |  | 0 | 0 |  |  |  | 603708.09 |  | should have been $604,633.59 difference of $925.50
2024-10-10 | CMB CONSULTANTS GAX FC2024101043840 | DF |  | 0 | 2345.15 | 0 | 0 |  | 2370531 | 6849
2024-10-16 | RE 25C3*56 | N/A |  | 0 |  | 0 | 0 |  |  |  | 533.99
2024-10-16 | IDT 150 25M2*001 RISK 209259 | DF | 52950.21 | 52950.21 |  | 0 | 52950.21 |  |  | 4672
2024-10-17 | R&O CONST GAX FC2024101744144 | DF |  | 0 | 636473.15 | 0 | 0 |  | 2275419 | 6811
2024-10-17 | ZIONS/R&O RTNG GAX FC2024101744145 | DF |  | 0 | 33498.59 | 0 | 0 |  | 2275419 | 6811
2024-10-18 | USU GAX FC2024101844221 | DF |  | 0 | 173312.03 | 0 | 0 |  | 2375321 | 6811
2024-08-19 | R&O CONST CO 013 | CO |  | 0 |  | 131432.97 | 0 |  | 2275419
2024-10-17 | R&O CONST CO 014 | CO |  | 0 |  | 73618.78 | 0 |  | 2275419
2024-11-01 | TRNSF TO 22214770 FROM 21139300 RETURN PROJ CONTINGENCY | DF | 7898.92 | 7898.92 |  | 0 | 7898.92 |  |  | 4664
2024-10-31 | CR 25M5*042 RE 25C3*29 | N/A |  | 0 |  | 0 | 0 | 603708.09 |  | 4760
2024-11-06 | SUNRISE ENG GAX FC2024110645024 | DF |  | 0 | 304.72 | 0 | 0 |  | 2470020 | 6873
2024-11-13 | USU GAX FC2024111345345 | DF |  | 0 | 26540.21 | 0 | 0 |  | 2375321 | 6811
2024-11-15 | RE 25C3*86 | N/A |  | 0 |  | 0 | 0 |  |  |  | 200470.71 |  | would have been 199,545.21, $925.50 was added to make up for difference of RE 25C3*029
2024-11-15 | R&O CONST GAX FC2024111545458 | DF |  | 0 | 233487.14 | 0 | 0 |  | 2275419 | 6811
2024-11-15 | ZIONS/R&O RTNG GAX FC2024111545459 | DF |  | 0 | 12288.8 | 0 | 0 |  | 2275419 | 6811
2024-11-25 | CR 25M5*050 RE 25C3*056 | N/A |  | 0 |  | 0 | 0 | 533.99 |  | 4760
2024-11-26 | SUNRISE ENG GAX FC2024112645970 | DF |  | 0 | 367.36 | 0 | 0 |  | 2470020 | 6873
2024-12-09 | R&O CONST CO 015 | CO |  | 0 |  | 33706.74 | 0 |  | 2275419
2024-12-20 | CR 25M5*058 RE 25C3*086 | N/A |  | 0 |  | 0 | 0 | 200470.71 |  | 4760
2024-12-18 | USU GAX FC024121846921 | EH |  | 0 | 11358.67 | 0 | 0 |  | 2375321 | 6811
2024-12-19 | RE 25C3*120 | N/A |  | 0 |  | 0 | 0 |  |  |  | 58632.87 |  | 57917.95 | a
2025-01-10 | R & O CONSTRUCTION GAX300FC2025011047926 | EH |  | 0 | 171290.63 | 0 | 0 |  | 2275419 | 6811
2025-01-10 | Zions/R & O CONSTRUCTION RTNG GAX300FC2025011047927 | EH |  | 0 | 9015.3 | 0 | 0 |  | 2275419 | 6811
2025-01-25 | UTAH STATE GAXFC2025011548154 | EH |  | 0 | 415433.33 | 0 | 0 |  | 2375321 | 6811
2025-01-14 | TOTAL BUILDING COMMISS GAX300FC2025011448086 | EH |  | 0 | 1880 | 0 | 0 |  | 2370065 | 6849
2025-01-22 | CMB CONSULT GAX300FC2025012248468 | EH |  | 0 | 1965.36 | 0 | 0 |  | 2370531 | 6849
2025-02-05 | RE25C3*156 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 195157.52 |  | 192777.9359
2025-02-06 | R&O CONSTRUCTION GAX300FC2025020649251 | HH |  | 0 | 129172.58 | 0 | 0 |  | 2275419 | 6811
2025-02-06 | ZIONS/R&O CONSTRUCTION RTNG GAX300FC2025020649252 | HH |  | 0 | 6798.56 | 0 | 0 |  | 2275419 | 6811
2025-01-23 | CR 25M5*068 RE 25C3*120 | N/A |  | 0 |  | 0 | 0 | 58632.87 |  | 4760
2025-02-14 | USU GAX300FC2025021449654 | HH |  | 0 | 1223.46 | 0 | 0 |  | 2375321 | 6811
2025-02-28 | R&o coNST GAX300FC2025022850218 | HH |  | 0 | 102048.07 | 0 | 0 |  | 2275419 | 6811
2025-02-28 | ZIONS/R&O CONST RTNG GAX300FC2025022850219 | HH |  | 0 | 5370.95 | 0 | 0 |  | 2275419 | 6811
2025-02-24 | R&O CONST CO 016 | CO |  | 0 |  | 10516.31 | 0 |  | 2275419
2025-03-21 | R&O CONST CO 017 | CO |  | 0 |  | 8240.3 | 0 |  | 2275419
2025-03-18 | USU MEHDI HERAVI GLOBAL TEACHING AND LEARNING CENTER CR30025M5000087 | N/A |  | 0 |  | 0 | 0 | 195157.52 |  | 4760
2025-04-10 | UTAH STATE UNIVERSITY GAX300FC2025041052151 | HH |  | 0 | 4732.71 | 0 | 0 |  | 2375321 | 6811
2025-04-22 | R & O CONSTRUCTION CO GAX300FC2025042252655 | HH |  | 0 | 76679.15 | 0 | 0 |  | 2275419 | 6811
2025-04-22 | R & O CONSTRUCTION CO GAX300FC2025042252656 | HH |  | 0 | 4035.75 | 0 | 0 |  | 2275419 | 6811
2025-04-22 | R & O CONSTRUCTION CO GAX300FC2025042252657 | HH |  | 0 | 34680.51 | 0 | 0 |  | 2275419 | 6811
2025-04-22 | R & O CONSTRUCTION CO GAX300FC2025042252658 | HH |  | 0 | 1825.29 | 0 | 0 |  | 2275419 | 6811
2025-05-08 | RE 25C3*263 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 25017.05
2025-06-11 | R & O CONSTRUCTION CO GAX300FC2025061055097 CONTRACT 2275419-PAY APP#31-USU MEHDI HERAVI GLOBAL LRNG CNTR | HH |  | 0 | 26861.21 | 0 | 0 |  | 2275419 | 6811
2025-06-11 | R & O CONSTRUCTION CO GAX300FC2025061055098 CONTRACT 2275419-PAY APP#31-USU MEHDI HERAVI GLOBAL LRNG CNTR | HH |  | 0 | 1413.75 | 0 | 0 |  | 2275419 | 6811
2025-06-19 | UTAH STATE UNIVERSITY GAX300FC2025061855452 CONTRACT 2375321-USU MEHDI HERAVI GLOBAL TEACH & LRNING CNTR | HH |  | 0 | 678913.59 | 0 | 0 |  | 2375321 | 6811
2025-06-10 | CR30025M5000127 | N/A |  | 0 |  | 0 | 0 | 25017.05 |  | 4760
2025-06-30 | RE 25C3*321 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 161025.93
2024-08-23 | CR 25M5*019 RE 24C3*346 | N/A |  | 0 |  | 0 | 0 | 313542.32 |  | 4760
13/25 | CR 24M5*130 RE 24C3*297 | N/A |  | 0 |  | 0 | 0 | 4342.46 |  | 4760
13/25 | UTAH STATE UNIVERSITY GAX300FC2025070956686 CONTRACT 2375321-USU MEHDI HERAVI GLOBAL TEACH & LRNING CNTR | HH |  | 0 | 66 | 0 | 0 |  | 2375321 | 6811
13/25 | RE 25C3*363 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 15.03
2024-07-25 | UTAH STATE UNIVERSITY - AMA | CO |  | 0 |  | 779374 | 0 |  | 2375321
2024-11-26 | SUNRISE ENG - AMD 001 | CO |  | 0 |  | -115542.74 | 0 |  | 2470020
|  |  |  | 0 |  | 0 | 0
FY' 26 |  |  |  | 0 |  | 0 | 0
2025-08-01 | USU CONTROLLERS OFFICE ATTN GLEN SCHMIDT CR30026M5000007 22214770 USU MEHDI HERAVI GLOBAL TEACHING AND LEARNING CENTER | HH |  | 0 |  | 0 | 0 | 15.03 |  | 4760
2025-08-01 | USU CONTROLLERS OFFICE ATTN GLEN SCHMIDT CR30026M5000007 22214770 USU MEHDI HERAVI GLOBAL TEACHING AND LEARNING CENTER | HH |  | 0 |  | 0 | 0 | 161025.93 |  | 4760
2025-10-25 | UTAH STATE UNIVERSITY GAX300FC2025102461255 CONTRACT 2375321-USU MEHDI HERAVI GLOBAL TEACH & LRNING CNTR | HH |  | 0 | 282855 | 0 | 0 |  | 2375321 | 6811
2025-11-06 | RE 26C3*099 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 63620.4133
2025-11-20 | UTAH STATE UNIVERSITY GAX300FC2025111962340 CONTRACT 2375321-USU MEHDI HERAVI GLOBAL TEACH & LRNING CNTR | HH |  | 0 | 276 | 0 | 0 |  | 2375321 | 6811
2025-11-21 | R & O CONSTRUCTION CR30026M5000035 | HH |  | 0 | -3149.34 | -3149.34 | 0 |  |  | 6811
2025-12-12 | USU CONTROLLERS OFFICE ATTN GLEN SCHMIDT CR30026M5000039 22214770 USU MEHDI HERAVI GLOBAL TEACHING AND LEARNING CENTER | HH |  | 0 |  | 0 | 0 | 63620.41 |  | 4760
2025-12-02 | R&O CONST CO 018 | CO |  | 0 |  | -214701.99 | 0 |  | 2275419
2026-02-26 | R & O CONSTRUCTION CO GAX300FC2026022566528 CONTRACT 2275419-PAY APP#32-USU MEHDI HERAVI GLOBAL LRNG CNTR | HH |  | 0 | 813.54 | 0 | 0 |  | 2275419 | 6811
2026-02-26 | R & O CONSTRUCTION CO GAX300FC2026022566529 CONTRACT 2275419-PAY APP#32-USU MEHDI HERAVI GLOBAL LRNG CNTR | HH |  | 0 | 42.82 | 0 | 0 |  | 2275419 | 6811
2026-03-09 | CONTRACT 2270497-USU MEHDI HERAVI GLOBAL TEACHING&LRNG CNTR GAX300F250000039 | HH |  | 0 | 2032.25 | 0 | 0 |  | 2270497 | 6861
13/26 | UTAH STATE UNIVERSITY GAX300FC2026071472965 CONTRACT 2375321-USU MEHDI HERAVI GLOBAL TEACH & LRNING CNTR | HH |  | 0 | 29317.85 | 29317.85 | 0 |  |  | 6811
13/26 | IDT30026000000320 CHANGING REVENUE_SOURCE TO 4658 | HH | 64405.72 | 64405.72 |  | 0 | 64405.72 |  |  | 4658
13/26 | IDT30026000000320 CHANGING REVENUE_SOURCE TO 4658 | HH | -64405.72 | -64405.72 |  | 0 | -64405.72 |  |  | 4760
13/26 | IDT30026000000315 CHANGING REVENUE_SOURCE TO 4658 | HH | -785.31 | -785.31 |  | 0 | -785.31 |  |  | 4658
13/26 | IDT30026000000315 CHANGING REVENUE_SOURCE TO 4658 | HH | 785.31 | 785.31 |  | 0 | 785.31 |  |  | 4760
|  |  |  | 0 |  | 0 | 0
FY' 27 |  |  |  | 0 |  | 0 | 0
2026-07-15 09:16 | UTAH STATE UNIVERSITY CO 002 | CO |  | 0 |  | -180850.85 | 0 |  | 2375321
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0

## BUDGET
FUNDING
STATE | 14500000 | 83.21%
USU | 2924899 | 16.79%
TOTALS | 17424899
CHANGE ORDER | STATE | USU | 100% USU | PROJECT | TOTAL
CO 001 |  |  | 389475.95 |  | 389475.95 | not from contingency, from constr budget
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTALS | 0 | 0 | 389475.95 | 0 | 389475.95