## PROJECT
RESERVES:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR
| FUNDING |  | OTHER |  |  |  | DESIGN
| STATE RISK NUMBER |  | 00000 |  |  |  | INSPECTION
| PROJECT TITLE |  | USU BASTIAN EQUESTRIAN ARENA |  |  |  | INSURANCE
| PROJECT # |  | 25401770 | OPEN |  |  | CONTINGENCY/LEGAL
| CODING BLOCK |  | 3000-300-3500-FXAAA-25401770 |  |  | 187586.88 | TOTAL | 0
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
5734359.56
YR | CURRENT TOTALS |  | 7000000 | 1265640.44 | 5734359.56 | 5921946.44 | 1078053.56 | 5309141.69 |  |  | 5591474.87 | 0
[11 empty] | 142884.69 | -5591474.87
|  |  |  | 0 |  | 0 | 0
FY'25 |  |  |  | 0 |  | 0 | 0
2024-11-12 | GORDON GEOTECHNICAL ENGINEERING INC - CONTRACT | N/A |  | 0 |  | 7900 | 0 |  | 2570118
2024-11-20 | METHOD STUDIO, INC - CONTRACT | N/A |  | 0 |  | 371839 | 0 |  | 2570135
2024-11-29 | METHOD STUDIO GAX FC2024112946050 | DF |  | 0 | 225373.85 | 0 | 0 |  | 2570135 | 6861
2025-01-25 | METHOD STUDIO GAXFC2025010847773 | EH |  | 0 | 24213.74 | 0 | 0 |  | 2570135 | 6861
2024-12-13 | IDT 25C3*086 MGMT FEES TO 24425300 | EH |  | 0 | 51832.34 | 51832.34 | 0 |  |  | 6865 |  |  | ADDED PER FP06 EXP REPORT
2025-01-10 | GORDON GEOTECHNICAL ENG GAX300FC2025011047901 | EH |  | 0 | 6400 | 0 | 0 |  | 2570118 | 6864
2025-01-24 | METHOD GAX300FC2025012448615 | EH |  | 0 | 6934.58 | 0 | 0 |  | 2570135 | 6861
2025-03-14 | UTAH STATE FIRE MARSHAL'S OFFICE GAX30025C5000121 | HH |  | 0 | 1100 | 1100 | 0 |  |  | 6873
2025-04-25 | METHOD STUDIO GAX300FC2025042552859 | TR |  | 0 | 15602.81 | 0 | 0 |  | 2570135 | 6861
2025-05-06 | WEST COAST CODE CONSULTANTS INC GAX30025C5000139 | TR |  | 0 | 625 | 625 | 0 |  |  | 6873
2025-05-06 | WEST COAST CODE CONSULTANTS INC GAX30025C5000139 | TR |  | 0 | 625 | 625 | 0 |  |  | 6873
2025-05-07 | RE 25C3*241 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 332707.32
2025-05-27 | WEST COAST CODE CONSULTANTS INC GAX30025C5000142 Plan Review Services 04/03/2025-PHONE CALL(S) | TR |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-05-27 | WEST COAST CODE CONSULTANTS INC GAX30025C5000142 Plan Review Services 04/03/2025-3RD REVIEW | TR |  | 0 | 250 | 250 | 0 |  |  | 6873
2025-05-30 | METHOD STUDIO GAX300FC2025052954456 CONTRACT 2570135-BASTIAN EQUESTRIAN ARENA | TR |  | 0 | 8668.22 | 0 | 0 |  | 2570135 | 6861
2025-06-06 | IDT INCREASE REV ESTIMATE - 25401770 COMMITMENT LETTER 10.7.24 | HH | 7000000 | 7000000 |  | 0 | 7000000 |  |  | 4761
2025-06-05 | RE 25C3*296 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 9043.22
2025-06-13 | USU CONTROLLERS OFFICE ATTN GLEN SCHMIDT CR30025M5000128 25401770 USU BASTIAN EQUESTRIAN ARENA | N/A |  | 0 |  | 0 | 0 | 332707.32 |  | 4760
2025-06-13 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2025061255275 CONTRACT 2575473-PAY APP #1-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 684901.07 | 0 | 0 |  | 2575473 | 6811
2025-06-13 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2025061255276 CONTRACT 2575473-PAY APP #1-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 36047.43 | 0 | 0 |  | 2575473 | 6811
2025-06-30 | RE 25C3*327 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 720948.5
13/25 | USU CONTROLLERS OFFICE ATTN GLEN SCHMIDT CR30025M5000134 25401770 USU BASTIAN EQUESTRIAN ARENA | N/A |  | 0 |  | 0 | 0 | 9043.22 |  | 4760
13/25 | ITA3002500000117 DFCM Course of Construction May 1, 2025 thru May 31, 2025 (See Excel attachment) $13,895,546.44 | HH |  | 0 | 9506.51 | 9506.51 | 0 |  |  | 6872
13/25 | METHOD STUDIO GAX300FC2025070956629 CONTRACT 2570135-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 7700 | 0 | 0 |  | 2570135 | 6861
13/25 | RE 25C3*370 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 17206.51
2025-05-14 | JARDINE MALASKA CONSTRUCTION SERVICES LLC - CONTRACT | CO |  | 0 |  | 4421631 | 0 |  | 2575473
2025-05-21 | SUNRISE ENGINEERING - CONTRACT | CO |  | 0 |  | 44216.31 | 0 |  | 2570354
FY'26
2025-07-30 | METHOD STUDIO GAX300FC2025072957476 CONTRACT 2570135-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 3850 | 0 | 0 |  | 2570135 | 6861
2025-08-01 | USU CONTROLLERS OFFICE ATTN GLEN SCHMIDT CR30026M5000007 25401770 USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 |  | 0 | 0 | 720948.5 |  | 4760
2025-08-01 | USU CONTROLLERS OFFICE ATTN GLEN SCHMIDT CR30026M5000007 25401770 USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 |  | 0 | 0 | 17206.51 |  | 4760
2025-08-22 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2025082158402 CONTRACT 2575473-PAY APP #2-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 394940.27 | 0 | 0 |  | 2575473 | 6811
2025-08-22 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2025082158403 CONTRACT 2575473-PAY APP #2-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 20786.33 | 0 | 0 |  | 2575473 | 6811
2025-08-30 | METHOD STUDIO GAX300FC2025082958818 CONTRACT 2570135-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 7700 | 0 | 0 |  | 2570135 | 6861
2025-08-30 | UTAH STATE FIRE MARSHAL'S OFFICE GAX30026C5000013 GENERAL BUILDING FIRE PLANS -25-555 -07-07-2025 | HH |  | 0 | 75 | 75 | 0 |  |  | 6873
2025-09-05 | RE 26C3*032 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 427351.6
2025-09-08 | Gordon Geotechnical Engineering, Inc. GAX300FC2025090659060 CONTRACT 2570118-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 828.75 | 0 | 0 |  | 2570118 | 6864
2025-09-09 | Gordon Geotechnical Engineering, Inc. GAX300FC2025090859117 CONTRACT 2570118-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 465 | 0 | 0 |  | 2570118 | 6864
2025-09-12 | Sunrise Engineering Holdings, Inc GAX300FC2025091159334 CONTRACT 2570354-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 2308.48 | 0 | 0 |  | 2570354 | 6873
2025-09-18 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2025091759585 CONTRACT 2575473-PAY APP #3-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 391609.76 | 0 | 0 |  | 2575473 | 6811
2025-09-18 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2025091759586 CONTRACT 2575473-PAY APP #3-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 20611.04 | 0 | 0 |  | 2575473 | 6811
2025-09-26 | METHOD STUDIO GAX300FC2025092559882 CONTRACT 2570135-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 13611 | 0 | 0 |  | 2570135 | 6861
2025-09-03 | EAGLE ENVIRONMENTAL INC CONTRACT | CO |  | 0 |  | 49986 | 0 |  | 2675088
2025-10-06 | RE 26C3*068 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 429434.03
2025-10-02 09:00 | CR30026M5000022 | HH |  | 0 |  | 0 | 0 | 427351.6 |  | 4760
2025-10-30 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2025102961404 CONTRACT 2575473-PAY APP #4-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 367845.51 | 0 | 0 |  | 2575473 | 6811
2025-10-30 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2025102961405 CONTRACT 2575473-PAY APP #4-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 19360.29 | 0 | 0 |  | 2575473 | 6811
2025-11-01 | METHOD STUDIO GAX300FC2025103161489 CONTRACT 2570135-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 6261 | 0 | 0 |  | 2570135 | 6861
2025-11-01 | Sunrise Engineering Holdings, Inc GAX300FC2025103161502 CONTRACT 2570354-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 3893.12 | 0 | 0 |  | 2570354 | 6873
2025-11-06 | RE 26C3*106 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 397359.92
2025-11-08 | USU CONTROLLERS OFFICE ATTN GLEN SCHMIDT CR30026M5000032 25401770 USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 |  | 0 | 0 | 429434.03 |  | 4760
2025-11-13 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2025111262000 CONTRACT 2575473-PAY APP #5-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 450132.8 | 0 | 0 |  | 2575473 | 6811
2025-11-13 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2025111262001 CONTRACT 2575473-PAY APP #5-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 23691.2 | 0 | 0 |  | 2575473 | 6811
2025-11-19 | UTAH STATE UNIVERSITY CONTRACT | CO |  | 0 |  | 330972.31 | 0 |  | 2675203
2025-11-07 | JARDINE MALASKA CO 001 | CO |  | 0 |  | 7520.65 | 0 |  | 2575473
2025-12-03 | Sunrise Engineering Holdings, Inc GAX300FC2025120262825 CONTRACT 2570354-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 4117.85 | 0 | 0 |  | 2570354 | 6873
2025-12-03 | WEST COAST CODE CONSULTANTS INC GAX30026C5000078 Plan Review Services 10/27/2025-1ST REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-12-03 | WEST COAST CODE CONSULTANTS INC GAX30026C5000078 Plan Review Services 10/22/2025-1ST REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-12-04 | RE 26C3*150 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 478191.85
2025-12-12 | METHOD STUDIO GAX300FC2025121163223 CONTRACT 2570135-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 6261 | 0 | 0 |  | 2570135 | 6861
2025-12-12 | USU CONTROLLERS OFFICE ATTN GLEN SCHMIDT CR30026M5000039 25401770 USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 |  | 0 | 0 | 397359.92 |  | 4760
2025-12-13 | QUESTAR GAS COMPANY GAX300FC2025121263294 PO 241944 USU BASTIAN EQUESTRIAN ARENA UTILITY FEES | HH |  | 0 | 15432.67 | 15432.67 | 0 |  |  | 6811
2026-01-06 | RE 26C3*178 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 21693.67
2026-01-09 | METHOD STUDIO GAX300FC2026010864236 CONTRACT 2570135-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 8311 | 0 | 0 |  | 2570135 | 6861
2026-01-12 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2026011064329 CONTRACT 2575473-PAY APP #6-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 751333.48 | 0 | 0 |  | 2575473 | 6811
2026-01-12 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2026011064330 CONTRACT 2575473-PAY APP #6-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 39543.87 | 0 | 0 |  | 2575473 | 6811
2026-01-14 | ROCKY MOUNTAIN POWER & LIGHT GAX300FC2026011364457 PO 242673 BASTIAN EQUESTRIAN ARENA UTILITY FEES | HH |  | 0 | 400 | 400 | 0 |  |  | 6811
2026-01-16 | USU CONTROLLERS OFFICE ATTN GLEN SCHMIDT CR30026M5000050 25401770 USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 |  | 0 | 0 | 478191.85 |  | 4760
2026-01-22 | Sunrise Engineering Holdings, Inc GAX300FC2026012164827 CONTRACT 2570354-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 479.4 | 0 | 0 |  | 2570354 | 6873
2026-01-23 | EAGLE ENVIRONMENTAL INC GAX300FC2026012264906 CONTRACT 2675088-USU BASTIAN EQUESTRIAN STABLES | HH |  | 0 | 49986 | 0 | 0 |  | 2675088 | 6819
2026-01-30 | ROCKY MOUNTAIN POWER & LIGHT GAX300FC2026011364457 PO 242673 BASTIAN EQUESTRIAN ARENA UTILITY FEES | HH |  | 0 | -400 | -400 | 0 |  |  | 6811
2026-02-05 | RE 26C3*219 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 849653.75
2026-02-07 | METHOD STUDIO GAX300FC2026020665745 CONTRACT 2570135-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 8311 | 0 | 0 |  | 2570135 | 6861
2026-02-12 | USU CONTROLLERS OFFICE ATTN GLEN SCHMIDT CR30026M5000057 25401770 USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 |  | 0 | 0 | 21693.67 |  | 4760
2026-02-19 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2026021866203 CONTRACT 2575473-PAY APP #8-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 22213.7 | 0 | 0 |  | 2575473 | 6811
2026-02-19 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2026021866200 CONTRACT 2575473-PAY APP #7-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 211810.73 | 0 | 0 |  | 2575473 | 6811
2026-02-19 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2026021866201 CONTRACT 2575473-PAY APP #7-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 11147.93 | 0 | 0 |  | 2575473 | 6811
2026-02-19 | UTAH STATE UNIVERSITY GAX300FC2026021866208 CONTRACT 2675203-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 122193.76 | 0 | 0 |  | 2675203 | 6824
2026-02-19 | Sunrise Engineering Holdings, Inc GAX300FC2026021866191 CONTRACT 2570354-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 998.2 | 0 | 0 |  | 2570354 | 6873
2026-02-19 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2026021866202 CONTRACT 2575473-PAY APP #8-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 422060.3 | 0 | 0 |  | 2575473 | 6811
2026-02-13 | JARDINE MALASKA CO 002 | CO |  | 0 |  | 205520.39 | 0 |  | 2575473
2026-03-06 | RE 26C3*255 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 798735.62
2026-03-06 | METHOD STUDIO GAX300FC2026030566912 CONTRACT 2570135-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 10111 | 0 | 0 |  | 2570135 | 6861
2026-03-17 | UTAH STATE UNIVERSITY GAX300FC2026031667514 CONTRACT 2675203-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 40731.24 | 0 | 0 |  | 2675203 | 6824
2026-03-12 | USU CONTROLLERS OFFICE ATTN GLEN SCHMIDT CR30026M5000065 25401770 USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 |  | 0 | 0 | 849653.75 |  | 4760
2026-03-18 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2026031767583 CONTRACT 2575473-PAY APP #9-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 10525.38 | 0 | 0 |  | 2575473 | 6811
2026-03-18 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2026031767582 CONTRACT 2575473-PAY APP #9-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 199982.14 | 0 | 0 |  | 2575473 | 6811
2026-03-18 | Sunrise Engineering Holdings, Inc GAX300FC2026031767558 CONTRACT 2570354-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 2180.05 | 0 | 0 |  | 2570354 | 6873
2026-03-28 | METHOD STUDIO GAX300FC2026032767954 CONTRACT 2570135-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 6261 | 0 | 0 |  | 2570135 | 6861
2026-04-06 | RE 26C3*281 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 269790.81
2026-04-18 | USU CONTROLLERS OFFICE ATTN GLEN SCHMIDT CR30026M5000077 25401770 USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 |  | 0 | 0 | 798735.62 |  | 4760
2026-04-10 | METHOD STUDIO AMD 001 | CO |  | 0 |  | 5959.25 | 0 |  | 2570135
2026-04-29 | UTAH STATE UNIVERSITY GAX300FC2026042869265 CONTRACT 2675203-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 323.48 | 0 | 0 |  | 2675203 | 6824
2026-05-01 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2026043069381 CONTRACT 2575473-PAY APP #10-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 528322.37 | 0 | 0 |  | 2575473 | 6811
2026-05-01 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2026043069382 CONTRACT 2575473-PAY APP #10-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 27806.44 | 0 | 0 |  | 2575473 | 6811
2026-05-06 | Sunrise Engineering Holdings, Inc GAX300FC2026050569590 CONTRACT 2570354-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 572.6 | 0 | 0 |  | 2570354 | 6873
2026-05-06 | RE 26C3*318 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 557024.89
2026-05-07 | USU CONTROLLERS OFFICE ATTN GLEN SCHMIDT CR30026M5000085 25401770 USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 |  | 0 | 0 | 269790.81 |  | 4760
2026-05-16 | Sunrise Engineering Holdings, Inc GAX300FC2026051570068 CONTRACT 2570354-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 49 | 0 | 0 |  | 2570354 | 6873
2026-05-16 | METHOD STUDIO GAX300FC2026051570061 CONTRACT 2570135-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 5959.25 | 0 | 0 |  | 2570135 | 6861
2026-05-16 | WEST COAST CODE CONSULTANTS INC GAX30026C5000104 Plan Review Services 03/25/2026-2ND REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2026-05-16 | WEST COAST CODE CONSULTANTS INC GAX30026C5000104 Plan Review Services 03/25/2026-2ND REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2026-05-12 09:48 | JARDINE MALASKA CONSTRUCTION SERVICES LLC CO 003 | CO |  | 0 |  | 221406.45 | 0 |  | 2575473
2026-06-08 | RE 26C3*345 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 6258.25
2026-06-20 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2026061971670 CONTRACT 2575473-PAY APP #11-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 210336.13 | 0 | 0 |  | 2575473 | 6811
2026-06-20 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2026061971671 CONTRACT 2575473-PAY APP #11-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 11070.32 | 0 | 0 |  | 2575473 | 6811
2026-06-25 | Sunrise Engineering Holdings, Inc GAX300FC2026062471892 CONTRACT 2570354-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 543.1 | 0 | 0 |  | 2570354 | 6873
2026-06-17 | METHOD STUDIO GAX300FC2026061671470 CONTRACT 2570135-BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 2801.57 | 0 | 0 |  | 2570135 | 6861
2026-06-12 | WEST COAST CODE CONSULTANTS INC GAX30026C5000116 Plan Review Services 04/29/2026 - 3DR REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2026-06-12 | WEST COAST CODE CONSULTANTS INC GAX30026C5000116 Plan Review Services 04/22/2026 - 1ST REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2026-06-12 | WEST COAST CODE CONSULTANTS INC GAX30026C5000116 Plan Review Services 04/01/2026 - 3RD REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2026-06-27 | USU CONTROLLERS OFFICE ATTN GLEN SCHMIDT CR30026M5000099 25401770 USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 |  | 0 | 0 | 557024.89 |  | 4760
13/26 | UTAH STATE UNIVERSITY GAX300FC2026071072824 CONTRACT 2675203-USU BASTIAN EQUESTRIAN ARENA | HH |  | 0 | 50948.81 | 0 | 0 |  | 2675203 | 6824
13/26 | JARDINE MALASKA CONSTRUCTION SERVICES LLC CO 004 | CO |  | 0 |  | 31663.87 | 0 |  | 2575473
13/26 | RE 26C3*398 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 276074.93
13/26 | IDT30026000000320 CHANGING REVENUE_SOURCE TO 4658 | HH | 429434.03 | 429434.03 |  | 0 | 429434.03 |  |  | 4658
13/26 | IDT30026000000320 CHANGING REVENUE_SOURCE TO 4658 | HH | -429434.03 | -429434.03 |  | 0 | -429434.03 |  |  | 4760
13/26 | IDT30026000000320 CHANGING REVENUE_SOURCE TO 4658 | HH | 397359.92 | 397359.92 |  | 0 | 397359.92 |  |  | 4658
13/26 | IDT30026000000320 CHANGING REVENUE_SOURCE TO 4658 | HH | -397359.92 | -397359.92 |  | 0 | -397359.92 |  |  | 4760
13/26 | IDT30026000000322 CHANGING REVENUE_SOURCE TO 4658 | HH | 849653.75 | 849653.75 |  | 0 | 849653.75 |  |  | 4658
13/26 | IDT30026000000322 CHANGING REVENUE_SOURCE TO 4658 | HH | -849653.75 | -849653.75 |  | 0 | -849653.75 |  |  | 4760
13/26 | IDT30026000000322 CHANGING REVENUE_SOURCE TO 4658 | HH | 269790.81 | 269790.81 |  | 0 | 269790.81 |  |  | 4658
13/26 | IDT30026000000322 CHANGING REVENUE_SOURCE TO 4658 | HH | -269790.81 | -269790.81 |  | 0 | -269790.81 |  |  | 4760
13/26 | IDT30026000000318 CHANGING REVENUE_SOURCE TO 4658 | HH | 21693.67 | 21693.67 |  | 0 | 21693.67 |  |  | 4658
13/26 | IDT30026000000318 CHANGING REVENUE_SOURCE TO 4658 | HH | -21693.67 | -21693.67 |  | 0 | -21693.67 |  |  | 4760
13/26 | IDT30026000000318 CHANGING REVENUE_SOURCE TO 4658 | HH | 478191.85 | 478191.85 |  | 0 | 478191.85 |  |  | 4658
13/26 | IDT30026000000318 CHANGING REVENUE_SOURCE TO 4658 | HH | -478191.85 | -478191.85 |  | 0 | -478191.85 |  |  | 4760
13/26 | IDT30026000000319 CHANGING REVENUE_SOURCE TO 4658 | HH | 276074.93 | 276074.93 |  | 0 | 276074.93 |  |  | 4658
13/26 | IDT30026000000319 CHANGING REVENUE_SOURCE TO 4658 | HH | -276074.93 | -276074.93 |  | 0 | -276074.93 |  |  | 4760
13/26 | IDT30026000000316 CHANGING REVENUE_SOURCE TO 4658 | HH | 427351.6 | 427351.6 |  | 0 | 427351.6 |  |  | 4658
13/26 | IDT30026000000316 CHANGING REVENUE_SOURCE TO 4658 | HH | -427351.6 | -427351.6 |  | 0 | -427351.6 |  |  | 4760
13/26 | IDT30026000000319 CHANGING REVENUE_SOURCE TO 4658 | HH | 798735.62 | 798735.62 |  | 0 | 798735.62 |  |  | 4658
13/26 | IDT30026000000319 CHANGING REVENUE_SOURCE TO 4658 | HH | -798735.62 | -798735.62 |  | 0 | -798735.62 |  |  | 4760
13/26 | IDT30026000000321 CHANGING REVENUE_SOURCE TO 4658 | HH | 6258.25 | 6258.25 |  | 0 | 6258.25 |  |  | 4658
13/26 | IDT30026000000321 CHANGING REVENUE_SOURCE TO 4658 | HH | -6258.25 | -6258.25 |  | 0 | -6258.25 |  |  | 4760
13/26 | IDT30026000000321 CHANGING REVENUE_SOURCE TO 4658 | HH | 557024.89 | 557024.89 |  | 0 | 557024.89 |  |  | 4658
13/26 | IDT30026000000321 CHANGING REVENUE_SOURCE TO 4658 | HH | -557024.89 | -557024.89 |  | 0 | -557024.89 |  |  | 4760
|  |  |  | 0 |  | 0 | 0
FY'27 |  |  |  | 0 |  | 0 | 0
2026-08-06 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2026080573750 CONTRACT 2575473-PAY APP #13-USU BASTIAN EQUESTRIAN ARENA |  |  | 0 | 135740.46 | 135740.46 | 0 |  |  | 6811
2026-08-06 | JARDINE MALASKA CONSTRUCTION SERVICES LLC GAX300FC2026080573751 CONTRACT 2575473-PAY APP #13-USU BASTIAN EQUESTRIAN ARENA |  |  | 0 | 7144.23 | 7144.23 | 0 |  |  | 6811
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 25401770
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency