## PROJECT
[7 empty] | RESERVES: |  | USU | 19000000 | 0.65517
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR |  | STATE | 10000000 | 0.34483
| FUNDING |  | GFFY2024, HEF USU |  |  |  | DESIGN
| STATE RISK NUMBER |  | 00000 |  |  |  | INSPECTION
| PROJECT TITLE |  | USU GARDNER LEARNING & LEADERSHIP BUILDING (GLLB) |  |  |  | INSURANCE
| PROJECT # |  | 24247770 | OPEN |  |  | CONTINGENCY/LEGAL
| CODING BLOCK |  | 3000-300-3347-FWBAA-24247770 |  |  | -365875.05 | TOTAL | 0
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
8608641.7514
YR | CURRENT TOTALS |  | 31281420 | 18141865.76 | 13139554.24 | 12773679.19 | 18507740.81 |  |  |  | 8608641.75 | 0
[11 empty] | 0.0014208 | -8608641.75
|  |  |  | 0 |  | 0 | 0
FY'23 |  |  |  | 0 |  | 0 | 0
2023-05-25 | MHTN ARCHITECTS INC - CONTRACT | N/A |  | 0 |  | 1431989 | 0 |  | 2370505
2023-06-20 | MHTN ARCHI GAX FC2023062020751 | DF |  | 0 | 215378.35 | 0 | 0 |  | 2370505 | 6861
2023-06-12 | MHTN ARCHI AMD 001 | CO |  | 0 |  | 6250 | 0 |  | 2370505
2023-06-30 | BLUE HAVEN ENERGY LLC - CONTRACT | N/A |  | 0 |  | 24915 | 0 |  | 2370595
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'24 |  |  |  | 0 |  | 0 | 0
2023-08-02 | BLUE HAVEN ENERGY GAX FC2023080223141 | DF |  | 0 | 12540 | 0 | 0 |  | 2370595 | 6849
2023-08-16 | MHTH ARCHI GAX FC2023081623724 | DF |  | 0 | 136918.9 | 0 | 0 |  | 2370505 | 6861
2023-07-28 | JACOBSEN CONSTRUCTION COMPANY, INC - CONTRACT | N/A |  | 0 |  | 75000 | 0 |  | 2475028
2023-08-21 | CMB CONSULTANTS LC dba UNVC - CONTRACT | N/A |  | 0 |  | 47370 | 0 |  | 2470068
2023-09-18 | MHTN ARCHI GAX FC2023091825130 | DF |  | 0 | 109535.12 | 0 | 0 |  | 2370505 | 6861
2023-10-20 | MHTN ARCHI GAX FC2023102026576 | DF |  | 0 | 27383.78 | 0 | 0 |  | 2370505 | 6861
2023-10-30 | ITA 24*024 COFC INSURANCE | DF |  | 0 | 23250 | 23250 | 0 |  |  | 6872
2023-10-16 | MHTN ARCHI AMD 002 | CO |  | 0 |  | 20000 | 0 |  | 2370505
2023-11-08 | CMB CONSULTANTS GAX FC2023110827429 | DF |  | 0 | 1635.07 | 0 | 0 |  | 2470068 | 6849
2023-11-21 | MHTN ARCHI GAX FC2023112127958 | DF |  | 0 | 230190.24 | 0 | 0 |  | 2370505 | 6861
2023-11-14 | SUNRISE ENGINEERING INC - CONTRACT | N/A |  | 0 |  | 10000 | 0 |  | 2470203
2023-11-20 | BLUE HAVEN ENERGY AMD 001 | CO |  | 0 |  | -5115 | 0 |  | 2370595
2023-11-24 | ITA 24*031 DFCM FOR THE USU GARDNER LEARNING | DF |  | 0 | 100000 | 100000 | 0 |  |  | 6284
2023-12-13 | MHTN ARCHI GAX FC2023121329037 | DF |  | 0 | 139095.12 | 0 | 0 |  | 2370505 | 6861
2024-01-03 | BUDGETED CD CONTINGENCY - 24247770 | DF | -700816 | -700816 |  | 0 | -700816 |  |  | 4663
2024-01-05 | JACOBSEN CONST GAX FC2024010529960 | DF |  | 0 | 37500 | 0 | 0 |  | 2475028 | 6811
2024-01-16 | CMB CONSULTANTS GAX FC2024011630410 | DF |  | 0 | 3537.93 | 0 | 0 |  | 2470068 | 6849
2024-01-17 | WC3 PLAN REVIEW GAX 24C5*168 | DF |  | 0 | 2375 | 2375 | 0 |  |  | 6861
2024-01-19 | MHTN ARCHI GAX FC2024011930654 | DF |  | 0 | 118595.12 | 0 | 0 |  | 2370505 | 6861
2024-01-29 | JACOB CONST CO 001 | CO |  | 0 |  | 8038562 | 0 |  | 2475028
2024-01-30 | CMB CONSULTANTS GAX FC2024013031141 | DF |  | 0 | 435.62 | 0 | 0 |  | 2470068 | 6849
2024-02-05 | TRNSF FY24 CAP DEV FUNDS TO 24247770 FROM 24376300 SB 2 Item 44 | DF | 10000000 | 10000000 |  | 0 | 10000000 |  |  | 4667
2024-02-29 | EST REV USU - 24247770 | DF | 19000000 | 19000000 |  | 0 | 19000000 |  |  | 4760
2024-02-07 | JACOBSEN CONST GAX FC2024020731584 | DF |  | 0 | 22500 | 0 | 0 |  | 2475028 | 6811
2024-02-21 | MHTN ARCHITECTS GAXFC2024022132200 | DF |  | 0 | 143764.85 | 0 | 0 |  | 2370505 | 6861
2024-02-29 | DFCM MGMT FEES TO 24425300 FROM 24247770 | DF | -95580 | -95580 |  | 0 | -95580 |  |  | 6865
2024-03-01 | BLUE HAVEN ENERGY GAX FC2024030132674 | DF |  | 0 | 5610 | 0 | 0 |  | 2370595 | 6849
2024-03-11 | WC3 PLAN REVIEW GAX 24C5*221 | DF |  | 0 | 750 | 750 | 0 |  |  | 6861
2024-03-12 | CMB CONSULTANTS GAX FC2024031232999 | DF |  | 0 | 2239.6 | 0 | 0 |  | 2470068 | 6849
2024-03-14 | UT ST FIRE MARSHAL GAX 24C5*230 | DF |  | 0 | 971.19 | 971.19 | 0 |  |  | 6861
2024-03-20 | MHTN ARCHI GAX FC2024032033438 | DF |  | 0 | 34229.72 | 0 | 0 |  | 2370505 | 6861
2024-03-22 | WC3 PLAN REVIEW GAX 24C5*235 | DF |  | 0 | 125 | 125 | 0 |  |  | 6861
2024-03-26 | JACONSEN CONST GAX FC2024032633712 | DF |  | 0 | 450722.05 | 0 | 0 |  | 2475028 | 6811
2024-03-26 | ZIONS/JACOBSEN RTNG GAX FC2024032633713 | DF |  | 0 | 23722.21 | 0 | 0 |  | 2475028 | 6811
2024-04-30 | EST REV USU - 24247770 | DF | 2377000 | 2377000 |  | 0 | 2377000 |  |  | 4760
2024-04-09 | CMB CONSULTANTS GAX FC2024040934488 | DF |  | 0 | 540.34 | 0 | 0 |  | 2470068 | 6849
2024-04-30 | TRNSF TO 24247770 FROM 21139300 TO DECREASE CONTG IN PROJ | DF | 250816 | 250816 |  | 0 | 250816 |  |  | 4664
2024-04-17 | MHTN ARCHI GAX FC2024041734897 | DF |  | 0 | 15081.89 | 0 | 0 |  | 2370505 | 6861
2024-04-22 | JACOBSEN CONST GAX FC2024042235089 | DF |  | 0 | 389717.99 | 0 | 0 |  | 2475028 | 6811
2024-04-22 | ZIONS/JACOBSEN RTNG GAX FC2024042235090 | DF |  | 0 | 20511.47 | 0 | 0 |  | 2475028 | 6811
2024-04-24 | UTAH STATE UNIVERSITY AMA - CONTRACT | N/A |  | 0 |  | 2892112 | 0 |  | 2475412
2024-05-07 | SUNRISE ENG GAX FC2024050735805 | DF |  | 0 | 4382.59 | 0 | 0 |  | 2470203 | 6873
2024-05-13 | JACOBSEN CONST GAX FC2024051336106 | DF |  | 0 | 976463.48 | 0 | 0 |  | 2475028 | 6811
2024-05-13 | ZIONS/JACOBSEN RTNG GAX FC2024051336107 | DF |  | 0 | 51392.82 | 0 | 0 |  | 2475028 | 6811
2024-05-16 | MHTN ARCHI GAX FC2024051636293 | DF |  | 0 | 15754.39 | 0 | 0 |  | 2370505 | 6861
2024-05-22 | SUNRISE ENG GAX FC2024052136514 | DF |  | 0 | 4385.77 | 0 | 0 |  | 2470203 | 6873
2024-05-23 | USU GAX FC2024052336672 | DF |  | 0 | 8845 | 0 | 0 |  | 2475412 | 6811
2024-06-27 | MHTN ARCHI GAX FC2024062738726 |  |  | 0 | 28008.78 | 0 | 0 |  | 2370505 | 6861
2024-06-27 | USU GAX FC2024062738757 |  |  | 0 | 812 | 0 | 0 |  | 2475412 | 6811
13/24 | MHTN ARCHI GAX FC2024070239189 |  |  | 0 | 27696.28 | 0 | 0 |  | 2370505 | 6861
13/24 | CMB CONSULTANTS GAX FC2024070239191 |  |  | 0 | 1842.5 | 0 | 0 |  | 2470068 | 6849
13/24 | USU GAX FC2024071640029 |  |  | 0 | 290 | 0 | 0 |  | 2475412 | 6811
13/24 | RE 24C3*343 was $3,388,730.17 |  |  | 0 |  | 0 | 0 |  |  |  | 2220194.35
13/24 | JACOBSEN CONST GAX FC2024080140615 |  |  | 0 | 2426791.27 | 0 | 0 |  | 2475028 | 6811
13/24 | ZIONS/JACOBSEN RTNG GAX FC2024080140616 |  |  | 0 | 127725.86 | 0 | 0 |  | 2475028 | 6811
13/24 | JACOBSEN CONST GAX FC2024080140617 |  |  | 0 | 1065466.47 | 0 | 0 |  | 2475028 | 6811
13/24 | ZIONS/JACOBSEN RTNG GAX FC2024080140618 |  |  | 0 | 56077.18 | 0 | 0 |  | 2475028 | 6811
13/24 | RE 24C3* |  |  | 0 |  | 0 | 0 |  |  |  | 2408444.74
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'25 |  |  |  | 0 |  | 0 | 0
2024-08-23 | JACOBSEN CONST GAX FC2024082341513 | DF |  | 0 | 1791647.83 | 0 | 0 |  | 2475028 | 6811
2024-08-23 | ZIONS/JACOBSEN RTNG GAX FC2024082341514 | DF |  | 0 | 94297.25 | 0 | 0 |  | 2475028 | 6811
2024-08-14 | CMB CONSULTANTS GAX FC2024081441057 | DF |  | 0 | 1843.5 | 0 | 0 |  | 2470068 | 6849
2024-08-26 | MHTN ARCHI GAX FC2024082641561 | DF |  | 0 | 15754.39 | 0 | 0 |  | 2370505 | 6861
2024-08-06 | IDT 25C3*006 XFER LEGAL FEES TO 21257300 | DF |  | 0 | 11680 | 11680 | 0 |  |  | 6870
2024-09-12 | CMB CONSULTANTS GAX FC2024091242378 | DF |  | 0 | 944.2 | 0 | 0 |  | 2470068 | 6849
2024-09-17 | JACOBSEN CONST GAX FC2024091742633 | DF |  | 0 | 877121.53 | 0 | 0 |  | 2475028 | 6811
2024-09-17 | ZIONS/JACOBSEN RTNG GAX FC2024091742634 | DF |  | 0 | 46164.29 | 0 | 0 |  | 2475028 | 6811
2024-09-19 | MHTN ARCHI GAX FC2024091942763 | DF |  | 0 | 15754.39 | 0 | 0 |  | 2370505 | 6861
2024-09-20 | SUNRISE ENG GAX FC2024092042809 | DF |  | 0 | 9414.33 | 0 | 0 |  | 2470203 | 6873
2024-09-24 | SUNRISE ENG GAX FC2024092442993 | DF |  | 0 | 2269.53 | 0 | 0 |  | 2470203 | 6873
2024-08-30 | RE 25C3*30 | N/A |  | 0 |  | 0 | 0 |  |  |  | 1878301.13
2024-09-16 | IDT 25C3*025 XFER FROM 21138300 JACOBSEN CO 003 | DF | 5898 | 5898 |  | 0 | 5898 |  |  | 4664
2024-10-10 | CMB CONSULTANTS GAX FC2024101043842 | DF |  | 0 | 550 | 0 | 0 |  | 2470068 | 6849
2024-10-15 | RE 25C3* 57 | N/A |  | 0 |  | 0 | 0 |  |  |  | 360.34
2024-10-17 | JACOBSEN CONST GAX FC2024101744140 | DF |  | 0 | 897484.63 | 0 | 0 |  | 2475028 | 6811
2024-10-17 | ZIONS/JACOBSEN RTNG GAX FC2024101744141 | DF |  | 0 | 47236.03 | 0 | 0 |  | 2475028 | 6811
2024-10-22 | USU GAX FC2024102244351 | DF |  | 0 | 52206 | 0 | 0 |  | 2475412 | 6811
2024-11-01 | TRNSF TO 24247770 FROM 21139300 RETURN PROJ CONTINGENCY | DF | 444102 | 444102 |  | 0 | 444102
2024-10-28 | MTHN ARCHI GAX FC2024102844588 | DF |  | 0 | 15754.39 | 0 | 0 |  | 2370505 | 6861
2024-10-31 | CR 25M5*042 RE 25C3*030 | N/A |  | 0 |  | 0 | 0 | 1878301.13 |  | 4760
2024-10-23 | JACOBSEN CONST CO 005 | CO |  | 0 |  | 7048 | 0 |  | 2475028
2024-11-07 | SUNRISE ENG GAX FC2024110745110 | DF |  | 0 | 1309.76 | 0 | 0 |  | 2470203 | 6873
2024-11-13 | USU GAX FC2024111345347 | DF |  | 0 | 42586 | 0 | 0 |  | 2475412 | 6811
2024-11-14 | MHTN ARCHI GAX FC2024111445392 | DF |  | 0 | 15754.39 | 0 | 0 |  | 2370505 | 6861
2024-11-15 | RE 25C3*87 |  |  | 0 |  | 0 | 0 |  |  |  | 702559.24
2024-11-27 | JACOBSEN CONST GAX FC2024112746018 | DF |  | 0 | 1967833.9 | 0 | 0 |  | 2475028 | 6811
2024-11-27 | ZIONS/JACOBSEN RTNG GAX FC2024112746019 | DF |  | 0 | 103570.21 | 0 | 0 |  | 2475028 | 6811
2024-11-25 | CR 25M5*050 RE 25C3*057 | N/A |  | 0 |  | 0 | 0 | 360.34 |  | 4760
2024-12-02 | BLUE HAVEN GAX FC2024120246121 |  |  | 0 | 1650 | 0 | 0 |  | 2370595 | 6849
2024-12-01 | JACOBSEN CONST CO 006 | CO |  | 0 |  | 86397 | 0 |  | 2475028
2024-12-10 | SUNRISE ENG GAX FC2024121046531 |  |  | 0 | 2049.34 | 0 | 0 |  | 2470203 | 6873
2024-12-10 | CMB CONSULTANTS GAX FC2024121046547 |  |  | 0 | 1547.01 | 0 | 0 |  | 2470068 | 6849
2024-12-18 | MHTN ARCHI GAX FC2024121846873 |  |  | 0 | 15754.39 | 0 | 0 |  | 2370505 | 6861
2024-12-18 | USU GAX FC2024121846922 |  |  | 0 | 42586 | 0 | 0 |  | 2475412 | 6811
2024-12-19 | RE 25C3* |  |  | 0 |  | 0 | 0 |  |  |  | 1398781.95
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 24247770
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency