## PROJECT
[7 empty] | RESERVES: |  |  |  | FUNDING:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT |  | RE USU 92.68% OF EXPENSES |  |  |  | CONSTR/AMA | -8.2946e-10 |  |  | USU | 14190603.92 | 92.72%
| FUNDING |  | HEF USU |  |  |  | DESIGN/PROGRAMMING | 35177.66 |  |  | STATE PASS THROUGH FUNDS | 1000000 | 6.534%
| STATE RISK NUMBER |  | 18367 |  |  |  | INSPECTION/DFCM MNGT | 3553.78 |  |  | ENERGY LOAN | 115000 | 0.7514%
| PROJECT TITLE |  | USU MOAB ACADEMIC BUILDING |  |  |  | INSURANCE/COMMISSIONING | 41049.58 |  |  | TOTAL | 15305603.92 | 100%
| PROJECT # |  | 20149770 | OPEN |  |  | CONTINGENCY | 242177.39 | AMA CO 004
| CODING BLOCK |  | 3000-300-3401-FWB-20149770 |  |  | 125445.17 | TOTAL | 321958.41 | -57933.52
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
13942666.1813
YR | CURRENT TOTALS |  | 15427655 | 389470.06 | 15038184.94 | 15163630.11 | 264024.89 | 13952687.36 |  |  | 13942666.18 | 328663.7574
[11 empty] | 0.0012668 | -13614002.4226
|  |  |  | 0 |  | 0 | 0
FY'19 |  |  |  | 0 |  | 0 | 0
13/19 | FEDEX GMA 19C2-001 | PG |  | 0 | 36.74 | 36.74 | 0 |  |  | 6879
13-19 | IET USU EST REV | DW | 9000000 | 9000000 |  | 0 | 9000000 |  |  | 4761
13/19 | RE 19C3-414 BILL $36.74 | N/A |  | 0 |  | 0 | 0 |  |  |  | 36.74
13/19 | PBIET10019*2289 LUNCH MEETING | PG |  | 0 | 230.28 | 230.28 | 0 |  |  | 6879
13/19 | RE 19C3-468 BILL $230.28 | N/A |  | 0 |  | 0 | 0 |  |  |  | 230.28
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'20 |  |  |  | 0 |  | 0 | 0
2019-07-01 | MHTN ARCHITECTS INC - PROGRAMMING | N/A |  | 0 |  | 63500 | 0 |  | 2070008
2019-08-01 | ETC GROUP INC - COMMISSIONING | N/A |  | 0 |  | 23080 | 0 |  | 2070068
2019-07-01 | HOGAN & ASSOC CONSTR - CONTRACT CMGC | N/A |  | 0 |  | 45000 | 0 |  | 2075009
2019-07-01 | USU - AMA FOR FFE, INFOR TECH, AV, USU MNGT FEE, VARIOUS CONSTR | N/A |  | 0 |  | 1324068 | 0 |  | 2075026
2019-08-02 | CR 20M2-013 RE 19C3-414 | N/A |  | 0 |  | 0 | 0 | 36.74
2019-08-19 | CR 20M2-018 RE 19C3-468 | N/A |  | 0 |  | 0 | 0 | 230.28
2019-09-06 | MHTN ARCHITECTS INC GAX 20C5-324 | DF |  | 0 | 25400 | 0 | 0 |  | 2070008 | 6864
2019-09-01 | IET INCREASE USU EST REV FOR SOLAR ARRAY | DF | 300000 | 300000 |  | 0 | 300000 |  |  | 4761
2019-09-24 | RE 20C3-29 BILL $25,400.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 25400
2019-09-25 | MHTN ARCHI GAX 20C5-569 | DF |  | 0 | 22225 | 0 | 0 |  | 2070008 | 6864
2019-09-25 | UTAH NEW VISION CONSTR LLC - COMMISSIONING | N/A |  | 0 |  | 20400 | 0 |  | 2070134
2019-10-16 | ETC GROUP GAX 20C5*873 | DF |  | 0 | 4500.6 | 0 | 0 |  | 2070068 | 6849
2019-10-17 | SOUND GEOTHERMAL CORP GAX 20C5*900 | DF |  | 0 | 6800 | 6800 | 0 |  |  | 6861
2019-10-17 | GEO ENERGY SYS GAX 20C5*901 | DF |  | 0 | 10000 | 10000 | 0 |  |  | 6811
2019-09-19 | ETC GRUP GAX 20C5*514 | DF |  | 0 | 4616 | 0 | 0 |  | 2070068 | 6861
2019-10-30 | RE 20C3- 75 BILL $48,141.60 | N/A |  | 0 |  | 0 | 0 |  |  |  | 48141.6
2019-11-04 | MHTN ARCHITECTS GAX 20C5-1141 | DF |  | 0 | 6350 | 0 | 0 |  | 2070008 | 6864
2019-11-04 | SOUND GEOTHERMAL GRP GAX 20C5*1203 | DF |  | 0 | 10185 | 10185 | 0 |  |  | 6861
2019-10-24 | CR 20M2-045 RE 20C3-029 | N/A |  | 0 |  | 0 | 0 | 25400
2019-11-05 | IDT 20C3*008 PRJ MGR FEE | DF |  | 0 | 63500 | 63500 | 0 |  |  | 6865
2019-12-06 | ETC GROUP GAX 20C5*1459 | DF |  | 0 | 2885 | 0 | 0 |  | 2070068 | 6849
2019-12-02 | CR 20M2-058 RE 20C3-075 | N/A |  | 0 |  | 0 | 0 | 48141.6
2019-12-16 | RE 20C3*121 BILL $82,920.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 82920
2019-12-10 | ETC GROUP GAX 20C8*126 | DF |  | 0 | 2885 | 0 | 0 |  | 2070068 | 6849
2019-12-10 | IET TRNSF FUNDS FROM 20404770, FY'20 PASS-THROUGH FUNDS FOR THIS PROJECT PER USU | DF | 1000000 | 1000000 |  | 0 | 1000000 |  |  | 4667
2019-12-10 | IET REDUCE USU EST REV, THE PASS-THROUGH FUNDS ARE A PART OF THIS OVERALL $9.3M COMITTMENT | DF | -1000000 | -1000000 |  | 0 | -1000000 |  |  | 4761
2020-01-02 | ETC GROUP GAX 20C8*153 | DF |  | 0 | 1673.3 | 0 | 0 |  | 2070068 | 6849
2020-01-14 | RE 20C3*161 BILL 4,558.30 | N/A |  | 0 |  | 0 | 0 |  |  |  | 4558.3
2020-02-10 | COFC INSURANCE ITA 300 2-037 | PG |  | 0 | 286.63 | 286.63 | 0 |  |  | 6872
2020-01-27 | CR 20M2-078 RE 20C3-121 | N/A |  | 0 |  | 0 | 0 | 82920
2020-02-11 | ETC GROUP INC AMD 001 | CO |  | 0 |  | 21600 | 0 |  | 2070068
2020-02-10 | ETC GROUP GAX 20C5*2005 | DF |  | 0 | 1904.1 | 0 | 0 |  | 2070068 | 6849
2020-02-10 | UTAH NEW VISION CONST GAX 20C8*228 | DF |  | 0 | 500 | 0 | 0 |  | 2070134 | 6849
2020-02-13 | MHTN ARCHITECTS GAX 20C7*528 | DF |  | 0 | 9525 | 0 | 0 |  | 2070008 | 6864
2020-02-18 | RE 20C3*202 BILL 12,215.63 | N/A |  | 0 |  | 0 | 0 |  |  |  | 12215.63
2020-03-03 | UTAH NEW VISION CONST GAX 20C7*644 | DF |  | 0 | 500 | 0 | 0 |  | 2070134 | 6849
2020-03-03 | ETC GROUP GAX 20C5*2146 | DF |  | 0 | 4616 | 0 | 0 |  | 2070068 | 6849
2019-12-10 | ETC GROUP GAX 20C8*126 (DUP PMT CHK CANCELLED) | DF |  | 0 | -2885 | 0 | 0 |  | 2070068 | 6849
2020-02-24 | CR 20M2-088 RE 20C3-161 | N/A |  | 0 |  | 0 | 0 | 4558.3
2020-03-10 | RE 20C3*234 BILL 2,231.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 2231
2020-03-24 | MHTN ARCHITECTS INC GAX 20C5*2247 | DF |  | 0 | 179752 | 0 | 0 |  | 2070304 | 6861
2020-04-01 | IET INCREASE USU EST REV | PG | 1300000 | 1300000 |  | 0 | 1300000 |  |  | 4761
2020-03-19 | CR 20M2-101 RE 20C3-202 | N/A |  | 0 |  | 0 | 0 | 12215.63
2020-02-01 | MHTN ARCHITECTS INC - DESIGN | N/A |  | 0 |  | 530000 | 0 |  | 2070304
2020-04-13 | RE 20C3*265 BILL $179,752.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 179752
2020-04-14 | ETC GROUP LLC GAX 20C5*2534 | DF |  | 0 | 2885 | 0 | 0 |  | 2070068 | 6849
2020-04-22 | MHTN ARCHITECTS GAX 20C5*2664 | DF |  | 0 | 21712 | 0 | 0 |  | 2070304 | 6861 |  |  |  | 67995.761
2020-04-28 | ETC GROUP GAX 20C5*2724 | DF |  | 0 | 11040 | 0 | 0 |  | 2070068 | 6849
2020-04-20 | CR 20M2-108 RE 20C3-234 | N/A |  | 0 |  | 0 | 0 | 2231
2020-05-13 | RE 20C3*305 BILL $35,637.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 35637
2020-05-13 | ETC GROUP INC AMD 002 | CO |  | 0 |  | 10800 | 0 |  | 2070068
2020-05-22 | CR 20M2-117 RE 20C3-265 | N/A |  | 0 |  | 0 | 0 | 179752
2020-06-05 | ETC GROUP LLC GAX 20C7*891 | PG |  | 0 | 7915 | 0 | 0 |  | 2070068 | 6849
2020-06-12 | RE 20C3*343 BILL $7,915.10 | N/A |  | 0 |  | 0 | 0 |  |  |  | 7915.1
2020-06-16 | CR 20M2-122 RE 20C3-305 | N/A |  | 0 |  | 0 | 0 | 35637
2020-06-18 | MHTN ARCHITECTS INC GAX 20C5*3588 | PG |  | 0 | 10376 | 0 | 0 |  | 2070304 | 6861
2020-06-30 | MHTN ARCHITECTS GAX 20C7*944 | PG |  | 0 | 30762.4 | 0 | 0 |  | 2070304 | 6861
13/20 | UTAH STATE UNIVERSITY CO 001 | CO |  | 0 |  | -32350 | 0 |  | 2075026 |  |  | AMA - TRANSFER THE FOLLOWING COSTS TO THE DESIGN BUDGET COMPONENT GROUP TO COVER THE DESIGN FEE PROPOSED FROM MHTN FOR FF&E, $32,350 from ama co 001
13/20 | HOGAN & ASSOC CONST GAX 20C7*987 | NP |  | 0 | 36200 | 0 | 0 |  | 2075009 | 6811
13/20 | RE 20C3*387 BILL $77,343.40 | N/A |  | 0 |  | 0 | 0 |  |  |  | 77343.4 | S/B $77,348.40 @ 100%
2020-06-30 | CR 20M2-126 RE 20C3-343 | N/A |  | 0 |  | 0 | 0 | 7915.1
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0 | [6 empty] | 0.92715
FY'21 |  |  |  | 0 |  | 0 | 0
2020-07-23 | MHTN ARCHITECTS AMD 001 | CO |  | 0 |  | 32350 | 0 |  | 2070304
2020-07-28 | MHTN ARCHITECTS AMD 002 | CO |  | 0 |  | 24788 | 0 |  | 2070304
2020-08-20 | MHTN ARCHITECTS GAX 21C5*228 | DF |  | 0 | 70049.6 | 0 | 0 |  | 2070304 | 6861
2020-07-31 | CR 21M2-008 RE 20C3-383 | N/A |  | 0 |  | 0 | 0 | 103420.11
2020-09-11 | RE 21C3*022 BILL $70,044.60 | N/A |  | 0 |  | 0 | 0 |  |  |  | 70044.6 | 64946.5473
2020-09-17 | UTAH NEW VISION CONST GAX 21C7*160 | DF |  | 0 | 3200 | 0 | 0 |  | 2070134 | 6849
2020-09-22 | MHTN ARCHITECTS GAX 21C7*177 | DF |  | 0 | 115560 | 0 | 0 |  | 2070304 | 6861
2020-10-14 | RE 21C3*56 BILL $118,760.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 118760 | 100%
2020-10-14 | IET INCREASE USU EST REV PER USU FUNDING LETTER | DF | 3822711 | 3822711 |  | 0 | 3822711 |  |  | 4761
2020-10-19 | WC3 GAX 21C5*610 | DF |  | 0 | 660 | 660 | 0 |  |  | 6861
2020-10-20 | UT ST FIRE MARSHALL GAX 21C5*611 | DF |  |  | 484 | 484 |  |  |  | 6861
2020-10-26 | SHUMS CODA ASSOCIATES, INC. - CONTRACT | N/A |  | 0 |  | 112725.22 | 0 |  | 2170735
2020-11-02 | UTAH STATE UNIV GAX 21C7*370 | DF |  | 0 | 272738.75 | 0 | 0 |  | 2075026 | 6811
2020-11-04 | HOGAN & ASSOCIATES CONSTRUCTION, INC. - CONTRACT | N/A |  | 0 |  | 11290169 | 0 |  | 2175183
2020-11-12 | USU CO 002 | CO |  | 0 |  | 107937.96 | 0 |  | 2075026
13-21 | JVA 100 21F*364 ENERGY LOAN FUNDS | DF | 115000 | 115000 |  | 0 | 115000 |  |  |  |  | DFCM ENERGY LOAN $115,000
2020-11-19 | HOGAN & ASSOC CONST GAX 21C7*489 | DF |  | 0 | 8800 | 0 | 0 |  | 2075009 | 6864
2020-11-20 | RE 21C3*90 BILL $209,984.01 | N/A |  | 0 |  | 0 | 0 |  |  |  | 209984.01 | 262089.5563
2020-12-01 | ETC GRUP AMD 003 | CO |  | 0 |  | 44519 | 0 |  | 2070068
2020-11-23 | CR 21M2*044 RE 21C3*056 | N/A |  | 0 |  | 0 | 0 | 118760
2020-10-23 | CR 21M2*035 RE 21C3*022 | N/A |  | 0 |  | 0 | 0 | 70044.6
2020-12-01 | ETC GROUP GAX 21C5*919 | DF |  | 0 | 2885 | 0 | 0 |  | 2070068 | 6849
2020-12-01 | ETC GROUP GAX 21C5*920 | DF |  | 0 | 4320 | 0 | 0 |  | 2070068 | 6849
2020-11-12 | WC3 GAX 21C5*796 | DF |  | 0 | 330 | 330 | 0 |  |  | 6861
2020-11-25 | IDT 300 21C3*022 PROJ MNGR FEES | DF |  | 0 | 64319 | 64319 | 0 |  |  | 6865
2020-12-14 | RE 21C3*122 BILL $6,975.09 | N/A |  | 0 |  | 0 | 0 |  |  |  | 6957.09 | 0.9233
2020-12-18 | MHTN ARCHITECTS GAX 21C7*679 | DF |  | 0 | 14302.9 | 0 | 0 |  | 2070304 | 6861
2020-12-28 | USU GAX 21C5*1123 | DF | 0 | 0 | 13000 | 0 | 0 |  | 2075026 | 6811
2020-12-30 | CR 21M2*052 RE 21C3*090 | N/A |  | 0 |  | 0 | 0 | 209984.01 |  | 4760
2021-01-15 | RE 21C3*155 BILL $25,208.85 | N/A |  | 0 |  | 0 | 0 |  |  |  | 25208.85 | 0.9233 | Proj Manager credit not inculded
2021-01-12 | HOGAN & ASSOC CONST GAX 21C8*315 | DF |  | 0 | 516991 | 0 | 0 |  | 2175183 | 6811
2021-01-12 | ZIONS/HOGAN & ASSOC RTNG GAX 21C8*316 | DF |  | 0 | 27211 | 0 | 0 |  | 2175183 | 6811
2021-01-25 | SHUMS CODA ASSOC GAX 21C7*898 | DF |  | 0 | 1260.7 | 0 | 0 |  | 2170735 | 6873
2021-02-03 | MHTN ARCHITECTS GAX 21C5*1447 | DF |  | 0 | 16947.8 | 0 | 0 |  | 2070304 | 6861
2021-01-14 | COFC ITA 21*037 | DF |  | 0 | 5983.79 | 5983.79 | 0 |  |  | 6872
2021-01-28 | CR 21M2*060 RE 21C3*122 | N/A |  | 0 |  | 0 | 0 | 6957.09 |  | 4760
2021-02-11 | RE 21C3*192 BILL $524,800.18 | N/A |  | 0 |  | 0 | 0 |  |  |  | 524800.18 | 0.93315
2021-02-17 | HOGAN & ASSOC CONST CO 001 | CO |  | 0 |  | -120000 | 0 |  | 2175183
2021-02-20 | SHUMS CODA ASSOC GAX 21C8*470 | DF |  | 0 | 2244.4 | 0 | 0 |  | 2170735 | 6873
2021-02-25 | USU GAX 21C7*1036 | DF |  | 0 | 17073 | 0 | 0 |  | 2075026 | 6811
2021-02-24 | ETC GROUP LLC GAX 21C8*489 | DF |  | 0 | 1725 | 0 | 0 |  | 2070068 | 6849
2021-02-24 | ETC GROUP LLC GAX 21C8*490 | DF |  | 0 | 2115 | 0 | 0 |  | 2070068 | 6849
2021-02-25 | USU CO 003 | CO |  | 0 |  | 362719.54 | 0 |  | 2075026
2021-03-02 | SHUMS CODA ASSOC GAX 21C7*1086 | DF |  | 0 | 4216.7 | 0 | 0 |  | 2170735 | 6873
2021-02-26 | CR 21M2*067 RE 21C3*155 | N/A |  | 0 |  | 0 | 0 | 25208.85 |  | 4760
2021-03-09 | PBIET10021*540030 AGENT FEE | DF |  | 0 | 8 | 8 | 0 |  |  | 6879
2021-03-01 | MTHN ARCITECTS GAX 21C8*0467 | DF |  | 0 | 11983.1 | 0 | 0 |  | 2070304 | 6861
2021-03-10 | UTAH NEW VISION CONST GAX 21C8*531 | DF |  | 0 | 1200 | 0 | 0 |  | 2070134 | 6849
2021-03-16 | RE 21C3*231 BILL $37,453.96 | N/A |  | 0 |  | 0 | 0 |  |  |  | 37453.96 | 0.98917
2021-03-19 | CR 21M5*004 RE 21C3*192 | N/A |  | 0 |  | 0 | 0 | 524800.18 |  | 4760
2021-03-19 | USU GAX 21C5*1763 | DF |  | 0 | 14598 | 0 | 0 |  | 2075026 | 6811
2021-03-22 | MHTN ARCHITECTS INC GAX 21C7*1217 | DF |  | 0 | 9976.2 | 0 | 0 |  | 2070304 | 6861
2021-04-08 | PBIET100210307010430030 AGENT FEE | DF |  | 0 | 8 | 8 | 0 |  |  | 6879
2021-04-16 | RE 21C3*267 BILL $22,696.82 | N/A |  | 0 |  | 0 | 0 |  |  |  | 22696.82 | 0.9884
2021-04-22 | ETC GROUP GAX 21C5*2043 | DF |  | 0 | 2735 | 0 | 0 |  | 2070068 | 6849
2021-04-22 | MHTN ARCHITECTS GAX 21C5*2045 | DF |  | 0 | 11003.6 | 0 | 0 |  | 2070304 | 6861
2021-04-22 | UTAH NEW VISION CONST GAX 21C9*051 | DF |  | 0 | 3108.3 | 0 | 0 |  | 2070134 | 6849
2021-04-27 | PBIET10021*4230033 AGENT FEE | DF |  | 0 | 8 | 8 | 0 |  |  | 6879
2021-04-23 | CR 21M2*076 RE 21C3*231 | N/A |  | 0 |  | 0 | 0 | 37453.96 |  | 4760
2021-05-06 | MHTN ARCHITECTS AMD 003 | CO |  | 0 |  | 132934 | 0 |  | 2070304
2021-05-06 | IET INCREASE USU EST REV PER USU FUNDING LETTER MAY 2021 | DF | 275000 | 275000 |  | 0 | 275000 |  |  | 4761
2021-05-13 | ZIONS/HOGAN & ASSOC CONST RTNG GAX 21C5*2198 | DF |  | 0 | 23723 | 0 | 0 |  | 2175183 | 6811
2021-05-13 | HOGAN & ASSOC GAX 21C5*2199 | DF |  | 0 | 450704.53 | 0 | 0 |  | 2175183 | 6811
2021-05-19 | RE 21C3*300 BILL $456,603.40 | N/A |  | 0 |  | 0 | 0 |  |  |  | 456603.4 | 1619.9826
2021-05-13 | WC3 PLAN REVIEW SVCS GAX 21C5*2196 | DF |  | 0 | 220 | 220 | 0 |  |  | 6861
2021-05-19 | SHUMS CODA ASSOC GAX 21C7*1530 | DF |  | 0 | 3246 | 0 | 0 |  | 2170735 | 6873
2021-05-20 | MHTN ARCHITECTS GAX 21C9*164 | DF |  | 0 | 7497.4 | 0 | 0 |  | 2070304 | 6861
2021-05-21 | CR 21M2*085 RE 21C3*267 | N/A |  | 0 |  | 0 | 0 | 22696.82 |  | 4760
2021-05-24 | UTAH STATE UNIV GAX 21C7*1545 | DF |  | 0 | 34984.65 | 0 | 0 |  | 2075026 | 6811
2021-05-27 | ETC GROUP GAX 21C9*194 | DF |  | 0 | 2340 | 0 | 0 |  | 2070068 | 6849
2021-06-04 | UTAH NEW VISION CONST GAX 21C7*1600 | NP |  | 0 | 509.72 | 0 | 0 |  | 2070134 | 6849
2021-06-07 | PBIET100210513114090032 AGENT FEE | NP |  | 0 | 8 | 8 | 0 |  |  | 6879
2021-06-10 | SHUMS CODA ASSOC GAX 21C9*370 | NP |  | 0 | 19132.85 | 0 | 0 |  | 2170735 | 6873
2021-06-14 | RE 21C3*332 BILL $62,824.66 | N/A |  | 0 |  | 0 | 0 |  |  |  | 62824.66 | 0.92473
2021-06-14 | MHTN ARCHI GAX 21C9*431 | NP |  | 0 | 40730.9 | 0 | 0 |  | 2070304 | 6861
2021-06-15 | ZIONS/HOGAN & ASSOC CONST RTNG GAX 21C7*1658 | NP |  | 0 | 24336 | 0 | 0 |  | 2175183 | 6811 |  | WRONG AMOUNT KEYED IN
2021-06-15 | HOGAN & ASSOC GAX 21C7*1659 | NP |  | 0 | 462322.95 | 0 | 0 |  | 2175183 | 6811
2021-06-29 | PBIET 21*60039 AGENT FEES | NP |  | 0 | 8 | 8 | 0 |  |  | 6879
2021-06-29 | USU GAX 21C5*2401 | NP |  | 0 | 14598 | 0 | 0 |  | 2075026 | 6811
2021-06-30 | ZIONS/HOGAN & ASSOC RTNG GAX 21C7*1719 | NP |  | 0 | 39576 | 0 | 0 |  | 2175183 | 6811
2021-06-30 | HOGAN & ASSOC CONST GAX 21C7*1720 | NP |  | 0 | 745649.09 | 0 | 0 |  | 2175183 | 6811 |  | WRONG AMOUNT KEYED IN
2021-06-30 | ZIONS/HOGAN & ASSOC RTNG GAX 21C7*1721 | NP |  | 0 | 35183 | 0 | 0 |  | 2175183 | 6811
2021-06-30 | HOGAN & ASSOC CONST GAX 21C7*1722 | NP |  | 0 | 668449.42 | 0 | 0 |  | 2175183 | 6811
2021-06-30 | ZIONS/HOGAN & ASSOC RTNG GAX 21C7*1723 | NP |  | 0 | 37685 | 0 | 0 |  | 2175183 | 6811
2021-06-30 | HOGAN & ASSOC GAX 21C7*1724 | np |  | 0 | 715896.39 | 0 | 0 |  | 2175183 | 6811 |  | WRONG AMOUNT KEYED IN
2021-06-30 | ZIONS/HOGAN & ASSOC RTNG GAX 21C7*1725 | NP |  | 0 | 38865 | 0 | 0 |  | 2175183 | 6811
2021-06-30 | HOGAN & ASSOC GAX 21C7*1726 | NP |  | 0 | 738345.45 | 0 | 0 |  | 2175183 | 6811
13/21 | MHTN ARCHI GAX 21C9*784 | NP |  | 0 | 12526.6 | 0 | 0 |  | 2070304 | 6861
2021-06-23 | CR 21M2*095 RE 21C3*300 | N/A |  | 0 |  | 0 | 0 | 456603.4 |  | 4760
2021-06-30 | CR 21M2*097 RE 21C3*332 | N/A |  | 0 |  | 0 | 0 | 62824.66 |  | 4760
13/21 | ETC GROUP GAX 21C9*834 | NP |  | 0 | 3435 | 0 | 0 |  | 2070068 | 6849
13/21 | RE 21C3*371 BILL $3,308,308.93 (was $2,072,966.38) | N/A |  | 0 |  | 0 | 0 |  |  |  | 3308308.93 | Need to fix this RE since wrong amount was bill |  | 3316981.2407
13/21 | NSF PROJECT MANAGER FEES | NP |  | 0 | -64319 | 0 | 0 |  | 2075026 | 6811
13/21 | USU GAX 21C5*2502 | NP |  | 0 | 435128.5 | 0 | 0 |  | 2075026 | 6811
13/21 | SHUMS CODA ASSOC GAX 21C9*896 | NP |  | 0 | 4396.05 | 0 | 0 |  | 2170735 | 6873 |  | 0.98919
13/21 | WC3 GAX 21C5*2485 | NP |  | 0 | 110 | 110 | 0 |  |  | 6861
13/21 | RE 21C3*404 BILL $406,541.85 | N/A |  | 0 |  | 0 | 0 |  |  |  | 406541.85
13/21 | JVA 100 21F*944 RETURN ENGERY LOANS THAT WERE DOUBLE DRAWN | NP | -115000 | -115000 |  | 0 | -115000 |  |  | 4737
13/21 | ENERY LOAN FUNDS TRNSFRED FROM PRJ 20415770 | NP | 115000 | 115000 |  | 0 | 115000 |  |  | 4737
13/21 | PBIET 100 21*460039 | NP |  | 0 | 8 | 8 | 0 |  |  | 6879
13/21 | RE 21C3*421 BILL $7.40 |  |  | 0 |  | 0 | 0 |  |  |  | 7.4
13/21 |  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'22 | USU CO 004 | CO |  | 0 |  | 57810.96 | 0 |  | 2075026
2021-07-22 | WC3 GAX 22C5*099 | DF |  | 0 | 440 | 440 | 0 |  |  | 6861
2021-08-16 | HOGAN & ASSOC CONST CO 002 | CO |  | 0 |  | 136746.1 | 0 |  | 2175183
2021-08-23 | CR 22M2*010 RE 21C3*371 | N/A |  | 0 |  | 0 | 0 | 3308308.93 |  | 4760
2021-08-12 | CR 22M2*010 RE 21C3*404 | N/A |  | 0 |  | 0 | 0 | 406541.85 |  | 4760
2021-08-12 | CR 22M2*013 RE 21C3*421 | N/A |  | 0 |  | 0 | 0 | 7.4 |  | 4760
2021-08-23 | USU GAX 22C5*188 | DF |  | 0 | 36158.71 | 0 | 0 |  | 2075026 | 6811
2021-09-03 | RE 22C3*22 BILL $33,843.81 | N/A |  | 0 |  | 0 | 0 |  |  |  | 33843.81
2021-09-14 | PBIET100220925609140046 AGENT FEES | DF |  | 0 | 16 | 16 | 0 |  |  | 6879
2021-09-28 | ZIONS/HOGAN & ASSOC RTNG FC2021092277 | DF |  | 0 | 50293 | 0 | 0 |  | 2175183 | 6811
2021-09-24 | HOGAN & ASSOC FC2021092276 | DF |  | 0 | 955472.17 | 0 | 0 |  | 2175183 | 6811
2021-09-24 | MHTN ARCHI GAX FC20210927207 | DF |  | 0 | 12526.6 | 0 | 0 |  | 2070304 | 6861
2021-09-28 | MHTN ARCHI GAX FC20210930352 | DF |  | 0 | 34084.2 | 0 | 0 |  | 2070304 | 6861
2021-10-01 | UT NEW VISION GAX FC20210930329 | DF |  | 0 | 1711.16 | 0 | 0 |  | 2070134 | 6849
2021-10-01 | RE 22C3*49 BILL $974,757.42 | N/A |  | 0 |  | 0 | 0 |  |  |  | 974757.42
2021-10-18 | HOGAN & ASSOC GAX FC20211015755 | DF |  | 0 | 864457.63 | 0 | 0 |  | 2175183 | 6811
2021-10-15 | SHUMS CODA ASSOC GAX FC20211004479 | DF |  | 0 | 752.4 | 0 | 0 |  | 2170735 | 6873
2021-10-04 | SHUMS CODA ASSOC GAX FC20211004414 | DF |  | 0 | 2855.3 | 0 | 0 |  | 2170735 | 6873
2021-10-04 | IET INCREASE USU EST REV FOR AMA CO 005 | DF | 185716.52 | 185716.52 |  | 0 | 185716.52 |  |  | 4761
2021-10-04 | ZIONS/HOGAN & ASSOC RTNG GAX FC20211015756 | DF |  | 0 | 45502 | 0 | 0 |  | 2175183 | 6811
2021-10-15 | MHTN ARCHI GAX FC202110291029 | DF |  | 0 | 13766 | 0 | 0 |  | 2070304 | 6861
2021-10-29 | USU CO 005 | CO |  | 0 |  | 185716.52 | 0 |  | 2075026
2021-11-03 | MHTN ARCHITECTS GAX FC202111091327 | DF |  | 0 | 20412.7 | 0 | 0 |  | 2070304 | 6861
2021-11-09 | USU GAX FC202111091334 | DF |  | 0 | 30546 | 0 | 0 |  | 2075026 | 6811
2021-11-09 | CR 22M2*027 RE 22C3*022 | N/A |  | 0 |  | 0 | 0 | 33843.81 |  | 4760
2021-10-25 | PBIET 100 22*440044 AGENT FEE | DF |  | 0 | 8 | 8 | 0 |  |  | 6879
2021-11-02 | RE 22C3*82 BILL $912,360.71 | N/A |  | 0 |  | 0 | 0 |  |  |  | 912360.71
2021-11-15 | MHTN ARCHI AMD 004 | CO |  | 0 |  | 28257.32 | 0 |  | 2070304
2021-11-18 | ETC GAX FC202111151383 | DF |  | 0 | 4862 | 0 | 0 |  | 2070068 | 6849
2021-11-15 | UT NEW VISION GAX FC202111151384 | DF |  | 0 | 3212.1 | 0 | 0 |  | 2070134 | 6849
2021-11-15 | HOGAN & ASSOC GAX FC202111151402 | DF |  | 0 | 537711.79 | 0 | 0 |  | 2175183 | 6811
2021-11-15 | ZIONS/HOGAN & ASSOC RTNG GAX FC202111151403 | DF |  | 0 | 28305 | 0 | 0 |  | 2175183 | 6811
2021-11-15 | UT NEW VISION GAX FC202111171462 | DF |  | 0 | 3687.9 | 0 | 0 |  | 2070134 | 6849
2021-11-17 | CR 22M2*034 RE 22C3*049 | N/A |  | 0 |  | 0 | 0 | 974757.42 |  | 4760
2021-11-24 | HOGAN & ASSOC CONSTR- CO 003 | CO |  | 0 |  | 66286.25 | 0 |  | 2175183
2021-11-01 | HOGAN & ASSOC CONSTR - CO 004 | CO |  | 0 |  | 20415.55 | 0 |  | 2175183
2021-11-01 | SHUMS CODA GAX FC202112091841 | DF |  | 0 | 1994.3 | 0 | 0 |  | 2170735 | 6873
2021-12-09 | PBIET100221234715420045 AGENT FEE | DF |  | 0 | 8 | 8 | 0 |  |  | 6879
2021-12-17 | RE 22C3*115 BILL $536,678.68 | N/A |  | 0 |  | 0 | 0 |  |  |  | 536678.68
2021-12-20 | MHTN ARCHI GAX FC202112212062 | DF |  | 0 | 36158.86 | 0 | 0 |  | 2070304 | 6861
2021-12-21 | PBIET 100 22*5420045 AGENT FEE | DF |  | 0 | 8 | 8 | 0 |  |  | 6879
2021-12-17 | USU GAX FC202112232135 | DF |  | 0 | 31330 | 0 | 0 |  | 2075026 | 6811
2021-12-23 | IET INCREASE USU EST REV FOR IMPACT FEES | DF | 232479.36 | 232479.36 |  | 0 | 232479.36 |  |  | 4761
2022-01-01 | SHUMS CODA GAX FC202112302219 | DF |  | 0 | 2178 | 0 | 0 |  | 2170735 | 6873
2022-01-03 | CR 22M2*041 RE 22C3*082 | N/A |  | 0 |  | 0 | 0 | 912360.71 |  | 4760
2022-12-22 | RE 22C3*151 BILL $74,606.82 | N/A |  | 0 |  | 0 | 0 |  |  |  | 74606.82
2022-01-18 | MHTN ARCHI GAX FC202201252645 | DF |  | 0 | 14974.23 | 0 | 0 |  | 2070304 | 6861
2022-01-25 | USU GAX FC202201312804 | DF |  | 0 | 16003 | 0 | 0 |  | 2075026 | 6811
2022-01-31 | CR 22M5*003 RE 22C3*115 | N/A |  | 0 |  | 0 | 0 | 536678.68 |  | 4760
2022-01-27 | UT NEW VISION GAX FC202202022839 | DF |  | 0 | 1470.82 | 0 | 0 |  | 2070134 | 6849
2022-02-02 | SHUMS CODA GAX FC202202042889 | DF |  | 0 | 4998.6 | 0 | 0 |  | 2170735 | 6873
2022-02-04 | HOGAN & ASSOC GAX FC202202072946 | DF |  | 0 | 363503.49 | 0 | 0 |  | 2175183 | 6811
2022-02-07 | ZIONS/HOGAN & ASSOC RTNG GAX FC202202072947 | DF |  | 0 | 19138 | 0 | 0 |  | 2175183 | 6811
2022-02-07 | USU CO 006 | CO |  | 0 |  | 48533.2 | 0 |  | 2075026
2022-02-17 | GRAND WATER & SEWER GAX FC202202092986 | DF |  | 0 | 232479.36 | 232479.36 | 0 |  |  | 6811
2022-02-09 | HOGAN & ASSOC GAX FC202202153098 | DF |  | 0 | 514205.08 | 0 | 0 |  | 2175183 | 6811
2022-02-15 | ZIONS/HOGAN RTNG GAX FC202202153099 | DF |  |  | 27070 | 0 | 0 |  | 2175183 | 6811
2022-02-15 | RE 22C3*180 BILL $1,106,445.65 | N/A |  | 0 |  | 0 | 0 |  |  |  | 1106445.65
2022-02-18 | MHTN ARCHI GAX FC202202173134 | DF |  | 0 | 17626.5 | 0 | 0 |  | 2070304 | 6861
2022-02-17 | HOGAN & ASSOC GAX FC202202183160 | DF |  | 0 | 663503.89 | 0 | 0 |  | 2175183 | 6811
2022-02-18 | ZIONS/HOGAN RTNG GAX FC202202183161 | DF |  | 0 | 34927 | 0 | 0 |  | 2175183 | 6811
2022-02-18 | HOGAN & ASSOC GAX FC202202223204 | DF |  | 0 | 400548.12 | 0 | 0 |  | 2175183 | 6811
2022-02-22 | ZIONS/HOGAN RTNG GAX FC202202223205 | DF |  | 0 | 21085 | 0 | 0 |  | 2175183 | 6811
2022-02-22 | PBIET100221131508540038 AGENT FEE | DF |  | 0 | 8 | 8 | 0 |  |  | 6879
2022-02-24 | USU GAX FC202203013309 | DF |  | 0 | 1870 | 0 | 0 |  | 2075026 | 6811
2022-03-01 | CR 22M5*013 RE 22C3*151 | N/A |  | 0 |  | 0 | 0 | 74606.82 |  | 4760
2022-02-25 | SHUMS CODA ASSOC GAXGC202203043393 | DF |  | 0 | 2032.8 | 0 | 0 |  | 2170735 | 6873
2022-03-04 | ETC GROUP GAX FC202203073439 | DF |  | 0 | 2150 | 0 | 0 |  | 2070068 | 6849
2022-03-07 | RE 22C3*209 BILL $1,060,021.38 | N/A |  | 0 |  | 0 | 0 |  |  |  | 1060021.38
2022-03-11 | USU CO 007 | CO |  | 0 |  | 7100 |  |  | 2075026
2022-03-25 | MHTN ARCHI GAX FC202203293880 | DF |  | 0 | 16341.26 | 0 | 0 |  | 2070304 | 6861
2022-03-29 | PBIET100220307008270043 AGENT FEE | DF |  | 0 | 8 | 8 | 0 |  |  | 6879
2022-03-29 | SHUMS CODA ASSOC GAX FC202204013973 | NP |  | 0 | 732.6 | 0 | 0 |  | 2170735 | 6873
2022-04-01 | CR 22M5*025 RE 22C3*180 | N/A |  | 0 |  | 0 | 0 | 1106445.65 |  | 4760
2022-03-24 | RE 22C3*244 BILL $15,831.36 | N/A |  | 0 |  | 0 | 0 |  |  |  | 15831.36
2022-04-11 | MHTN ARCHI GAX FC202204224401 | DF |  | 0 | 10909.1 | 0 | 0 |  | 2070304 | 6861
2022-04-22 | IET INCREASE USU EST REV FOR AMA CO 008 | DF | 122051.08 | 122051.08 |  | 0 | 122051.08 |  |  | 4761
2022-04-01 | USU CO 008 | CO |  | 0 |  | 122051.08 | 0 |  | 2075026
2022-04-27 | SHUMS CODA GAX FC202205024560 | DF |  | 0 | 1558.35 | 0 | 0 |  | 2170735 | 6873
2022-05-02 | USU GAX FC202205034631 | DF |  | 0 | 39806 | 0 | 0 |  | 2075026 | 6811
2022-05-03 | HOGAN & ASSOC GAX FC202204294548 | DF |  | 0 | 221585.02 | 0 | 0 |  | 2175183 | 6811
2022-04-29 | ZIONS/HOGAN RTNG GAX FC202204294549 | DF |  | 0 | 11667 | 0 | 0 |  | 2175183 | 6811
2022-04-29 | RE 22C3*280 BILL $264,623.18 | N/A |  | 0 |  | 0 | 0 |  |  |  | 264623.18
2022-05-10 | MHTN ARCHITECTS GAX FC202205114913 | DF |  | 0 | 11249.62 | 0 | 0 |  | 2070304 | 6861
2022-05-11 | CR 22M5*052 RE 22C3*209 | N/A |  | 0 |  | 0 | 0 | 1060021.38 |  | 4760
2022-05-12 | CR 22M5*056 RE 22C3*244 | N/A |  | 0 |  | 0 | 0 | 15831.36 |  | 4760
2022-05-20 | HOGAN & ASSOC GAX FC202206025457 | NP |  | 0 | 546533.33 | 0 | 0 |  | 2175183 | 6811
2022-06-02 | ZIONS/HOGAN RTNG GAX FC202206025458 | NP |  | 0 | 28771 | 0 | 0 |  | 2175183 | 6811
2022-06-02 | ETC GROUP GAX FC202206065546 | NP |  | 0 | 15653 | 0 | 0 |  | 2070068 | 6849
2022-06-06 | HOGAN & ASSOC GAX FC202206075617 | NP |  | 0 | 265086.86 | 0 | 0 |  | 2175183 | 6811
2022-06-07 | ZIONS/HOGAN & ASSOC RTNG GAX FC202206075618 | NP |  | 0 | 13953 | 0 | 0 |  | 2175183 | 6811
2022-06-07 | PBIET100220513108540042 AGENT FEE | NP |  | 0 | 8 | 8 | 0 |  |  | 6879
2022-06-08 | RE 22C3*313 BILL $816,741.31 | NP |  | 0 |  | 0 | 0 |  |  |  | 816741.31
2022-06-14 | HOGAN & ASSOC GAX FC202206145881 | NP |  | 0 | 14297 | 0 | 0 |  | 2175183 | 6811
2022-06-14 | ZIOS/HOGAN ASSOC RTNG GAX FC202206145882 | NP |  | 0 | 753 | 0 | 0 |  | 2175183 | 6811
2022-06-14 | MHTN ARCHI GAX FC202206226009 | NP |  | 0 | 3749.88 | 0 | 0 |  | 2070304 | 6861
2022-06-22 | UT ST UNIV GAX 22C5*461 | NP |  | 0 | 455964.38 | 0 | 0 |  | 2075026 | 6811
2022-06-30 | HOGAN & ASSOC GAX 22C7*177 | NP |  | 0 | 28545.11 | 0 | 0 |  | 2175183 | 6811
2022-06-30 | ZIONS/HOGAN RTNG GAX 22C7*178 | NP |  | 0 | 1504 | 0 | 0 |  | 2175138 | 6811
2022-06-30 | PBIET100220204207340042 AGENT FEES | NP |  | 0 | 24 | 24 | 0 |  |  | 6879
2022-06-30 | RE 22C3*349 BILL $467,880.87 | N/A |  | 0 |  | 0 | 0 |  |  |  | 467880.87
13/22 | CR 22M5*072 RE 22C3*280 | N/A |  | 0 |  | 0 | 0 | 264623.18 |  | 4760
2022-06-23 | USU GAX 22C9*818 | NP |  | 0 | 326789.5 | 0 | 0 |  | 2075026 | 6811
13/22 | RE 22C3*384 BILL $302,866.42 | N/A |  | 0 |  | 0 | 0 |  |  |  | 302866.42
13/22 |  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'23 | CR 23M5*001 RE 22C3*313 | N/A |  | 0 |  | 0 | 0 | 816741.31 |  | 4760
2022-07-08 | CR 23M5*011 RE 22C3*384 | N/A |  | 0 |  | 0 | 0 | 302866.42 |  | 4760
2022-08-04 | CR 23M5*011 RE 22C3*349 | N/A |  |  |  | 0 | 0 | 467880.87 |  | 4760
2022-08-04 | HOGAN & ASSOC CO 005 | CO |  | 0 |  | 8337.79 | 0 |  | 2175183
2022-08-26 | USU CO 009 | CO |  | 0 |  | 23621.78 | 0 |  | 2075026
2022-08-26 | USU GAX FC202209067816 | DF |  | 0 | 13435.31 | 0 | 0 |  | 2075026 | 6811
2022-09-06 | HOGAN & ASSOC GAX FC202209128011 | DF |  | 0 | 936308.63 | 0 | 0 |  | 2175183 | 6811
2022-09-12 | RE 23C3*26 BILL $880,216.59 | N/A |  | 0 |  | 0 | 0 |  |  |  | 880216.59
2022-09-15 | HOGAN & ASSOC GAX FC202209299006 | DF |  | 0 | 44997.11 | 0 | 0 |  | 2175183 | 6811
2022-09-29 | RE 23C3*67 BILL $41,703.04 | N/A |  | 0 |  | 0 | 0 |  |  |  | 41703.04
2022-10-18 | CR 23M5*039 RE 23C3*026 | N/A |  | 0 |  | 0 | 0 | 880216.59 |  | 4760
2022-10-21 | USU GAX FC2022102710181 | DF |  | 0 | 259355.16 | 0 | 0 |  | 2075026 | 6811
2022-10-27 | HOGAN & ASSOC CO 006 | CO |  | 0 |  | 0 | 0 |  | 2175183
2022-11-04 | RE 23C3*105 BILL $240,368.70 | N/A |  | 0 |  | 0 | 0 |  |  |  | 240368.7 | 240461.361
2022-11-18 | CR 23M5*051 RE 23C3*067 | N/A |  | 0 |  | 0 | 0 | 41703.04 |  | 4760
2022-11-29 | ETC GROUP GAX FC2022121212232 | DF |  | 0 | 13239 | 0 | 0 |  | 2070068 | 6849
2022-12-12 | USU GAX FC2022121312312 | DF |  | 0 | 144 | 0 | 0 |  | 2075026 | 6811 |  | RESERVES CHECKED TO THIS POINT
2022-12-13 | RE 23C3*141 BILL $12,403.27 | N/A |  | 0 |  | 0 | 0 |  |  |  | 12403.27
2022-12-16 | MHTN ARCHI AMD 005 | CO |  | 0 |  | 15710 | 0 |  | 2070304
2022-12-23 | USU GAX FC2023012113843 | DF |  | 0 | 115169.77 | 0 | 0 |  | 2075026 | 6811
2023-01-21 | HOGAN & ASSOC CO 007 | CO |  | 0 |  | -2079.64 | 0 |  | 2175183
2023-01-27 | USU GAX FC2023021314945 | DF |  | 0 | 1483.13 | 0 | 0 |  | 2075026 | 6811
2023-02-13 | RE 23C3*208 BILL $108,113.16 | N/A |  | 0 |  | 0 | 0 |  |  |  | 108113.16
2023-02-28 | CR 23M5*072 RE 23C3*141 | N/A |  | 0 |  | 0 | 0 | 12403.27 |  | 4760 |  |  | 0.92715
2023-01-24 | CR 23M5*075 RE 23C3*105 | N/A |  | 0 |  | 0 | 0 | 240368.7 |  | 4760
2023-01-31 | MHTN ARCHITECTS INC - GAX FC2023032116508 | DF |  | 0 | 15710 | 0 | 0 |  | 2070304 | 6861
2023-03-21 | CR 23M5*112 RE 23C3*208 | N/A | [5 empty] | 108113.16 |  | 4760
2023-04-10 | RE 23C3*243 BILL $14,559.93 | N/A |  | 0 |  | 0 | 0 |  |  |  | 14559.93
2023-04-12 | USU CO 010 | CO |  | 0 |  | 15107.58 | 0 |  | 2075026
2023-03-23 | CR 23M5*130 RE 23C3*243 | N/A |  | 0 |  | 0 | 0 | 14559.93 |  | 4760
2023-05-18 | PBIET150230204407220043 AGENT FEE | DF |  | 0 | 8 | 8 | 0 |  |  | 6879
2023-05-24 | RE 23C3*313 BILL $7.42 | N/A |  | 0 |  | 0 | 0 |  |  |  | 7.42 | 7.4172
2023-06-15 | USU CO 011 | CO |  | 0 |  | 6085 | 0 |  | 2075026
2023-06-12 | HOGAN & ASSOC CO 008 | CO |  | 0 |  | 71019.64 | 0 |  | 2175183
2023-06-15 | USU GAX FC20230713222356 |  |  | 0 | 7043.16 | 0 | 0 |  | 2075026 | 6811
13/23 | USU GAX FC2023071322359 |  |  | 0 | 7043.16 | 0 | 0 |  | 2075026 | 6811
13/23 | PBIET150230925615110048 AGENT FEE |  |  | 0 | 8 | 8 | 0 |  |  | 6879
13/23 | HOGAN & ASSOC GAX FC2023072823039 |  |  | 0 | 163872.78 | 0 | 0 |  | 2175183 | 6811
13/23 | ZIONS/HOGAN ASSOC RTNG GAX FC2023072823040 |  |  | 0 | 2217 | 0 | 0 |  | 2175183 | 6811
13/23 | RE 23C3*391 BILL $167,727.49 | N/A |  | 0 |  | 0 | 0 |  |  |  | 167727.49 | 167057.8442
13/23 |  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'24 | USU GAX FC2023081523668 | DF |  | 0 | 6250 | 0 | 0 |  | 2075026 | 6811
2023-08-15 | CR 23M5*148 RE 23C3*313 | N/A |  | 0 |  | 0 | 0 | 7.42 |  | 4760
2023-07-05 | CR 24M5*015 RE 23C3*391 | N/A |  | 0 |  | 0 | 0 | 167727.49 |  | 4760
2023-08-17 | ETC GROUP GAX F23*097 | DF |  | 0 | 2505 | 0 | 0 |  | 2070068 | 6849
2023-08-30 | UT NEW VISION GAX F23*127 | DF |  | 0 | 1300 | 0 | 0 |  | 2070134 | 6849
2023-09-08 | RE 24C3*24 BILL $9,318.90 | N/A |  | 0 |  | 0 | 0 |  |  |  | 9318.9 | 9322.502
2023-09-13 | CR 24M5*044 RE 24C3*024 | N/A |  | 0 |  | 0 | 0 | 9318.9 |  | 4760
2023-10-30 | USU GAX FC2023111727852 | DF |  | 0 | 2382 | 0 | 0 |  | 2075026 | 6811
2023-11-17 | HOGAN & ASSOC CO 009 | CO |  | 0 |  | -141126.04 | 0 |  | 2175183 |  |  |  |  | 0.92715
2023-11-28 | RE 24C3*114 BILL $1,473.61 | N/A |  | 0 |  | 0 | 0 |  |  |  | 1473.61 | 2208.4734
2023-12-15 | USU GAX FC2024010429868 | DF |  | 0 | 4679.16 | 0 | 0 |  | 2270379 | 6864
2024-01-04 | RE 24C3*144 BILL $4,336.61 | N/A |  | 0 |  | 0 | 0 |  |  |  | 4336.61 | 4338.2872
2024-01-18 | HOGAN & ASSOC CO 010 | CO |  | 0 |  | 141126.04 | 0 |  | 2175183
2024-12-14 | CR 24M5*077 RE 24C3*114 | N/A | [5 empty] | 1473.61 |  | 4760
2024-02-07 | USU GAX FC2024032133582 | DF |  |  | 25050.9 |  |  |  | 2075026 | 6811
2024-03-21 | CR 24M5*090 RE 24C3*144 | N/A | [5 empty] | 4336.61 |  | 4760
2024-03-14 | RE 24C3*231 | N/A | [8 empty] | 23217.02
2024-04-18 | USU GAX FC2024041834967 | DF |  |  | 8230.84 |  |  |  | 2075026 | 6811
2024-04-18 | IET INCREASE USU EST REV | DF | 74697.04 | 74697.04 |  | 0 | 74697.04 |  |  | 4760
2024-04-03 | CR 24M5*114 RE 24C3*231 | N/A | [5 empty] | 23217.02 |  | 4760
2024-05-31 | RE 24C3*374 | [9 empty] | 12949.7
FY'25
2024-09-09 | HOGAN & ASSOC GAX FC2024090942169 | DF |  |  | 133136.66 |  |  |  | 2175183 | 6811
2024-09-09 | ZIONS/HOGAN ASSOC RTNG GAX FC2024090942170 | DF |  |  | 7007.19 |  |  |  | 2175183 | 6811
2024-09-30 | RE 25C3*28 | N/A | [8 empty] | 129934.5
2024-10-31 | CR 25M5*042 RE 25C3*028 | N/A | [5 empty] | 129934.5 |  | 4760
2024-12-03 | USU CO 012 | CO |  |  |  | -37546.54 |  |  | 2075026
2024-12-18 | MHTN ARCHI GAX FC2024121846875 |  |  |  | 3349.87 |  |  |  | 2070304 | 6861
2024-12-19 | RE 25C3* | [9 empty] | 3105.83
BILL USU ALL BUT 1,115,000

## EXPENDITURES
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
USU MOAB ACADEMIC BUILDING
PROJECT #20149770
EXPENDITURE TOTALS TO JULY 9, 2021
FUNDING:
USU FUNDING | 14190603.92
STATE FY'20 PASS-THROUGH FUNDING | 1000000
DFCM ENERGY LOAN FUND | 115000
TOTAL AVAILABLE FUNDING |  | 15305603.92 | 122051.08 | 4433332.16
11419959.84
EXPENDITURES TO DATE: |  | ACTUAL EXPENDITURES |  | 15853292
DESIGN |  |  |  | 15853292
MHTN Architects Inc - Programming |  | 63500
MHTN Architects Inc - Design |  | 553180.5
Sound Geothermal Corp |  | 16985
WC3 - plan reviews |  | 1210
Utah State Fire Marshall Review |  | 484
Misc. Expendtiures |  | 307.02
COMMISSIONING
ETC Group - Commissioning |  | 61590
Utah New Vision Construction |  | 9018.02
CONSTRUCTION
Hogan & Assoc Construction Inc. |  | 45000
Hogan & Assoc Construction Inc. |  | 4524937.83
Geo Energy Systems |  | 10000
USU AMA for Furnishings, IT, AV, USU fees, etc. |  | 366992.4
COURSE OF CONSTRUCTION INSURANCE |  | 6270.42
INSPECTION
Shums Coda Assoc Inc |  | 25883.95
DFCM MANAGEMENT FEES |  | 63500
EXPENDITURES TO DATE |  | 5748859.14

## CHECK CLEAR
Check/EFT Number | Bank Clear Date | EFT Effective Date | Vendor Number | Vendor Name | Dept | Unit | Invoice Number | Ref Tran ID | Line Description | Amount
12605253 | 2019-07-23 |  | 35454H | FEDERAL EXPRESS CO GOVERNMENT SALES | 300 | 3401 | 6-595-67717 | GMA30019C2000001 | ACCT 1037-7558-2 TRK 814577815590 LANA EDWARDS WAYMS, SLC TO DEREK APYNE, SLC | 6.85
12605253 | 2019-07-23 |  | 35454H | FEDERAL EXPRESS CO GOVERNMENT SALES | 300 | 3401 | 6-595-67717 | GMA30019C2000001 | ACCT 1037-7558-2 TRK 814577815784 DFCM, SLC TO THOMAS GRAHAM, LOGAN | 6.85
12605253 | 2019-07-23 |  | 35454H | FEDERAL EXPRESS CO GOVERNMENT SALES | 300 | 3401 | 6-595-67717 | GMA30019C2000001 | ACCT 1037-7558-2 TRK 814577815670 DFCM, SLC TO MATT BOYER, MORGAN | 16.19
12605253 | 2019-07-23 |  | 35454H | FEDERAL EXPRESS CO GOVERNMENT SALES | 300 | 3401 | 6-595-67717 | GMA30019C2000001 | ACCT 1037-7558-2 TRK 814577815681 DFCM, SLC TO THOMAS GRAHAM | 6.85
12661809 | 2019-09-18 |  | 04407C | MHTN ARCHITECTS INC | 300 | 3401 | 26637 | GAX30020C5000324 | CONTRACT 2070008 - USU MOAB ACADEMIC BUILDING | 25400
12678015 | 2019-10-01 |  | 04407C | MHTN ARCHITECTS INC | 300 | 3401 | 26730 | GAX30020C5000569 | CONTRACT 2070008 - USU MOAB ACADEMIC BUILDING | 22225
12724607 | 2019-11-13 |  | VC0000179201 | SOUND GEOTHERMAL CORP | 300 | 3401 | 110626 | GAX30020C5001203 | PO 169261 - MOAB ACADEMIC BUILDING | 10185
12699681 | 2019-10-24 |  | 46614D | ETC GROUP INC | 300 | 3401 | 19-10066-2 | GAX30020C5000873 | CONTRACT 2070068 - USU MOAB ACADEMIC BUILDING | 4500.6
12701358 | 2019-10-28 |  | VC0000179201 | SOUND GEOTHERMAL CORP | 300 | 3401 | 110617 | GAX30020C5000900 | PO 169261 - UTAH STATE UNIVERSITY MOAB ACADEMIC BUILDING | 6800
12701420 | 2019-10-22 |  | VC226150 | GEO ENERGY SYSTEMS INC | 300 | 3401 | 20149770-1 | GAX30020C5000901 | PO 169421 - UTAH STATE UNIVERSITY MOAB ACADEMIC BUILDING | 10000
12672134 | 2019-09-24 |  | 46614D | ETC GROUP INC | 300 | 3401 | 19-066 - 1 | GAX30020C5000514 | CONTRACT 2070068 - USU MOAB ACADEMIC BUILDING | 4616
12720022 | 2019-11-13 |  | 04407C | MHTN ARCHITECTS INC | 300 | 3401 | 26796 | GAX30020C5001141 | CONTRACT 2070008 - USU MOAB ACADEMIC BUILDING | 6350
12752583 | 2019-12-12 |  | 46614D | ETC GROUP INC | 300 | 3401 | 19-10066 - 3 | GAX30020C5001459 | CONTRACT 2070068 - USU MOAB ACADEMIC BUILDING | 2885
12759210 |  |  | 46614D | ETC GROUP INC | 300 | 3401 | 19-10066-3 | GAX30020C8000126 | CONTRACT 2070068-USU Moab Academic Buildling - Cx | 2885
12759210 |  |  | 46614D | ETC GROUP INC | 300 | 3401 | 19-10066-3 | GAX30020C8000126 | CONTRACT 2070068-USU Moab Academic Buildling - Cx | -2885
12774444 | 2020-01-07 |  | 46614D | ETC GROUP INC | 300 | 3401 | 19-10066-4 | GAX30020C8000153 | CONTRACT 2070068-USU MOAB ACADEMIC BUILDING COMMISSIONING | 1673.3
12810334 | 2020-02-14 |  | 46614D | ETC GROUP LLC | 300 | 3401 | 19-10066-5 | GAX30020C5002005 | CONTRACT 2070068 - USU MOAB ACADEMIC BUILDING | 1904.1
12814539 | 2020-02-19 |  | 89347A | UTAH NEW VISION CONSTRUCTION | 300 | 3401 | 4529 | GAX30020C8000228 | CONTRACT 2070134-USU MOAB ACADEMIC BLDG | 500
12816091 | 2020-02-24 |  | 04407C | MHTN ARCHITECTS INC | 300 | 3401 | 26892 | GAX30020C7000528 | 2070008-UTAH STATE UNIVERSITY MOAB ACADEMIC BUILDING | 9525
12838504 | 2020-03-10 |  | 89347A | UTAH NEW VISION CONSTRUCTION | 300 | 3401 | 137 | GAX30020C7000644 | 2070134-UTAH STATE UNIVERSITY MOAB ACADEMIC CLASSROOM BUILDING - BECX | 500
12838446 | 2020-03-10 |  | 46614D | ETC GROUP LLC | 300 | 3401 | 19-10066-6 | GAX30020C5002146 | CONTRACT 2070068 - UTAH STATE UNIVERSITY MOAB ACADEMIC CLASSROOM BUILDING | 4616
12861738 | 2020-04-09 |  | 04407C | MHTN ARCHITECTS INC | 300 | 3401 | 27183 | GAX30020C5002247 | CONTRACT 2070304 - USU MOAB ACADEMIC BUILDING | 179752
12886755 | 2020-04-21 |  | 46614D | ETC GROUP LLC | 300 | 3401 | 19-10066-7 | GAX30020C5002534 | CONTRACT 2070068 - USU MOAB ACADEMIC CLASSROOM BUILDING | 2885
12892020 | 2020-04-30 |  | 04407C | MHTN ARCHITECTS INC | 300 | 3401 | 27250 | GAX30020C5002664 | CONTRACT 2070304 - USU MOAB ACADEMIC BUILDING | 21712
12897787 | 2020-05-04 |  | 46614D | ETC GROUP LLC | 300 | 3401 | 19-10066-8 | GAX30020C5002724 | USU MOAB ACADEMIC CLASSROOM BUILDING - COMMISSIONING | 11040
12954675 | 2020-06-11 |  | 46614D | ETC GROUP LLC | 300 | 3401 | 19-10066-9 | GAX30020C7000891 | 2070068-UTAH STATE UNIVERSITY MOAB ACADEMIC CLASSROOM BUILDING COMMISSIONING | 7915
12983124 | 2020-06-25 |  | 04407C | MHTN ARCHITECTS INC | 300 | 3401 | 27390 | GAX30020C5003588 | CONTRACT 2070304 - USU MOAB ACADEMIC BUILDING | 10376
13015041 | 2020-07-16 |  | 04407C | MHTN ARCHITECTS INC | 300 | 3401 | 27422 | GAX30020C7000944 | 2070304-UTAH STATE UNIVERSITY MOAB ACADEMIC BUILDING | 30762.4
202007060312370 |  | 2020-07-08 | 35208H | HOGAN & ASSOCIATES CONSTRUCTION INC | 300 | 3401 | 20149770#1 | GAX30020C7000987 | 2075009-USU Moab Academic Building | 36200
13104390 |  |  | 04407C | MHTN ARCHITECTS INC | 300 | 3401 | 27529 | GAX30021C5000228 | CONTRACT 2070304 - USU MOAB ACADEMIC BUILDING | 70049.6
482408.74