## PROJECT
RESERVES:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR
| FUNDING |  | HEF USU |  |  |  | DESIGN |  |  |  |  | -406619.78
| STATE RISK NUMBER |  | 18525 |  |  |  | INSPECTION
| PROJECT TITLE |  | USU NEW PARKING TERRACE |  |  |  | INSURANCE
| PROJECT # |  | 20011770 | OPEN |  |  | CONTINGENCY/LEGAL
| CODING BLOCK |  | 3000-300-3401-FWA-20011770 |  |  | 0 | TOTAL | 0
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
12006619.78
YR | CURRENT TOTALS |  | 14835833.78 | 0 | 14835833.78 | 14835833.78 | 0 | 12006619.78 |  |  | 12006619.78 | 0
[11 empty] | 0 | -12006619.78
|  |  |  | 0 |  | 0 | 0
FY'19 |  |  |  | 0 |  | 0 | 0
2019-01-29 | VCBO ARCHITECTURE - CONTRACT | N/A |  | 0 |  | 29000 | 0 |  | 1970294
2019-02-01 | IET USU EST REV FOR PROGRAMMING | SS | 100000 | 100000 |  | 0 | 100000 |  |  | 4761
2019-03-29 | VCBO ARCHITECTURE - AMD 001 | CO |  | 0 |  | 16370 | 0 |  | 1970294
2019-06-18 | VCBO ARCHITECTURE PRC 19C5-598 | EH |  | 0 | 4275 | 0 | 0 |  | 1970294 | 6861
13/19 | VCBO ARCHITECT PRC 19C5-1063 | EH |  | 0 | 18751.78 | 0 | 0 |  | 1970294 | 6861
13/19 | VCBO ARCHITECT PRC 19C5-1065 | EH |  | 0 | 12475 | 0 | 0 |  | 1970294 | 6861
13/19 | VCBO ARCHITECT PRC 19C5*1064 | EH |  | 0 | 9610 | 0 | 0 |  | 1970294 | 6861
13/19 | RE 19C3-412 BILL $45,111.78 | N/A |  | 0 |  | 0 | 0 |  |  |  | 45111.78
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'20 |  |  |  | 0 |  | 0 | 0
2019-08-01 | RALPH WADSWORTH CONSTR - CONTRACT | N/A |  | 0 |  | 10374085 | 0 |  | 2075038
2019-08-05 | FED EX GMA F19-5 | DF |  | 0 | 14.94 | 14.94 | 0 |  |  | 6879
2019-08-02 | CR 20M2-013 RE 19C3-412 | N/A |  | 0 |  | 0 | 0 | 45111.78
2019-09-04 | RALPH WADSWORTH CO 001 | CO |  | 0 |  | 541680 | 0 |  | 2075038
2019-09-24 | RE 20C3 BILL $14.94 | N/A |  | 0 |  | 0 | 0 |  |  |  | 14.94
2019-09-30 | CACHE LANDMARK ENG GAX 20C5-647 | DF |  | 0 | 4440 | 4440 | 0 |  |  | 6864
2019-10-01 | IET INCREASE USU EST REV FOR FULL PROJECT FUNDING | DF | 11600000 | 11600000 |  | 0 | 11600000 |  |  | 4761
2019-10-15 | ZIONS/RALPH L WADSWORTH RTNG GAX 20C5*855 | DF |  | 0 | 59315 | 0 | 0 |  | 2075038 | 6811
2019-10-15 | RALPH L WADSWORTH GAX 20C5*856 | DF |  | 0 | 1126976 | 0 | 0 |  | 2075038 | 6811
2019-10-18 | W3 GAX 20C5*865 | DF |  | 0 | 1100 | 1100 | 0 |  |  | 6861
2019-10-30 | RE 20C3- 73 BILL $1,191,831.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 1191831
2019-11-04 | ZIONS/RALPH L WADSWORTH RTNG GAX 20C5-1152 | DF |  | 0 | 73388 | 0 | 0 |  | 2075038 | 6811
2019-11-04 | RALPH L WADSWORTH CONST GAX 20C5-1153 | DF |  | 0 | 1394316 | 0 | 0 |  | 2075038 | 6811
2019-10-24 | CR 20M2-045 RE 20C3-027 | N/A |  | 0 |  | 0 | 0 | 14.94
2019-11-05 | IDT 20C3*008 PRJ MGR FEE | DF |  | 0 | 64508 | 64508 | 0 |  |  | 6865
2019-11-05 | IET INCREASE USU EST PER REVISED CBE | DF | 453400 | 453400 |  | 0 | 453400 |  |  | 4761
2019-12-03 | CMT ENG LAB GAX 20C5*1438 | DF |  | 0 | 6350 | 6350 | 0 |  |  | 6864
2019-12-03 | WC3 CONSULTS GAX 20C5*1441 | DF |  | 0 | 110 | 110 | 0 |  |  | 6861
2019-12-10 | ZIONS/RALPH WADSWORTH RTNG GAX 20C5*1493 | DF |  | 0 | 21788 | 0 | 0 |  | 2075038 | 6811
2019-12-10 | RALPH L WADSWORTH CONST GAX 20C5*1494 | DF |  | 0 | 413900 | 0 | 0 |  | 2075038 | 6811
2019-12-03 | CR 20M2-060 RE 20C3-073 | N/A |  | 0 |  | 0 | 0 | 1191831
2019-12-16 | RE 20C3*119 BILL $1,974,360.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 1974360
2020-01-07 | QUALITY ASSURANCE ENG GAX 20C5*1729 | DF |  | 0 | 10697.95 | 0 | 0 |  | 2070179 | 6873
2020-01-10 | ZIONS/RALPH L WADSWORTH RTNG GAX 20C7*350 | DF |  | 0 | 29961 | 0 | 0 |  | 2075038 | 6811
2020-01-10 | RALPH L WADSWORTH GAX 20C7*351 | DF |  | 0 | 596203 | 0 | 0 |  | 2075038 | 6811
2020-01-14 | RE 20C3*158 BILL $636, 861.95 | N/A |  | 0 |  | 0 | 0 |  |  |  | 636861.95
2019-11-01 | CONSOLIDATED ENGINEERING CONTRACT | N/A |  | 0 |  | 115393.5 | 0 |  | 2070179
2020-02-01 | COFC INSURANCE ITA 300 -2-037 | DF |  | 0 | 6025.66 | 6025.66 | 0 |  |  | 6872 |  |  | 2803491.9
2020-02-04 | ZIONS/RALPH L WADSWORTH RTNG GAX 20C5*1952 | DF |  | 0 | 51912 | 0 | 0 |  | 2075038 | 6811
2020-02-04 | RALPH L WADSWORTH CONST GAX 20C5*1953 | DF |  | 0 | 986268 | 0 | 0 |  | 2075038 | 6811
2020-01-27 | CR 20M2-078 RE 20C3-119 | N/A |  | 0 |  | 0 | 0 | 1974360
2020-02-18 | RE 20C3*199 BILL $1,044,205.66 | N/A |  | 0 |  | 0 | 0 |  |  |  | 1044205.66
2020-03-05 | RALPH L WADSWORTH CONST CO 002 | CO |  | 0 |  | 394251 | 0 |  | 2075038
2020-02-24 | CR 20M2-088 RE 20C3-158 | N/A |  | 0 |  | 0 | 0 | 636861.95
2020-03-11 | ZIONS/RL WADSWORTH RTNG GAX 20C5*2170 | DF |  | 0 | 31453 | 0 | 0 |  | 2075038 | 6811
2020-03-11 | RALPH L WADSWORTH GAX 20C5*2171 | DF |  | 0 | 570538 | 0 | 0 |  | 2075038 | 6811
2020-03-11 | USU CONTROLLERS OFFICE GAX 20C8*352 | DF |  | 0 | 680 | 0 | 0 |  | 2075296 | 6824
2020-04-01 | ZIONS/R L WADSWORTH RTNG GAX 20C5*2343 | DF |  | 0 | 53545 | 0 | 0 |  | 2075038 | 6811
2020-04-01 | RALPH L WADSWORTH CONST GAZ 20C5*2344 | DF |  | 0 | 1017255 | 0 | 0 |  | 2075038 | 6811
2020-03-30 | CR 20M2-103 RE 20C3-199 | N/A |  | 0 |  | 0 | 0 | 1044205.66
2020-02-01 | USU CONTROLLERS OFFICE - AMA | N/A |  | 0 |  | 479272 | 0 |  | 2075296
2019-07-01 | VCBO ARCHITECTURE- AMD002 | CO |  | 0 |  | -258.22 | 0 |  | 1970294
2020-04-13 | RE 20C3*262 BILL $1,673,471.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 1673471
2020-04-18 | RALPH L WADSWORTH CONST CO 003 | CO |  | 0 |  | 65848 | 0 |  | 2075038
2020-04-21 | QUALITY ASSURANCE ENG GAX 20C8*494 | DF |  | 0 | 7083.55 | 0 | 0 |  | 2070179 | 6873
2020-04-21 | QUALITY ASSURANCE ENG GAX 20C8*496 | DF |  | 0 | 10152.9 | 0 | 0 |  | 2070179 | 6873
2020-04-28 | QUALITY ASSURANCE ENG GAX 20C8*506 | DF |  |  | 10586.7 |  |  |  | 2070179 | 6873
2020-05-06 | ZIONS/RALPH L WADSWORTH RTNG GAX 20C5*2846 | DF |  | 0 | 42808 | 0 | 0 |  | 2075038 | 6811
2020-05-06 | RALPH L WADSWORTH CONST GAX 20C5*2847 | DF |  | 0 | 813311 | 0 | 0 |  | 2075038 | 6811
2020-05-13 | RE 20C3*302 BILL $883,942.15 | N/A |  | 0 |  | 0 | 0 |  |  |  | 883942.15
2020-05-22 | CR 20M2-117 RE 20C3-262 | N/A |  | 0 |  | 0 | 0 | 1673471
2020-06-04 | RALPH L WADSWORTH CONST CO 004 | CO |  | 0 |  | 153059 | 0 |  | 2075038
2020-06-04 | QUALITY ASSURANCE ENG GAX 20C8*562 | PG |  | 0 | 11293.2 | 0 | 0 |  | 2070179 | 6873
2020-06-12 | RE 20C3*340 BILL $11,293.20 | N/A |  | 0 |  | 0 | 0 |  |  |  | 11293.2
2020-06-18 | CR 20M2-123 RE 20C3-302 | N/A |  | 0 |  | 0 | 0 | 883942.15
2020-06-23 | UTAH STATE UNIV GAX 20C5*3627 | PG |  | 0 | 106593.75 | 0 | 0 |  | 2075296 | 6824
2020-06-23 | RALPH L WADSWORTH CONST GAX 20C8*614 | PG |  | 0 | 1265107 | 0 | 0 |  | 2075038 | 6811
2020-06-23 | ZIONS/RALPH WADSWORTH RTNG GAX 20C8*615 | PG |  | 0 | 66589 | 0 | 0 |  | 2075038 | 6811
2020-06-30 | QUALITY ASSUR ENG GAX 20C8*624 | DW |  | 0 | 13332 | 0 | 0 |  | 2070179 | 6873
13/20 | RE 20C3*384 BILL $1,451,621.75 | N/A |  | 0 |  | 0 | 0 |  |  |  | 1451621.75
13/20 | WC3 GAX 20C5*3879 | DW |  | 0 | 550 | 550 | 0 |  |  | 6861
2020-06-30 | CR 20M2-126 RE 20C3-340 | N/A |  | 0 |  | 0 | 0 | 11293.2
13/20 | UTAH STATE UNIV GAX 20C7*1108 | DW |  | 0 | 35531.25 | 0 | 0 |  | 2075296 | 6824
13/20 | QUALITY ASSURANCE ENG GAX 20C8*832 | DW |  | 0 | 5167.8 | 0 | 0 |  | 2070179 | 6873
13/20 | ZIONS/RALPH WADSWORTH RTNG GAX 20C5-3978 | NP |  | 0 | 47294 | 0 | 0 |  | 2075038 | 6811
13/20 | RALPH WADSWORTH CONST GAX 20C5-3979 | NP |  | 0 | 898446 | 0 | 0 |  | 2075038 | 6811
13/20 | RE 20C3*429 BILL$986,989.05 (was $41,249.05) | N/A |  | 0 |  | 0 | 0 |  |  |  | 986989.05
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'21 |  |  |  | 0 |  | 0 | 0
2020-07-23 | RALPH L WADSWORTH CONST CO 005 | CO |  | 0 |  | 2479239 | 0 |  | 2075038
2020-08-11 | WC3 GAX 21C5*135 | DF |  | 0 | 660 | 660 | 0 |  |  | 6861
2020-08-17 | ZIONS/RALPH L WADSWORTH RTNG GAX 21C5*192 | DF |  | 0 | 51466 | 0 | 0 |  | 2075038 | 6811
2020-08-17 | RALPH L WADSWORTH GAX 21C5*193 | DF |  | 0 | 977803 | 0 | 0 |  | 2075038 | 6811
2020-07-31 | CR 21M2-008 RE 20C3-384 | N/A |  | 0 |  | 0 | 0 | 1451621.75
2020-08-18 | CR 21M2-014 RE 20C3-429 | N/A |  | 0 |  | 0 | 0 | 986989.05
2020-09-11 | RE 21C3*019 BILL $1,029,929.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 1029929
2020-09-15 | ZIONS/RALPH L WADSWORTH RTNG GAX 21C5*358 | DF |  | 0 | 40163 | 0 | 0 |  | 2075038 | 6811
2020-09-15 | RALPH L WADSWORTH GAX 21C5*359 | DF |  | 0 | 762945 | 0 | 0 |  | 2075038 | 6811
2020-09-15 | USU GAX 21C5*360 | DF |  | 0 | 2879.25 | 0 | 0 |  | 2075296 | 6824
2020-09-15 | WC3 GAX 21C5*353 | DF |  | 0 | 110 | 110 | 0 |  |  | 6861
2020-10-20 | IET TRNSF FY'21 CAP IMPR FUNDS FROM 21247300 | DF | 3000000 | 3000000 |  | 0 | 3000000 |  |  | 4667
2020-10-14 | RE 21C3*53 BILL $806,097.25 | N/A |  | 0 |  | 0 | 0 |  |  |  | 806097.25
2020-10-16 | ZIONS/RALPH L WADSWORTH RTNG GAX 21C7*253 | DF |  | 0 | 58278 | 0 | 0 |  | 2075038 | 6811
2020-10-16 | RALPH L WADSWORTH GAX 21C7*254 | DF |  | 0 | 1107202 | 0 | 0 |  | 2075038 | 6811
2020-10-23 | UTAH STATE UNIV GAX 21C5*644 | DF |  | 0 | 72361.38 | 0 | 0 |  | 2075296 | 6824
2020-10-23 | RALPH L WADSWORTH CONSTRUCTION CO 006 | CO |  | 0 |  | 20523 | 0 |  | 2075038
2020-11-09 | QUALITY ASSUR ENG GAX F20*099 | DF |  | 0 | 6985 | 0 | 0 |  | 2070179 | 6873
2020-11-12 | ZIONS/RALPH L WADSWORTH CONST RTNG GAX 21C5*753 | DF |  | 0 | 30596 | 0 | 0 |  | 2075038 | 6811
2020-11-12 | RALPH L WADSWORTH GAX 21C5*754 | DF |  | 0 | 581258 | 0 | 0 |  | 2075038 | 6811
2020-11-20 | RE 21C3*87 BILL $1,856,680.38 | N/A |  | 0 |  | 0 | 0 |  |  |  | 1856680.38
2020-11-20 | QUALITY ASSUR ENG GAX 21C5*804 | DF |  | 0 | 3630 | 3630 | 0 |  |  | 6873
2020-11-20 | QUALITY ASSURANCE ENG GAX 21C5*805 | DF |  | 0 | 2329.8 | 0 | 0 |  | 2070179 | 6873
2020-11-20 | QUALITY ASSURANCE ENG GAX 21C5*806 | DF |  | 0 | 3903.01 | 0 | 0 |  | 2070179 | 6873
2020-11-23 | CR 21M2*044 RE 21C3*053 | N/A |  | 0 |  | 0 | 0 | 806097.25
2020-10-23 | CR 21M2*035 RE 21C3*019 | N/A |  | 0 |  | 0 | 0 | 1029929
2020-11-19 | WC3 GAX 21C5*796 | DF |  | 0 | 110 | 110 | 0 |  |  | 6861
2020-12-14 | RE 21C3*119 BILL $9,972.81 | N/A |  | 0 |  | 0 | 0 |  |  |  | 9972.81
2020-12-22 | USU GAX 21C7*729 | DF |  | 0 | 77067.82 | 0 | 0 |  | 2075296 | 6824
2021-12-30 | CR 21M2*052 RE 21C3*087 | N/A |  | 0 |  | 0 | 0 | 1856680.38 |  | 4760
2021-01-15 | RE 21C3*152 BILL $77,067.82 | N/A |  | 0 |  | 0 | 0 |  |  |  | 77067.82
2021-01-20 | RALPH L WADSWORTH CO 007 | CO |  | 0 |  | 9278 | 0 |  | 2075038
2021-01-28 | CR 21M2*060 RE 21C3*119 | N/A |  | 0 |  | 0 | 0 | 9972.81 |  | 4760
2021-02-10 | RALPH L WADSWORTH GAX 21C7*970 | DF |  | 0 | 619243 | 0 | 0 |  | 2075038 | 6811
2021-02-11 | RALPH L WADSWORTH GAX 21C8*446 | DF |  | 0 | 132999 | 0 | 0 |  | 2075038 | 6811
2021-02-11 | ZIONS/RALPH L WADSWORTH RTNG GAX 21C8*447 | DF |  | 0 | 7000 | 0 | 0 |  | 2075038 | 6811
2021-02-11 | RALPH L WADSWORTH GAX 21C8*448 | DF |  |  | 34675 |  |  |  | 2075038 | 6811
2021-02-11 | ZIONS/RALPH L WADSWORTH RTNG GAX 21C8*449 | DF |  | 0 | 1825 | 0 | 0 |  | 2075038 | 6811
2021-02-22 | USU GAX 21C7*1001 | DF |  | 0 | 444.74 | 0 | 0 |  | 2075296 | 6824
2021-02-26 | CR 21M2*067 RE 21C3*152 | N/A |  | 0 |  | 0 | 0 | 77067.82 |  | 4760
2021-03-16 | RE 21C3*228 BILL $796,186.74 | N/A |  | 0 |  | 0 | 0 |  |  |  | 796186.74
2021-03-16 | RALPH L WADSWORTH GAX 21C8*542 | DF |  | 0 | 9278 | 0 | 0 |  | 2075038 | 6811
2021-03-18 | USU GAX 21C5*1762 | DF |  | 0 | 115609.92 | 0 | 0 |  | 2075296 | 6824
2021-04-16 | RE 21C3*264 BILL $124,887.92 MODIFIED TO $0.00 per Dave | DF |  | 0 |  | 0 | 0 |  |  |  | 124887.92
2021-04-16 | IET TRNSF BUDGETED CONTINGENCY TO 21138300 FOR $3M IMPR FUNDS SHARE | DF | -189681 | -189681 |  | 0 | -189681 |  |  | 4663
2021-04-16 | IET TRNSF FUNDS FROM CONTG RESERVE21138300 FOR CO 008 | DF | 18895 | 18895 |  | 0 | 18895 |  |  | 4664
2021-04-21 | RLW CONST CO CO 008 | CO |  | 0 |  | 18895 | 0 |  | 2075038
2021-04-28 | CR 21M2*077 RE 21C3*228 | N/A |  | 0 |  | 0 | 0 | 796186.74 |  | 4760
2021-05-24 | UTAH STATE UNIV GAX 21C7*1550 | DF |  | 0 | 298.21 | 0 | 0 |  | 2075296 | 6824 | commitments check to this point
2021-06-11 | RALPH L. WADSWORTH CONST GAX 21C7*1646 | NP |  | 0 | 76755 | 0 | 0 |  | 2075038 | 6811
2021-06-21 | RLW CO 009 | CO |  | 0 |  | 87773 | 0 |  | 2075038
2021-06-22 | RETURN FUNDS TO USU GAX 21C2*004 THROUGH 20029 | N/A |  | 0 |  | 0 | 0 | -2627272.87 |  |  | -2627272.87
2021-06-29 | USU GAX 21C5*2398 | NP |  | 0 | 5452.55 | 0 | 0 |  | 2075296 | 6824
13/21 | RE 21C3*368 BILL $5,452.55 | N/A |  | 0 |  | 0 | 0 |  |  |  | 5452.55
13/21 | CR 21M2- RE 21C3*264 | N/A | [5 empty] | 124887.92
13/21 | RETURN FUNDS TO USU GAX 21C2*006 | N/A | [5 empty] | -124887.92 |  |  | -124887.92
13/21 | QUAL ASSUR ENG GAX 21C9*858 | NP |  | 0 | 1078 | 0 | 0 |  | 2070179 | 6873
13/21 | QUALIY ASSUR ENG GAX 21C9*857 | NP |  | 0 | 1137.4 | 0 | 0 |  | 2070179 | 6873
13/21 | QUALIY ASSUR ENG GAX 21C9*859 | NP |  | 0 | 792 | 0 | 0 |  | 2070179 | 6873
13/21 | QUALIY ASSUR ENG GAX 21C9*860 | NP |  |  | 939.4 | 0 |  |  | 2070179 | 6873
13/21 | QUALIY ASSUR ENG GAX 21C9*861 | NP |  | 0 | 939.4 | 0 | 0 |  | 2070179 | 6873
13/21 | QUALIY ASSUR ENG GAX 21C9*862 | NP |  | 0 | 853.6 | 0 | 0 |  | 2070179 | 6873
13/21 | QUALIY ASSUR ENG GAX 21C9*863 | NP |  | 0 | 165 | 0 | 0 |  | 2070179 | 6873
13/21 | USU CONTROLLER'S OFFC GAX 21C5*2507 | NP |  | 0 | 767.29 | 0 | 0 |  | 2075296 | 6824
13/21 | RE 21C3*401 BILL $6,672.09 | N/A |  | 0 |  | 0 | 0 |  |  |  | 6672.09
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'22
2021-08-12 | CR 22M2*010 RE 21C3*401 | N/A |  | 0 |  | 0 | 0 | 6672.09 |  | 4760
2021-08-12 | CR 22M2*010 RE 21C3*368 | N/A |  | 0 |  | 0 | 0 | 5452.55 |  | 4760
2021-09-01 | USU CONTROLLERS OFFC GAX 22C7*087 | DF |  | 0 | 568.24 | 0 | 0 |  | 2075296
2021-09-14 | RE 22C3*19 BILL $568.24 | N/A |  | 0 |  | 0 | 0 |  |  |  | 568.24
2021-10-25 | CR 22M2*027 RE 22C3*019 | N/A |  | 0 |  | 0 | 0 | 568.24 |  | 4760
2021-11-03 | USU GAX FC202111031131 | DF |  | 0 | 2763.58 | 0 | 0 |  | 2075296 | 6824
2021-12-20 | RE 22C3*112 BILL $2,763.58 | N/A |  | 0 |  | 0 | 0 |  |  |  | 2763.58
2021-12-20 | USU GAX FC202112202033 | DF |  | 0 | 7747.82 | 0 | 0 |  | 2075296 | 6824
2022-01-18 | RE 22C3*148 BILL $7,747.82 | N/A |  | 0 |  | 0 | 0 |  |  |  | 7747.82
2022-01-31 | USU GAX FC202201312797 | DF |  | 0 | 700.89 | 0 | 0 |  | 2075296 | 6824
2022-01-27 | CR 22M5*003 RE 22C3*112 | N/A |  | 0 |  | 0 | 0 | 2763.58 |  | 4760
2022-02-18 | RE 22C3*177 BILL $700.89 | N/A |  | 0 |  | 0 | 0 |  |  |  | 700.89
2022-02-25 | CR 22M5*013 RE 22C3*148 | N/A |  | 0 |  | 0 | 0 | 7747.82 |  | 4760
2022-03-29 | RALPH WADSWORTH GAX FC202203293896 | DF |  | 0 | 92772 | 0 | 0 |  | 2075038 | 6811
2022-03-24 | CR 22M5*025 RE 22C3*177 | N/A |  | 0 |  | 0 | 0 | 700.89 |  | 4760
2022-04-11 | RE 22C3*241 BILL $92,772.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 92772
2022-05-20 | CR 22M5*056 RE 22C3*241 | N/A |  | 0 |  | 0 | 0 | 92772 |  | 4760
2022-06-23 | USU GAX FC202206236125 | NP |  | 0 | 384 | 0 | 0 |  | 2075296 | 6824
13/22 | RE 22C3*346 BILL $384.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 384
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'23 |  |  |  | 0 |  | 0 | 0
2022-07-29 | CR 23M5*009 RE 22C3*346 | N/A |  | 0 |  | 0 | 0 | 384 |  | 4760
2022-09-15 | RALPH WADSWORTH CO 010 | CO |  | 0 |  | 41195 | 0 |  | 2075038
2022-10-04 | QUALITY ASSUR ENG AMD 001 | CO |  | 0 |  | -27956.79 | 0 |  | 2070179
2023-03-14 | RALPH WADSWORTH GAX FC2023031416182 | CB |  | 0 | 41195 | 0 | 0 |  | 2075038 | 6811
2023-04-12 | RE 23C3*240 BILL $41,195.00 | N/A |  | 0 |  | 0 | 0 |  |  |  | 41195
2023-05-18 | CR 23M5*130 RE 23C3*240 | N/A |  | 0 |  | 0 | 0 | 41195 |  | 4760
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'24 |  |  |  | 0 |  | 0 | 0
2024-02-05 | USU CO 001 | CO |  | 0 |  | -49421.31 | 0 |  | 2075296
13/24 | DECREASE USU EST REV |  | -146780.22 | -146780.22 |  | 0 | -146780.22 |  |  | 4760
|  |  |  | 0 |  | 0 | 0
| PROJECT CLOSED |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
BILL USU ALL COSTS LESS $3M FROM STATE CAP IMPR FUNDS
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 20011770
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency