## PROJECT
RESERVES:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR
| FUNDING |  | EFFY2024 |  |  |  | DESIGN
| STATE RISK NUMBER |  | 00087 |  |  |  | INSPECTION
| PROJECT TITLE |  | USU SER COMPUTER SCIENCE RENOVATION |  |  |  | INSURANCE
| PROJECT # |  | 24135770 | OPEN |  |  | CONTINGENCY/LEGAL
| CODING BLOCK |  | 3000-300-3347-FWBAA-24135770 |  |  | 1028686.14 | TOTAL | 0
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
YR | CURRENT TOTALS |  | 4200000 | 1854797.49 | 2345202.51 | 3373888.65 | 826111.35 | 0 |  |  |  | 0
0
|  |  |  | 0 |  | 0 | 0
FY'23 |  |  |  | 0 |  | 0 | 0
13/23 | CRSA GAX FC2023071422405 |  |  | 0 | 36118.5 | 36118.5 | 0 |  |  | 6861
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'24 |  |  |  | 0 |  | 0 | 0
2023-07-05 | UTAH STATE UNIVERSITY CONTROLLERS OFFICE | N/A |  | 0 |  | 829691.55 | 0 |  | 2475005
2023-07-05 | CRSA INC - CONTRACT | N/A |  | 0 |  | 240790 | 0 |  | 2470003
2023-09-13 | CRSA GAX FC2023091324900 | DF |  | 0 | 48158 | 0 | 0 |  | 2470003 | 6861
2023-10-31 | USU GAX FC2023103126972 | DF |  | 0 | 131003 | 0 | 0 |  | 2475005 | 6854
2023-11-01 | CRSA GAX FC2023110127008 | DF |  | 0 | 96316 | 0 | 0 |  | 2470003 | 6861
2023-11-17 | USU GAX FC2023111727866 | DF |  | 0 | 1438.82 | 0 | 0 |  | 2475005 | 6854
2023-12-20 | WC3 PLAN REVIEW SVCS NOV 2023 1ST REVIEW GAX 24C5*127 | DF |  | 0 | 125 | 125 | 0 |  |  | 6861
2023-12-20 | WC3 PLAN REVIEW SVCS NOV 2023 2ND REVIEW GAX 24C5*127 | DF |  | 0 | 125 | 125 | 0 |  |  | 6861
2024-01-03 | BUDGETED CD CONTINGENCY - 24135770 | DF | -156265 | -156265 |  | 0 | -156265 |  |  | 4663
2024-01-02 | UT ST FIRE MARSHAL GAX 24C5*155 | DF |  | 0 | 321.2 | 321.2 | 0 |  |  | 6861
2024-01-17 | WC3 PLAN REVIEW GAX 24C5*168 | DF |  | 0 | 125 | 125 | 0 |  |  | 6861
2024-01-24 | USU GAX FC2024012430839 | DF |  | 0 | 14173.97 | 0 | 0 |  | 2475005 | 6854
2024-02-05 | TRNSF FY24 CAP DEV FUNDS TO 24135770 FROM 24376300 SB 2 Item 44 | DF | 4200000 | 4200000 |  | 0 | 4200000 |  |  | 4667 |  | ADDED PER FP07 REV REPORT
2024-02-13 | USU GAX FC2024021331821 | DF |  | 0 | 6081.07 | 0 | 0 |  | 2475005 | 6854
2024-03-01 | CRSA GAX FC2024030132678 | DF |  | 0 | 12039.5 | 0 | 0 |  | 2470003 | 6861
2024-03-06 | SUNRISE ENGINEERING INC - CONTRACT | N/A |  | 0 |  | 20880.37 | 0 |  | 2470359
2024-02-28 | RAYMOND CONSTRUCTION CO - CONTRACT | N/A |  | 0 |  | 2088037 | 0 |  | 2475302
2024-04-03 | CRSA GAX FC2024040334144 | DF |  | 0 | 2407.9 | 0 | 0 |  | 2470003 | 6861
2024-04-11 | RAYMOND CONST GAX FC2024041134649 | DF |  | 0 | 104063.85 | 0 | 0 |  | 2475302 | 6811
2024-04-11 | ZIONS/RAYMOND RTNG GAX FC2024041134650 | DF |  | 0 | 5477.05 | 0 | 0 |  | 2475302 | 6811
2024-04-17 | USU GAX FC2024041734924 | DF |  | 0 | 8783.62 | 0 | 0 |  | 2475005 | 6854
2024-04-26 | ITA 24*121 COFC INS | DF |  | 0 | 2088.84 | 2088.84 | 0 |  |  | 6872
2024-05-07 | CRSA GAX FC2024050735812 | DF |  | 0 | 4815.8 | 0 | 0 |  | 2470003 | 6861
2024-05-17 | USU GAX FC2024051736381 | DF |  | 0 | 694 | 0 | 0 |  | 2475005 | 6854
2024-06-03 | CRSA GAX FC2024060337082 |  |  | 0 | 4815.8 | 0 | 0 |  | 2470003 | 6861
2024-06-13 | RAYMOND CONST GAX FC2024061337902 |  |  | 0 | 576474.25 | 0 | 0 |  | 2475302 | 6811
2024-06-13 | ZIONS/RAYMOND RTNG GAX FC2024061337902 |  |  | 0 | 30340.75 | 0 | 0 |  | 2475302 | 6811
2024-06-24 | RAYMOND CONST CO 001 | CO |  | 0 |  | 21058.45 | 0 |  | 2475302
2024-06-25 | RAYMOND CONST GAX FC2024062538517 |  |  | 0 | 241775.52 | 0 | 0 |  | 2475302 | 6811
2024-06-25 | ZIONS/RAYMOND RTNG GAX FC2024062538518 |  |  | 0 | 12725.03 | 0 | 0 |  | 2475302 | 6811
13/24 | CRSA GAX FC2024070239179 |  |  | 0 | 4815.8 | 0 | 0 |  | 2470003 | 6861
13/24 | USU GAX FC2024071640030 |  |  | 0 | 295 | 0 | 0 |  | 2470005 | 6854
13/24 | RAYMOND CONST GAX FC2024071640032 |  |  | 0 | 222167.9 | 0 | 0 |  | 2475302 | 6811
13/24 | ZIONS/RAYMOND RTNG GAX FC2024071640033 |  |  | 0 | 11693.05 | 0 | 0 |  | 2485302 | 6811
13/24 | SUNRISE ENG GAX FC2024072240274 |  |  | 0 | 442.4 | 0 | 0 |  | 2470359 | 6873
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'25 |  |  |  | 0 |  | 0 | 0
2024-08-29 | RAYMOND CONST GAX FC2024082941715 | DF |  | 0 | 104042.86 | 0 | 0 |  | 2475302 | 6811
2024-08-29 | ZIONS/RAYMOND RTNG GAX FC2024082941716 | DF |  | 0 | 5475.94 | 0 | 0 |  | 2475302 | 6811
2024-08-16 | USU GAX FC2024081641192 | DF |  | 0 | 793 | 0 | 0 |  | 2475005 | 6811
2024-08-08 | CRSA GAX FC2024080840843 | DF |  | 0 | 4815.8 | 0 | 0 |  | 2470003 | 6861
2024-09-05 | CRSA GAX FC2024090542017 | DF |  | 0 | 4815.8 | 0 | 0 |  | 2470003 | 6861
2024-08-06 | IDT 25C3*006 XFER LEGAL FEES TO 21257300 | DF |  | 0 | 1563 | 1563 | 0 |  |  | 6870
2024-09-04 | SUNRISE ENG GAX FC2024090441921 | DF |  | 0 | 221.2 | 0 | 0 |  | 2470359 | 6873
2024-09-11 | USU CO 001 | CO |  | 0 |  | 36798.92 | 0 |  | 2475005
2024-09-17 | RAYMOND CONST GAX FC2024091742631 | DF |  | 0 | 191440.06 | 0 | 0 |  | 2475302 | 6811
2024-09-17 | ZIONS/RAYMOND RTNG GAX FC2024091742632 | DF |  | 0 | 10075.79 | 0 | 0 |  | 2475302 | 6811
2024-10-02 | WC3 PLAN REVIEW GAX 25C5*041 | DF |  | 0 | 125 | 125 | 0 |  |  | 6873
2024-10-15 | CRSA GAX FC2024101543959 | DF |  | 0 | 4815.8 | 0 | 0 |  | 2470003 | 6861
2024-10-15 | RAYMOND CONST GAX FC2024101543974 | DF |  | 0 | 174838.57 | 0 | 0 |  | 2475302 | 6811
2024-10-15 | ZIONS/RAYMOND RTNG GAX FC2024101543975 | DF |  | 0 | 9202.03 | 0 | 0 |  | 2475302 | 6811
2024-10-22 | USU GAX FC2024102244354 | DF |  | 0 | 3149 | 0 | 0 |  | 2475005 | 6854
2024-11-01 | TRNSF TO 24135770 FROM 21139300 RETURN PROJ CONTINGENCY | DF | 156265 | 156265 |  | 0 | 156265
2024-11-06 | CRSA GAX FC2024110645013 | DF |  | 0 | 4815.8 | 0 | 0 |  | 2470003 | 6861
2024-11-07 | SUNRISE ENG GAX FC2024110745136 | DF |  | 0 | 221.2 | 0 | 0 |  | 2470359 | 6873
2024-11-13 | USU GAX FC2024111345346 | DF |  | 0 | 827.99 | 0 | 0 |  | 2475005 | 6854
2024-11-26 | RAYMOND CONST GAX FC2024112645977 | DF |  | 0 | 222890 | 0 | 0 |  | 2475302 | 6811
2024-11-26 | ZIONS/RAYMOND RTNG GAX FC2024112645978 | DF |  | 0 | 11731.05 | 0 | 0 |  | 2475302 | 6811
2024-12-05 | CRSA GAX FC2024120546354 |  |  | 0 | 4815.8 | 0 | 0 |  | 2470003 | 6861
2024-08-14 | RAYMOND CONST CO 002 POSTED 12.9.24 | CO |  | 0 |  | 51783.5 | 0 |  | 2475302
2024-12-09 | RAYMOND CONST CO 003 | CO |  | 0 |  | 44257.32 | 0 |  | 2475302
2024-12-18 | USU GAX FC2024121846919 |  |  | 0 | 4625.2 | 0 | 0 |  | 2475005 | 6854
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 24135770
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency