## PROJECT
[7 empty] | RESERVES: |  |  |  | FUNDING
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR |  |  |  | STATE CD | 28000000 | 71%
| FUNDING |  | GFFY2024, OTHER |  |  |  | DESIGN |  |  |  | STATE CI | 1934037.71 | 4.904%
| STATE RISK NUMBER |  | 00000 |  |  |  | INSPECTION |  |  |  | UTU | 9500000 | 24.09%
| PROJECT TITLE |  | UTU COX PERFORMING ARTS CENTER |  |  |  | INSURANCE |  |  |  |  | 39434037.71
| PROJECT # |  | 24275640 | OPEN |  |  | CONTINGENCY/LEGAL
| CODING BLOCK |  | 3000-300-3347-FWBAA-24275640 |  |  | 599173.25 | TOTAL | 0
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
8990121.3342
YR | CURRENT TOTALS |  | 39434037.71 | 2116481.53 | 37317556.18 | 37916729.43 | 1517308.28 | 0 |  |  | 0 | 0
[11 empty] | 8990121.3342 | 0
|  |  |  | 0 |  | 0 | 0
FY'24 |  |  |  | 0 |  | 0 | 0
2023-10-04 | LANDMARK TEST & ENG GAX FC2023100425782 | DF |  | 0 | 10200 | 10200 | 0 |  |  | 6861
2023-10-04 | TERRACON CONSULTANTS GAX FC2023100425812 | DF |  | 0 | 6610 | 6610 | 0 |  |  | 6861
2023-09-29 | SPARANO + MOONEY ARCHITECTURE - CONTRACT | N/A |  | 0 |  | 2966189 | 0 |  | 2470088
2023-11-27 | SPARANO + MOONEY ARCHI GAX FC2023112728158 | DF |  | 0 | 231647.65 | 0 | 0 |  | 2470088 | 6861
2023-12-14 | LAYTON CONSTRUCTION COMPANY LLC - CONTRACT | N/A |  | 0 |  | 75000 | 0 |  | 2475229
2024-12-28 | DIXIE STATE UNIVERSITY ACCOUNTS RECEIVABLE dba UTAH - CONTRACT | N/A |  | 0 |  | 2325323 | 0 |  | 2475248
2024-01-03 | BUDGETED CD CONTINGENCY - 24275640 | DF | -1158626.33 | -1158626.33 |  | 0 | -1158626.33 |  |  | 4663
2024-01-11 | SPARANO + MOONEY ARCHI GAX FC2024011130255 | DF |  | 0 | 404683.92 | 0 | 0 |  | 2470088 | 6861
2024-01-18 | PBIET150241234608170641 CAFÉ ZUPAS | DF |  | 0 | 116.87 | 116.87 | 0 |  |  | 6879
2024-01-18 | ALPHA ENG GAX FC2024011830574 | DF |  | 0 | 5320 | 5320 | 0 |  |  | 6861
2024-01-22 | VAN BOERUM & FRANK ASSOC INC VBFA - CONTRACT | N/A |  | 0 |  | 25650 | 0 |  | 2470277
2024-02-05 | TRNSF FY24 CAP DEV FUNDS TO 24275640FROM 24376300 SB 2 Item 44 | DF | 28000000 | 28000000 |  | 0 | 28000000 |  |  | 4667 |  | ADDED PER FP07 REV REPORT
2024-02-29 | EST REV UTU - 24275640 | DF | 7000000 | 7000000 |  | 0 | 7000000 |  |  | 4760
2024-02-16 | SPARANO + MOONEY GAX FC2024021632038 | DF |  | 0 | 545838.34 | 0 | 0 |  | 2470088 | 6861
2024-02-29 | CMB CONSULTANTS LC dba UNVC - CONTRACT | N/A |  | 0 |  | 146500 | 0 |  | 2470354
2024-03-04 | ITA 24*077 COFC INS | DF |  | 0 | 25700 | 25700 | 0 |  |  | 6872
2024-03-04 | ITA 24*076 COX PERFORMING ARTS | DF |  | 0 | 200000 | 200000 | 0 |  |  | 6284
2024-05-09 | CMB CONSULTANTS GAX FC2024050935951 | DF |  | 0 | 1341.21 | 0 | 0 |  | 2470354 | 6849
2024-05-09 | VBFA GAX FC2024050935952 | DF |  | 0 | 12825 | 0 | 0 |  | 2470277 | 6849
2024-05-15 | SPARANO + MOONEY ARCHI GAX FC2024051536177 | DF |  | 0 | 550510.62 | 0 | 0 |  | 2470088 | 6861
2024-06-11 | CMB CONSULTATNS GAX FC2024061137689 | HH |  | 0 | 2941.98 | 0 | 0 |  | 2470354 | 6849
13/24 | CMB CONSULTANTS GAX FC2024071539919 | HH |  | 0 | 442.55 | 0 | 0 |  | 2470354 | 6139
13/24 | LAYTON CONST GAX FC2024071539961 | HH |  | 0 | 65625 | 0 | 0 |  | 2475229 | 6813
13/24 | IDT30024C30000412 DFCM MGMT FEES TO 24425300 FROM 24275640 | HH | -109445.8 | -109445.8 |  | 0 | -109445.8 |  |  | 4672
|  |  |  | 0 |  | 0 | 0
FY'25 |  |  |  | 0 |  | 0 | 0
2024-07-31 | SPARANO + MOONEY GAX F2024073140544 | DF |  | 0 | 477727.5 | 0 | 0 |  | 2470088 | 6861
2024-08-23 | Trfr to 24275640 from 25081640 MOU CANCELLED PER UTU | DF | 930800.71 | 930800.71 |  | 0 | 930800.71 |  |  | 4667
2024-08-19 | LAYTON CONST GAX FC2024081941271 | DF |  | 0 | 7031 | 0 | 0 |  | 2475229 | 6813
2024-08-19 | LAYTON CONST CO 001 | CO |  | 0 |  | 406199 | 0 |  | 2475229
2024-08-26 | C MB CONSULTANTS LC dba UNVC - CONTRACT | N/A |  | 0 |  | 35500 | 0 |  | 2570047
2024-08-27 | SHUMS CODA ASSOCIATES - CONTRACT | N/A |  | 0 |  | 145960 | 0 |  | 2570035
2024-08-30 | UT ST FIRE MARSHAL GAX 25C5*008 | DF |  | 0 | 1824.83 | 1824.83 | 0 |  |  | 6861
2024-08-30 | WC3 PLAN REVIEW GAX 25C5*024 | DF |  | 0 | 1375 | 1375 | 0 |  |  | 6861
2024-08-06 | IDT 25C3*006 XFER LEGAL FEES TO 21257300 | DF |  | 0 | 13253 | 13253 | 0 |  |  | 6870
2024-09-11 | CMB CONSULTANTS GAX FC2024091142256 | DF |  | 0 | 6544.25 | 0 | 0 |  | 2570047 | 6849
2024-09-12 | LAYTON CONST GAX FC2024091242429 | DF |  | 0 | 199357.02 | 0 | 0 |  | 2475229 | 6813
2024-09-12 | ZIONS/LAYTON RTNG GAX FC2024091242430 | DF |  | 0 | 10492.48 | 0 | 0 |  | 2475229 | 6813
2024-09-27 | DSU CO 001 | CO |  | 0 |  | -564179 | 0 |  | 2475248
2024-10-09 | LAYTON CONST GAX FC2024100943795 | DF |  | 0 | 2226.8 | 0 | 0 |  | 2475229 | 6813
2024-10-09 | ZIONS/LAYTON RTNG GAX FC2024100943796 | DF |  | 0 | 117.2 | 0 | 0 |  | 2475229 | 6813
2024-10-10 | CMB CONSULTANTS GAX FC2024101043824 | DF |  | 0 | 1245.19 | 0 | 0 |  | 2470354 | 6849
2024-10-18 | Trfr to 24275640 from FY25 GFFY Capital Improvement Funds | DF | 1003237 | 1003237 |  | 0 | 1003237 |  |  | 4667
2024-09-27 | LAYTON CONST CO 002 | CO |  | 0 |  | 28162328 | 0 |  | 2475229
2024-10-11 | SPARANO + MOONEY AMD 001 | CO |  | 0 |  | 39185 | 0 |  | 2470088
2024-10-22 | MAGER CONSORTIUM LLC - CONTRACT | N/A |  | 0 |  | 75000 | 0 |  | 2570101
2024-11-01 | TRNSF TO 24275640 FROM 21139300 RETURN PROJ CONTINGENCY | DF | 1158626.33 | 1158626.33 |  | 0 | 1158626.33 |  |  | 4664
2024-11-07 | LAYTON CONST GAX FC2024110745154 | DF |  | 0 | 1247435.81 | 0 | 0 |  | 2475229 | 6813
2024-11-07 | ZIONS/LAYTON RTNG GAX FC2024110745155 | DF |  | 0 | 65654.52 | 0 | 0 |  | 2475229 | 6813
2024-11-07 | SPARANO + MOONEY GAX FC2024110745115 | DF |  | 0 | 207123.96 | 0 | 0 |  | 2470088 | 6861
2024-11-08 | CMB CONSULTANTS GAX FC2024110845187 | DF |  | 0 | 1846.17 | 0 | 0 |  | 2570047 | 6849
2024-11-12 | CMB CONSULTANTS GAX FC2024111245265 | DF |  | 0 | 1646.18 | 0 | 0 |  | 2470354 | 6849
2024-12-04 | MAGER CONSORTIUM GAX FC2024120446263 | DF |  | 0 | 20000 | 0 | 0 |  | 2570101 | 6864
2024-12-09 | LAYTON CONST GAX FC2024120946480 | EH |  | 0 | 1260167.43 | 0 | 0 |  | 2475229 | 6813
2024-12-09 | ZIONS/LAYTON RTNG GAX FC2024120946481 | EH |  | 0 | 66324.6 | 0 | 0 |  | 2475229 | 6813
2024-12-11 | SHUMS CODA GAX FC2024121146638 | EH |  | 0 | 804.3 | 0 | 0 |  | 2570035 | 6873
2024-12-12 | CMB CONSULTANTS GAX FC2024121246685 | EH |  | 0 | 4547.06 | 0 | 0 |  | 2470354 | 6849
2024-12-09 | WENGER CORPORATION - CONTRACT | N/A |  | 0 |  | 1470791 | 0 |  | 2575249
2024-12-20 | SPARANO + MOONEY GAX FC2024122047082 | EH |  | 0 | 28415.11 | 0 | 0 |  | 2470088 | 6861
2024-12-31 | WC3 PLAN REVIEW GAX 25C5*082 | EH |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-01-03 | MAGER CONSORTIUM GAX FC2025010347553 | EH |  | 0 | 20000 | 0 | 0 |  | 2570101 | 6864
2025-01-07 | STAGERIGHT CORPORATION - CONTRACT | N/A |  | 0 |  | 98765 | 0 |  | 2575266
2024-12-13 | IDT 25C3*086 MGMT FEES TO 24425300 | EH |  | 0 | 115443.55 | 115443.55 | 0 |  |  | 6865
2024-12-13 | IDT 25C3*093 LEGAL FEES TO 21257300 | EH |  | 0 | 1853.54 | 1853.54 | 0 |  |  | 6870 |  |  | ADDED PER FP06 EXP REPORT
2025-01-10 | CMB CONSULTANTS GAX300FC2025011047897 | EH |  | 0 | 1547.97 | 0 | 0 |  | 2470354 | 6849
2025-01-14 | SHUMS CODA GAXFC2025011347992 | EH |  | 0 | 8653.2 | 0 | 0 |  | 2570035 | 6873
2025-01-15 | LAYTON CONST. GAXFC2025011548150 | EH |  | 0 | 2445048.19 | 0 | 0 |  | 2475229 | 6813
2025-01-15 | ZIONS/LAYTON RTNG. GAXFC2025011548151 | EH |  | 0 | 128686.75 | 0 | 0 |  | 2475229 | 6813
2025-01-24 | SPARANO+MOONEY ARCHI GAX300FC2025012448610 | EH |  | 0 | 27087.33 | 0 | 0 |  | 2470088 | 6861
2025-01-28 | SHUMS CODA GAX300FC2025012848749 | EH |  | 0 | 11741.1 | 0 | 0 |  | 2570035 | 6873
2025-02-04 | ITA30025*56 DFCM COFC DEC 2024 | HH |  | 0 | 3162.2 | 3162.2 | 0 |  |  | 6872
2025-02-25 | LAYTON CONST. GAXFC2025021049386 | HH |  | 0 | 1881789.2 | 0 | 0 |  | 2475229 | 6813
2025-02-25 | ZIONS/LAYTON CONST. RTNG. GAXFC2025021049387 | HH |  | 0 | 99041.54 | 0 | 0 |  | 2475229 | 6813
2025-02-11 | CMB CONSULT GAX300FC2025021149482 | HH |  | 0 | 2748.89 | 0 | 0 |  | 2470354 | 6849
2025-02-11 | MAGER CONSRTM GAX300FC2025021149483 | HH |  | 0 | 20000 | 0 | 0 |  | 2570101 | 6864
2025-02-14 | UTAH STATE FIRE MARSHAL'S OFFICE GAX30025C5000101 | HH |  | 0 | 1824.83 | 1824.83 | 0 |  |  | 6873
2025-02-24 | WC3 GAX30025C5*111 | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-02-24 | ITA30025*061 | HH |  | 0 | 212.34 | 212.34 | 0 |  |  | 6872
2025-02-25 | SPARANO + MOONEY ARCH GAX300FC2025022550030 | HH |  | 0 | 155239.91 | 0 | 0 |  | 2470088 | 6861
2025-03-05 | SHUMS CODA GAX300FC2025030550425 | HH |  | 0 | 6526.4 | 0 | 0 |  | 2570035 | 6873
2025-03-10 | CMB Consultants LC GAX300FC2025031050737 | HH |  | 0 | 4249.82 | 0 | 0 |  | 2470354 | 6849
2025-03-10 | CMB Consultants LC GAX300FC2025031050738 | HH |  | 0 | 3149.81 | 0 | 0 |  | 2570047 | 6849
2025-03-10 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025031050770 | HH |  | 0 | 1933496.9 | 0 | 0 |  | 2475229 | 6813
2025-03-10 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025031050771 | HH |  | 0 | 101763 | 0 | 0 |  | 2475229 | 6813
2025-03-14 | UTAH STATE FIRE MARSHAL'S OFFICE GAX30025C5000120 | HH |  | 0 | 1824.83 | 1824.83 | 0 |  |  | 6873
2025-03-20 | SPARANO + MOONEY ARCHITECTURE GAX300FC2025032051258 | HH |  | 0 | 29973.64 | 0 | 0 |  | 2470088 | 6861
2025-03-31 | WEST COAST CODE CONSULTANTS INC GAX30025C5000123 | HH |  | 0 | 375 | 375 | 0
2024-12-27 | LAYTON CONST CO 003 | CO |  | 0 |  | 132581 | 0 |  | 2475229
2025-01-22 | LAYTON CONST CO 004 | CO |  | 0 |  | 324800 | 0 |  | 2475229
2025-02-26 | LAYTON CONST CO 005 | CO |  | 0 |  | 61416 | 0 |  | 2475229
2024-12-27 | WENGER COOP CO 001 | CO |  | 0 |  | 215790.98 | 0 |  | 2575249
2025-01-21 | SPARANO + MOONEY AMD 002 | CO |  | 0 |  | 151706 | 0 |  | 2470088
2025-04-15 | CMB Consultants LC GAX300FC2025041552288 | HH |  | 0 | 5250.64 | 0 | 0 |  | 2470354 | 6849
2025-04-18 | Wenger Corporation GAX300FC2025041852536 | HH |  | 0 | 14250 | 0 | 0 |  | 2575249 | 6813
2025-04-18 | Wenger Corporation GAX300FC2025041852537 | HH |  | 0 | 750 | 0 | 0 |  | 2575249 | 6813
2025-04-22 | MAGER CONSORTIUM, LLC GAX300FC2025042252640 | HH |  | 0 | 15000 | 0 | 0 |  | 2570101 | 6864
2025-04-23 | SPARANO + MOONEY ARCHITECTURE GAX300FC2025042352732 | HH |  | 0 | 29603.34 | 0 | 0 |  | 2470088 | 6861
2025-04-07 | LAYTON CONST CO 006 | CO |  | 0 |  | 140012 | 0 |  | 2475229
2025-04-30 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025043053056 | HH |  | 0 | 1722658 | 0 | 0 |  | 2475229 | 6813
2025-04-30 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025043053057 | HH |  | 0 | 90666.21 | 0 | 0 |  | 2475229 | 6813
2025-05-08 | SHUMS CODA ASSOCIATES INC GAX300FC2025050853453 | HH |  | 0 | 3399.8 | 0 | 0 |  | 2570035 | 6873
2025-05-16 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025051653947 | HH |  | 0 | 1600200.64 | 0 | 0 |  | 2475229 | 6813
2025-05-16 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025051653948 | HH |  | 0 | 84221.09 | 0 | 0 |  | 2475229 | 6813
2025-05-23 | CMB Consultants LC GAX300FC2025052254122 CONTRACT 2470354-UTU COX PERFORMING ARTS CENTER REMODEL | HH |  | 0 | 3951.52 | 0 | 0 |  | 2470354 | 6849
2025-05-23 | SPARANO + MOONEY ARCHITECTURE GAX300FC2025052254125 CONTRACT 2470088 - UTU COX AUDITORIUM ADDITION & REMODEL | HH |  | 0 | 28827.99 | 0 | 0 |  | 2470088 | 6861
2025-05-27 | WEST COAST CODE CONSULTANTS INC GAX30025C5000142 Plan Review Services 04/07/2025-1ST REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-05-28 | Utah Tech University GAX300FC2025052754309 CONTRACT 2475248-UTU COX AUDITORIUM REMODEL AND ADDITION | HH |  | 0 | 6724.56 | 0 | 0 |  | 2475248 | 6188
2025-05-28 | MAGER CONSORTIUM, LLC GAX300FC2025052754290 CONTRACT 2570101-UTU COX PERFORMING ARTS CENTER CBE | HH |  | 0 | 1951.06 | 0 | 0 |  | 2570101 | 6864
2025-05-09 07:02 | MAGER CONSORTIUM AMD 001 | CO |  | 0 |  | 1951.06 | 0 |  | 2570101
2025-06-04 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025060354670 CONTRACT 2475229-PAY APP #12-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 1562368.13 | 0 | 0 |  | 2475229 | 6813
2025-06-04 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025060354671 CONTRACT 2475229-PAY APP #12-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 82229.9 | 0 | 0 |  | 2475229 | 6813
2025-06-10 | CMB Consultants LC GAX300FC2025060954945 CONTRACT 2470354-UTU COX PERFORMING ARTS CENTER REMODEL | HH |  | 0 | 2852.41 | 0 | 0 |  | 2470354 | 6849
2025-06-19 | SHUMS CODA ASSOCIATES INC GAX300FC2025061855425 CONTRACT 2570035-UTU COX AUDITORIUM REMODEL AND ADDITION | HH |  | 0 | 7425.68 | 0 | 0 |  | 2570035 | 6873
2025-06-24 09:54 | LAYTON CONST CO 007 | CO |  | 0 |  | 150378 | 0 |  | 2475229
13/25 | CMB Consultants LC GAX300FC2025070256259 CONTRACT 2470354-UTU COX PERFORMING ARTS CENTER REMODEL | HH |  | 0 | 2253.2 | 0 | 0 |  | 2470354 | 6849
13/25 | CMB Consultants LC GAX300FC2025070256260 CONTRACT 2570047-COX AUDITORIUM REMODEL AND ADDIT ENCLOSURE | HH |  | 0 | 1513.19 | 0 | 0 |  | 2570047 | 6849
13/25 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025070256304 CONTRACT 2475229-PAY APP #13-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 1513274.49 | 0 | 0 |  | 2475229 | 6813
13/25 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025070256305 CONTRACT 2475229-PAY APP #13-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 79646.03 | 0 | 0 |  | 2475229 | 6813
13/25 | SPARANO + MOONEY ARCHITECTURE GAX300FC2025070756433 CONTRACT 2470088 - UTU COX AUDITORIUM ADDITION & REMODEL | HH |  | 0 | 29263.94 | 0 | 0 |  | 2470088 | 6861
13/25 | SPARANO + MOONEY ARCHITECTURE GAX300FC2025070756434 CONTRACT 2470088 - UTU COX AUDITORIUM ADDITION & REMODEL | HH |  | 0 | 28861.9 | 0 | 0 |  | 2470088 | 6861
13/25 | Utah Tech University GAX300FC2025070756475 CONTRACT 2475248-UTU COX AUDITORIUM REMODEL AND ADDITION | HH |  | 0 | 12936.42 | 0 | 0 |  | 2475248 | 6188
13/25 | SHUMS CODA ASSOCIATES INC GAX300FC2025071857180 CONTRACT 2570035-UTU COX AUDITORIUM REMODEL AND ADDITION | HH |  | 0 | 2029.53 | 0 | 0 |  | 2570035 | 6873
13/25 | Wenger Corporation GAX300FC2025071857199 CONTRACT 2575249-PAY APP #2-UTU COX AUDITORIUM RMDL/ADDIT | HH |  | 0 | 23750 | 0 | 0 |  | 2575249 | 6813
13/25 | Wenger Corporation GAX300FC2025071857200 CONTRACT 2575249-PAY APP #2-UTU COX AUDITORIUM RMDL/ADDIT | HH |  | 0 | 1250 | 0 | 0 |  | 2575249 | 6813
13/25 | SHUMS CODA ASSOCIATES INC GAX300FC2025072357346 CONTRACT 2570035-UTU COX AUDITORIUM REMODEL AND ADDITION | HH |  | 0 | 6052.3 | 0 | 0 |  | 2570035 | 6873
13/25 | SHUMS CODA ASSOCIATES INC GAX300FC2025072557361 CONTRACT 2570035-UTU COX AUDITORIUM REMODEL AND ADDITION | HH |  | 0 | 3299.23 | 0 | 0 |  | 2570035 | 6873
13/25 | SPARANO + MOONEY AMD 003 | CO |  | 0 |  | 6510 | 0 |  | 2470088
13/25 | UTAH STATE FIRE MARSHAL'S OFFICE GAX30025C5000168 FIRE SPRINKLER PLANS - 25-386 -05-02-2025 | TR |  | 0 | 1824.83 | 1824.83 | 0 |  |  | 6873
13/25 | IDT30024C30000412 DFCM MGMT FEES TO 24425300 FROM 24275640 | TR | 109445.8 | 109445.8 |  | 0 | 109445.8 |  |  | 4672
13/25 | EST UTU REVENUE ESTIMATE- 24275640 COMMITMENT LETTER 8.23.2024 | TR | 2500000 | 2500000 |  | 0 | 2500000 |  |  | 4761
FY'26
2025-08-14 | CMB Consultants LC GAX300FC2025081358108 CONTRACT 2570047-COX AUDITORIUM REMODEL AND ADDIT ENCLOSURE | HH |  | 0 | 1754.02 | 0 | 0 |  | 2570047 | 6849
2025-08-14 | CMB Consultants LC GAX300FC2025081358110 CONTRACT 2470354-UTU COX PERFORMING ARTS CENTER REMODEL | HH |  | 0 | 5054.03 | 0 | 0 |  | 2470354 | 6849
2025-08-21 | SPARANO + MOONEY ARCHITECTURE GAX300FC2025082058323 CONTRACT 2470088 - UTU COX AUDITORIUM ADDITION & REMODEL | HH |  | 0 | 28804.97 | 0 | 0 |  | 2470088 | 6861
2025-08-21 | StageRight Corporation GAX300FC2025082058355 CONTRACT 2575266-PAY APP #1-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 13240 | 0 | 0 |  | 2575266 | 6813
2025-08-21 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025082058356 CONTRACT 2475229-PAY APP #14-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 1544355.18 | 0 | 0 |  | 2475229 | 6813
2025-08-21 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025082058357 CONTRACT 2475229-PAY APP #14-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 81281.85 | 0 | 0 |  | 2475229 | 6813
2025-07-23 | LAYTON CONST CO 008 | CO |  | 0 |  | 120103 | 0 |  | 2475229
2025-09-03 | SHUMS CODA ASSOCIATES INC GAX300FC2025090258855 CONTRACT 2570035-UTU COX AUDITORIUM REMODEL AND ADDITION | HH |  | 0 | 2505.2 | 0 | 0 |  | 2570035 | 6873
2025-09-06 | WEST COAST CODE CONSULTANTS INC GAX30026C5000017 Plan Review Services 07/15/2025-1ST REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-09-22 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025092059654 CONTRACT 2475229-PAY APP #15-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 1516647.82 | 0 | 0 |  | 2475229 | 6813
2025-09-22 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025092059655 CONTRACT 2475229-PAY APP #15-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 79823.57 | 0 | 0 |  | 2475229 | 6813
2025-09-25 | SPARANO + MOONEY ARCHITECTURE GAX300FC2025092459792 CONTRACT 2470088 - UTU COX AUDITORIUM ADDITION & REMODEL | HH |  | 0 | 30399.03 | 0 | 0 |  | 2470088 | 6861
2025-09-25 | CMB Consultants LC GAX300FC2025092459796 CONTRACT 2570047-COX AUDITORIUM REMODEL AND ADDIT ENCLOSURE | HH |  | 0 | 1655.05 | 0 | 0 |  | 2570047 | 6849
2025-09-25 | CMB Consultants LC GAX300FC2025092459797 CONTRACT 2470354-UTU COX PERFORMING ARTS CENTER REMODEL | HH |  | 0 | 12055.06 | 0 | 0 |  | 2470354 | 6849
2025-09-23 | LAYTON CONST CO 009 | CO |  | 0 |  | 130264 | 0 |  | 2475229
2025-10-04 | SHUMS CODA ASSOCIATES INC GAX300FC2025100360350 CONTRACT 2570035-UTU COX AUDITORIUM REMODEL AND ADDITION | HH |  | 0 | 3580.3 | 0 | 0 |  | 2570035 | 6873
2025-10-09 | CMB Consultants LC GAX300FC2025100860571 CONTRACT 2570047-COX AUDITORIUM REMODEL AND ADDIT ENCLOSURE | HH |  | 0 | 2880 | 0 | 0 |  | 2570047 | 6849
2025-10-09 | CMB Consultants LC GAX300FC2025100860573 CONTRACT 2470354-UTU COX PERFORMING ARTS CENTER REMODEL | HH |  | 0 | 5055.9 | 0 | 0 |  | 2470354 | 6849
2025-10-09 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025100860584 CONTRACT 2475229-PAY APP #16-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 1694716.76 | 0 | 0 |  | 2475229 | 6813
2025-10-09 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025100860585 CONTRACT 2475229-PAY APP #16-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 89195.62 | 0 | 0 |  | 2475229 | 6813
2025-10-09 | LAYTON CONST CO 010 | CO |  | 0 |  | 79717 | 0 |  | 2475229
2025-10-24 | SPARANO + MOONEY ARCHITECTURE GAX300FC2025102361191 CONTRACT 2470088 - UTU COX AUDITORIUM ADDITION & REMODEL | HH |  | 0 | 45916.43 | 0 | 0 |  | 2470088 | 6861
2025-10-30 | Wenger Corporation GAX300FC2025102961398 CONTRACT 2575249-PAY APP #3-UTU COX AUDITORIUM RMDL/ADDIT | HH |  | 0 | 137395.51 | 0 | 0 |  | 2575249 | 6813
2025-10-30 | Wenger Corporation GAX300FC2025102961399 CONTRACT 2575249-PAY APP #3-UTU COX AUDITORIUM RMDL/ADDIT | HH |  | 0 | 7231.34 | 0 | 0 |  | 2575249 | 6813
2025-11-01 | SHUMS CODA ASSOCIATES INC GAX300FC2025103161504 CONTRACT 2570035-UTU COX AUDITORIUM REMODEL AND ADDITION | HH |  | 0 | 1668.5 | 0 | 0 |  | 2570035 | 6873
2025-11-12 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025111161898 CONTRACT 2475229-PAY APP #17-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 1420326.76 | 0 | 0 |  | 2475229 | 6813
2025-11-12 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025111161899 CONTRACT 2475229-PAY APP #17-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 74754.04 | 0 | 0 |  | 2475229 | 6813
2025-11-13 | CMB Consultants LC GAX300FC2025111261984 CONTRACT 2570047-COX AUDITORIUM REMODEL AND ADDIT ENCLOSURE | HH |  | 0 | 13156.73 | 0 | 0 |  | 2570047 | 6849
2025-11-25 | SPARANO + MOONEY ARCHITECTURE GAX300FC2025112462551 CONTRACT 2470088 - UTU COX AUDITORIUM ADDITION & REMODEL | HH |  | 0 | 29761.06 | 0 | 0 |  | 2470088 | 6861
2025-12-02 | SHUMS CODA ASSOCIATES INC GAX300FC2025120162738 CONTRACT 2570035-UTU COX AUDITORIUM REMODEL AND ADDITION | HH |  | 0 | 5093.8 | 0 | 0 |  | 2570035 | 6873
2025-12-12 | CMB Consultants LC GAX300FC2025121163256 CONTRACT 2470354-UTU COX PERFORMING ARTS CENTER REMODEL | HH |  | 0 | 20057.39 | 0 | 0 |  | 2470354 | 6849
2025-12-12 | SPARANO + MOONEY ARCHITECTURE GAX300FC2025121163251 CONTRACT 2470088 - UTU COX AUDITORIUM ADDITION & REMODEL | HH |  | 0 | 28920.15 | 0 | 0 |  | 2470088 | 6861
2025-12-12 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025121163274 CONTRACT 2475229-PAY APP #19-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 1404148.62 | 0 | 0 |  | 2475229 | 6813
2025-12-12 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2025121163275 CONTRACT 2475229-PAY APP #19-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 73902.56 | 0 | 0 |  | 2475229 | 6813
2025-12-23 10:33 | LAYTON CONST CO 011 | CO |  | 0 |  | 120024 | 0 |  | 2475229
2025-12-23 10:34 | LAYTON CONST CO 012 | CO |  | 0 |  | 52277 | 0 |  | 2475229
2026-01-06 | Bringhurst Plumbing & Heating, Inc. GAX300FC2026010264002 PO 240155 UTU COX AUDITORIUM | HH |  | 0 | 21270 | 21270 | 0 |  |  | 6813
2026-01-10 | CMB Consultants LC GAX300FC2026010964269 CONTRACT 2570047-COX AUDITORIUM REMODEL AND ADDIT ENCLOSURE | HH |  | 0 | 975 | 0 | 0 |  | 2570047 | 6849
2026-01-10 | CMB Consultants LC GAX300FC2026010964270 CONTRACT 2470354-UTU COX PERFORMING ARTS CENTER REMODEL | HH |  | 0 | 3500 | 0 | 0 |  | 2470354 | 6849
2026-01-12 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2026011064320 CONTRACT 2475229-PAY APP #20-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 57717.3 | 0 | 0 |  | 2475229 | 6813
2026-01-12 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2026011064319 CONTRACT 2475229-PAY APP #20-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 1096628.72 | 0 | 0 |  | 2475229 | 6813
2026-01-21 | SPARANO + MOONEY ARCHITECTURE GAX300FC2026012064697 CONTRACT 2470088 - UTU COX AUDITORIUM ADDITION & REMODEL | HH |  | 0 | 28525.91 | 0 | 0 |  | 2470088 | 6861
2026-09-29 | SPARANO + MOONEY AMD 004 | CO |  | 0 |  | 13670 | 0 |  | 2470088
2026-01-27 | SHUMS CODA ASSOCIATES INC GAX300FC2026012664959 CONTRACT 2570035-UTU COX AUDITORIUM REMODEL AND ADDITION | HH |  | 0 | 2217.55 | 0 | 0 |  | 2570035 | 6873
2026-02-03 | Wenger Corporation GAX300FC2026020265399 CONTRACT 2575249-PAY APP #4-UTU COX AUDITORIUM RMDL/ADDIT | HH |  | 0 | 344226.09 | 0 | 0 |  | 2575249 | 6813
2026-02-03 | Wenger Corporation GAX300FC2026020265400 CONTRACT 2575249-PAY APP #4-UTU COX AUDITORIUM RMDL/ADDIT | HH |  | 0 | 18117.16 | 0 | 0 |  | 2575249 | 6813
2026-02-03 | Wenger Corporation GAX300FC2026020265401 CONTRACT 2575249-PAY APP #5-UTU COX AUDITORIUM RMDL/ADDIT | HH |  | 0 | 48495.36 | 0 | 0 |  | 2575249 | 6813
2026-02-03 | Wenger Corporation GAX300FC2026020265402 CONTRACT 2575249-PAY APP #5-UTU COX AUDITORIUM RMDL/ADDIT | HH |  | 0 | 2552.39 | 0 | 0 |  | 2575249 | 6813
2026-02-10 | SPARANO + MOONEY ARCHITECTURE GAX300FC2026020965840 CONTRACT 2470088 - UTU COX AUDITORIUM ADDITION & REMODEL | HH |  | 0 | 25946.36 | 0 | 0 |  | 2470088 | 6861
2026-02-13 | CMB Consultants LC GAX300FC2026021265995 CONTRACT 2470354-UTU COX PERFORMING ARTS CENTER REMODEL | HH |  | 0 | 8000 | 0 | 0 |  | 2470354 | 6849
2026-02-13 | LAYTON CONST CO 013 | CO |  | 0 |  | 56482 | 0 |  | 2475229
2026-03-11 | SHUMS CODA ASSOCIATES INC GAX300FC2026031067189 CONTRACT 2570035-UTU COX AUDITORIUM REMODEL AND ADDITION | HH |  | 0 | 2079.05 | 0 | 0 |  | 2570035 | 6873
2026-03-10 | CMB Consultants LC GAX300FC2026030967091 CONTRACT 2470354-UTU COX PERFORMING ARTS CENTER REMODEL | HH |  | 0 | 3000 | 0 | 0 |  | 2470354 | 6849
2026-03-12 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2026031167295 CONTRACT 2475229-PAY APP #21-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 64370.49 | 0 | 0 |  | 2475229 | 6813
2026-03-12 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2026031167296 CONTRACT 2475229-PAY APP #22-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 1384362.64 | 0 | 0 |  | 2475229 | 6813
2026-03-12 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2026031167297 CONTRACT 2475229-PAY APP #22-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 72861.19 | 0 | 0 |  | 2475229 | 6813
2026-03-12 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2026031167294 CONTRACT 2475229-PAY APP #21-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 1223039.22 | 0 | 0 |  | 2475229 | 6813
2026-03-12 | SHUMS CODA ASSOCIATES INC GAX300FC2026031167282 CONTRACT 2570035-UTU COX AUDITORIUM REMODEL AND ADDITION | HH |  | 0 | 3177.8 | 0 | 0 |  | 2570035 | 6873
2026-03-18 | Wenger Corporation GAX300FC2026031767590 CONTRACT 2575249-PAY APP #6-UTU COX AUDITORIUM RMDL/ADDIT | HH |  | 0 | 276372.72 | 0 | 0 |  | 2575249 | 6813
2026-03-18 | Wenger Corporation GAX300FC2026031767591 CONTRACT 2575249-PAY APP #6-UTU COX AUDITORIUM RMDL/ADDIT | HH |  | 0 | 14545.93 | 0 | 0 |  | 2575249 | 6813
2026-03-19 | SPARANO + MOONEY ARCHITECTURE GAX300FC2026031867614 CONTRACT 2470088 - UTU COX AUDITORIUM ADDITION & REMODEL | HH |  | 0 | 33435.83 | 0 | 0 |  | 2470088 | 6861
2026-03-20 | City of St George GAX300FC2026031967651 PO 244723 UTU IMPACT FEES COX AUDITORIUM | HH |  | 0 | 97811.12 | 97811.12 | 0 |  |  | 6861
2026-04-02 | Wenger Corporation GAX300FC2026040168153 CONTRACT 2575249-PAY APP #7-UTU COX AUDITORIUM RMDL/ADDIT | HH |  | 0 | 230897.5 | 0 | 0 |  | 2575249 | 6813
2026-04-02 | Wenger Corporation GAX300FC2026040168154 CONTRACT 2575249-PAY APP #7-UTU COX AUDITORIUM RMDL/ADDIT | HH |  | 0 | 12152.5 | 0 | 0 |  | 2575249 | 6813
2026-04-04 | StageRight Corporation GAX300FC2026040368265 CONTRACT 2575266-PAY APP #2-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 85525 | 0 | 0 |  | 2575266 | 6813
2026-04-14 | CMB Consultants LC GAX300FC2026041368580 CONTRACT 2470354-UTU COX PERFORMING ARTS CENTER REMODEL | HH |  | 0 | 2100 | 0 | 0 |  | 2470354 | 6849
2026-04-28 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2026042769169 CONTRACT 2475229-PAY APP #23-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 1205051.62 | 0 | 0 |  | 2475229 | 6813
2026-04-28 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2026042769170 CONTRACT 2475229-PAY APP #23-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 63423.77 | 0 | 0 |  | 2475229 | 6813
2026-05-07 | CMB Consultants LC GAX300FC2026050669687 CONTRACT 2470354-UTU COX PERFORMING ARTS CENTER REMODEL | HH |  | 0 | 13000 | 0 | 0 |  | 2470354 | 6849
2026-05-14 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2026051369971 CONTRACT 2475229-PAY APP #24-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 518090.39 | 0 | 0 |  | 2475229 | 6813
2026-05-14 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2026051369972 CONTRACT 2475229-PAY APP #24-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 27267.92 | 0 | 0 |  | 2475229 | 6813
2026-05-16 | SPARANO + MOONEY ARCHITECTURE GAX300FC2026051570054 CONTRACT 2470088 - UTU COX AUDITORIUM ADDITION & REMODEL | HH |  | 0 | 15538.88 | 0 | 0 |  | 2470088 | 6861
2026-05-06 14:37 | LAYTON CONSTRUCTION COMPANY INC CO 014 | CO |  | 0 |  | 90428 | 0 |  | 2475229
2026-05-29 | Wenger Corporation GAX300FC2026052870597 CONTRACT 2575249-PAY APP #8-UTU COX AUDITORIUM RMDL/ADDIT | HH |  | 0 | 422387.72 | 0 | 0 |  | 2575249 | 6813
2026-05-29 | Wenger Corporation GAX300FC2026052870598 CONTRACT 2575249-PAY APP #8-UTU COX AUDITORIUM RMDL/ADDIT | HH |  | 0 | 22230.93 | 0 | 0 |  | 2575249 | 6813
2026-06-03 | Wenger Corporation GAX300FC2026060270817 CONTRACT 2575249-PAY APP #9-UTU COX AUDITORIUM RMDL/ADDIT | HH |  | 0 | 56542.72 | 0 | 0 |  | 2575249 | 6813
2026-06-03 | Wenger Corporation GAX300FC2026060270818 CONTRACT 2575249-PAY APP #9-UTU COX AUDITORIUM RMDL/ADDIT | HH |  | 0 | 2975.93 | 0 | 0 |  | 2575249 | 6813
2026-06-13 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2026061271372 CONTRACT 2475229-PAY APP #26-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 56335.63 | 0 | 0 |  | 2475229 | 6813
2026-06-13 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2026061271373 CONTRACT 2475229-PAY APP #26-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 2965.03 | 0 | 0 |  | 2475229 | 6813
2026-06-20 | SPARANO + MOONEY ARCHITECTURE GAX300FC2026061971639 CONTRACT 2470088 - UTU COX AUDITORIUM ADDITION & REMODEL | HH |  | 0 | 60373.58 | 0 | 0 |  | 2470088 | 6861
2026-06-25 | SHUMS CODA ASSOCIATES INC GAX300FC2026062471906 CONTRACT 2570035-UTU COX AUDITORIUM REMODEL AND ADDITION | HH |  | 0 | 2572.41 | 0 | 0 |  | 2570035 | 6873
2026-06-11 | CMB Consultants LC GAX300FC2026061071218 CONTRACT 2470354-UTU COX PERFORMING ARTS CENTER REMODEL | HH |  | 0 | 5500 | 0 | 0 |  | 2470354 | 6849
2026-06-24 | Utah Tech University GAX300FC2026062371820 CONTRACT 2475248-UTU COX AUDITORIUM REMODEL AND ADDITION | HH |  | 0 | 606199.45 | 0 | 0 |  | 2475248 | 6188
2026-07-09 | Utah Tech University GAX300FC2026070872608 CONTRACT 2475248-UTU COX AUDITORIUM REMODEL AND ADDITION | HH |  | 0 | 1010816.45 | 0 | 0 |  | 2475248 | 6188
2026-07-09 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2026070872633 CONTRACT 2475229-PAY APP #27-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 7292.86 | 0 | 0 |  | 2475229 | 6813
2026-07-09 | LAYTON CONSTRUCTION COMPANY INC GAX300FC2026070872634 CONTRACT 2475229-PAY APP #27-UTU COX AUDITORIUM REMODEL | HH |  | 0 | 383.84 | 0 | 0 |  | 2475229 | 6813
2026-07-07 | CMB Consultants LC GAX300FC2026070672436 CONTRACT 2470354-UTU COX PERFORMING ARTS CENTER REMODEL | HH |  | 0 | 4500 | 0 | 0 |  | 2470354 | 6849
2026-07-15 09:18 | LAYTON CONSTRUCTION COMPANY INC CO 015 | CO |  | 0 |  | 138228 | 0 |  | 2475229
13/26 | SHUMS CODA ASSOCIATES INC GAX300FC2026071773152 CONTRACT 2570035-UTU COX AUDITORIUM REMODEL AND ADDITION |  |  | 0 | 471 | 471 | 0 |  |  | 6873
13/26 | SHUMS CODA ASSOCIATES INC GAX300FC2026071773153 CONTRACT 2570035-UTU COX AUDITORIUM REMODEL AND ADDITION |  |  | 0 | 5207.45 | 5207.45 | 0 |  |  | 6873
|  |  |  | 0 |  | 0 | 0
FY'27 |  |  |  | 0 |  | 0 | 0
2026-08-06 | CMB Consultants LC GAX300FC2026080573703 CONTRACT 2470354-UTU COX PERFORMING ARTS CENTER REMODEL |  |  | 0 | 6000 | 6000 | 0 |  |  | 6849
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 24275640
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency