## PROJECT
[7 empty] | RESERVES: |  |  |  | FUNDING:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR |  |  |  | STATE | 3500000 | 24.08%
| FUNDING |  | OTHER |  |  |  | DESIGN |  |  |  | WSU | 11035000 | 75.92%
| STATE RISK NUMBER |  | 04017 |  |  |  | INSPECTION |  |  |  | TOTAL | 14535000
| PROJECT TITLE |  | WSU SUBSTATION BATTERY PROJECT
| PROJECT # |  | 25407810 | OPEN |  |  | CONTINGENCY/LEGAL
| CODING BLOCK |  | 3000-300-3402-FXAAA-25407810 |  |  | 105900.43 | TOTAL | 0
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's
10735541.2804
YR | CURRENT TOTALS |  | 14535000 | 394438.83 | 14140561.17 | 14246461.6 | 288538.4 | 13428543.79 |  |  | 10290635.76
444905.5204
|  |  |  | 0 |  | 0 | 0
FY'25 |  |  |  | 0 |  | 0 | 0
2024-10-28 | IDT 25C3*035 IDT WSU EST REV | DF | 11035000 | 11035000 |  | 0 | 11035000 |  |  | 4760 |  | ADDED PER FP04 REV REPORT
2024-12-18 | UT ST FIRE MARSHAL GAX 25C5*074 | EH |  | 0 | 75 | 75 | 0 |  |  | 6873
2024-12-24 | SOLAR FARMERS DEVCO LLC - CONTRACT | CO |  | 0 |  | 13362343.17 | 0 |  | 2575295
2025-01-03 | RE 25C3*132 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 4432757.39
2025-01-03 | CR 25M5*061 RE 25C3*132 | N/A |  | 0 |  | 0 | 0 | 4432757.39 |  | 4760
2025-01-06 | SOLAR FFARMERS GAX FC2025010647673 | EH |  | 0 | 4211119.52 | 0 | 0 |  | 2575295 | 6813
2025-01-06 | ZIONS/SOLAR FARMERS RTNG GAX FC2025010647674 | EH |  | 0 | 221637.87 | 0 | 0 |  | 2575295 | 6813
2025-02-04 | ITA30025*56 DFCM CofC Dec 2024 | HH |  | 0 | 28729.04 | 28729.04 | 0 |  |  | 6872
2025-02-06 | RE 25C3*170 | NA |  | 0 |  | 0 | 0 |  |  | 4760 | 28804.04
2025-02-06 | CR30025M5000082 RE30025C3000170 | NA |  | 0 |  | 0 | 0 | 28804.04 |  | 4760
2025-04-18 | UTAH STATE FIRE MARSHAL'S OFFICE GAX30025C5000128 | HH |  | 0 | 75 | 75 | 0 |  |  | 6873
2025-04-22 | SOLAR FARMERS DEVCO LLC GAX300FC2025042252653 | HH |  | 0 | 249511.13 | 0 | 0 |  | 2575295 | 6813
2025-04-22 | SOLAR FARMERS DEVCO LLC GAX300FC2025042252654 | HH |  | 0 | 13132.17 | 0 | 0 |  | 2575295 | 6813
2025-04-29 | IDT30025C30000134 | HH |  | 0 | 80292 | 80292 | 0 |  |  | 6865
2025-04-29 | IDT30025C30000134 | HH |  | 0 | 13384 | 13384 | 0 |  |  | 6870
2025-05-08 | RE 25C3*250 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 356394.3
2025-05-01 09:30 | WC3 AMD 001 | CO |  | 0 |  | -13470.45 | 0 |  | 2570277
2025-05-30 | SOLAR FARMERS DEVCO LLC GAX300FC2025052954461 CONTRACT 2575295-PAY APP #3-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 306112.44 | 0 | 0 |  | 2575295 | 6813
2025-05-30 | SOLAR FARMERS DEVCO LLC GAX300FC2025052954462 CONTRACT 2575295-PAY APP #3-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 16111.18 | 0 | 0 |  | 2575295 | 6813
2025-06-05 | RE 25C3*301 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 322223.62
2025-06-26 | WEST COAST CODE CONSULTANTS INC GAX300FC2025062555750 CONTRACT 2570277-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 153.4 | 0 | 0 |  | 2570277 | 6873
2025-06-30 | RE 25C3*332 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 153.4
13/25 | SOLAR FARMERS DEVCO LLC GAX300FC2025070156161 CONTRACT 2575295-PAY APP #4-WSU SUBSTATION BATTERY SYSTEM | TR |  | 0 | 1402347.85 | 0 | 0 |  | 2575295 | 6813
13/25 | SOLAR FARMERS DEVCO LLC GAX300FC2025070156162 CONTRACT 2575295-PAY APP #4-WSU SUBSTATION BATTERY SYSTEM | TR |  | 0 | 73807.78 | 0 | 0 |  | 2575295 | 6813
2025-05-22 | CR 25M5*121 RE 25C3*250 | N/A |  | 0 |  | 0 | 0 | 356394.3 |  | 4760
13/25 | RE 25C3*377 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 1476155.63
13/25 | WEST COAST CODE CONSULTANTS INC GAX300FC2025072257296 CONTRACT 2570277-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 1262.24 | 0 | 0 |  | 2570277 | 6873
13/25 | RE 25C3*398 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 1262.24
2025-04-02 | WEST COAST CODE CONSULTANTS INC CONTRACT | CO |  | 0 |  | 25000 | 0 |  | 2570277
|  |  |  | 0 |  | 0 | 0
FY'26 |  |  |  | 0 |  | 0 | 0
2025-08-01 | WEBER STATE UNIVERSITY CR30026M5000007 25407810 WSU SUBSTATION BATTERY PROJECT | HH |  | 0 |  | 0 | 0 | 1476155.63 |  | 4760
2025-07-24 | SOLAR FARMERS DEVCO LLC GAX300FC2025072357348 CONTRACT 2575295-PAY APP #5-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 768439.21 | 0 | 0 |  | 2575295 | 6813
2025-07-24 | SOLAR FARMERS DEVCO LLC GAX300FC2025072357349 CONTRACT 2575295-PAY APP #5-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 40444.17 | 0 | 0 |  | 2575295 | 6813
2025-07-26 | WEBER STATE UNIVERSITY CR30026M5000006 25407810 WSU SUBSTATION BATTERY PROJECT | HH |  | 0 |  | 0 | 0 | 153.4 |  | 4760
2025-07-19 | WEBER STATE UNIVERSITY CR30026M5000003 25407810 WSU SUBSTATION BATTERY PROJECT | HH |  | 0 |  | 0 | 0 | 322223.62 |  | 4760
2025-08-15 | IDT30026C30000004 2025 GS FY 26 CAPITAL IMPROVEMENT (HB6,SB2,SB3) - INCOME FUND | HH | 3500000 | 3500000 |  | 0 | 3500000 |  |  | 4667
2025-08-14 | SOLAR FARMERS CO 001 | CO |  | 0 |  | 59289.59 | 0 |  | 2575295
2025-08-23 | WEBER STATE UNIVERSITY CR30026M5000013 25407810 WSU SUBSTATION BATTERY PROJECT | HH |  | 0 |  | 0 | 0 | 1262.24 |  | 4760
2025-08-26 | WEST COAST CODE CONSULTANTS INC GAX300FC2025082558549 CONTRACT 2570277-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 857.3 | 0 | 0 |  | 2570277 | 6873
2025-09-04 | SOLAR FARMERS DEVCO LLC GAX300FC2025090358933 CONTRACT 2575295-PAY APP #6-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 403442.5 | 0 | 0 |  | 2575295 | 6813
2025-09-04 | SOLAR FARMERS DEVCO LLC GAX300FC2025090358934 CONTRACT 2575295-PAY APP #6-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 21233.82 | 0 | 0 |  | 2575295 | 6813
2025-09-05 | RE 26C3*038 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 1234417
2025-09-26 | SOLAR FARMERS DEVCO LLC GAX300FC2025092559889 CONTRACT 2575295-PAY APP #7-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 3447803.48 | 0 | 0 |  | 2575295 | 6813
2025-09-26 | SOLAR FARMERS DEVCO LLC GAX300FC2025092559890 CONTRACT 2575295-PAY APP #7-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 181463.34 | 0 | 0 |  | 2575295 | 6813
2025-10-06 | RE 26C3*073 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 3629266.82
2025-10-11 | WEST COAST CODE CONSULTANTS INC GAX300FC2025101060722 CONTRACT 2570277-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 1346.85 | 0 | 0 |  | 2570277 | 6873
2025-10-10 | CR30026M5000025 | HH |  | 0 |  | 0 | 0 | 1234417 |  | 4760
2025-10-14 | SOLAR FARMERS CO 002 | CO |  | 0 |  | 6000 | 0 |  | 2575295
2025-11-06 | RE 26C3*115 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 1346.85
2025-11-12 | WEST COAST CODE CONSULTANTS INC GAX300FC2025111161895 CONTRACT 2570277-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 97.8 | 0 | 0 |  | 2570277 | 6873
2025-11-20 | WEBER STATE UNIVERSITY CR30026M5000034 25407810 WSU SUBSTATION BATTERY PROJECT | HH |  | 0 |  | 0 | 0 | 3629266.82 |  | 4760
2025-11-27 | SOLAR FARMERS DEVCO LLC GAX300FC2025112662677 CONTRACT 2575295-PAY APP #8-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 1847774.98 | 0 | 0 |  | 2575295 | 6813
2025-11-27 | SOLAR FARMERS DEVCO LLC GAX300FC2025112662678 CONTRACT 2575295-PAY APP #8-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 97251.32 | 0 | 0 |  | 2575295 | 6813
2025-12-02 | WEST COAST CODE CONSULTANTS INC GAX300FC2025120162743 CONTRACT 2570277-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 638.4 | 0 | 0 |  | 2570277 | 6873
2025-12-04 | RE 26C3*156 | N/A |  | 0 |  | 0 | 0 |  |  | 4760 | 1945762.5
2025-12-05 | WEBER STATE UNIVERSITY CR30026M5000037 25407810 WSU SUBSTATION BATTERY PROJECT | HH |  | 0 |  | 0 | 0 | 1346.85 |  | 4760
2026-01-05 | WEBER STATE UNIVERSITY CR30026M5000046 25407810 WSU SUBSTATION BATTERY PROJECT | HH |  | 0 |  | 0 | 0 | 1945762.5 |  | 4760
2026-01-12 | SOLAR FARMERS DEVCO LLC GAX300FC2026011064292 CONTRACT 2575295-PAY APP #9-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 6300 | 0 | 0 |  | 2575295 | 6813
2026-01-12 | SOLAR FARMERS DEVCO LLC GAX300FC2026011064291 CONTRACT 2575295-PAY APP #9-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 119700 | 0 | 0 |  | 2575295 | 6813
2026-01-20 | GAX 26C5000083 Refund | HH |  | 0 |  | 0 | 0 |  |  | 4760 | -3137908.03
2026-12-02 | WEST COAST CODE AMD 002 | CO |  | 0 |  | -7173.56 | 0 |  | 2570277
2026-01-20 | SOLAR FARMERS CO 003 | CO |  | 0 |  | 233550.57 | 0 |  | 2575295
2026-03-12 | WEST COAST CODE CONSULTANTS INC GAX300FC2026031167237 PO 244533-WSU SUBSTATION BATTERY PROJECT | HH |  | 0 | 289.8 | 289.8 | 0 |  |  | 6873
2026-04-02 | SOLAR FARMERS DEVCO LLC GAX300FC2026040168135 CONTRACT 2575295-PAY APP #11-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 81006.4 | 0 | 0 |  | 2575295 | 6813
2026-04-02 | SOLAR FARMERS DEVCO LLC GAX300FC2026040168136 CONTRACT 2575295-PAY APP #11-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 4263.5 | 0 | 0 |  | 2575295 | 6813
2026-06-04 | SOLAR FARMERS DEVCO LLC GAX300FC2026060370902 CONTRACT 2575295-PAY APP #12-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 40261.23 | 0 | 0 |  | 2575295 | 6813
2026-06-04 | SOLAR FARMERS DEVCO LLC GAX300FC2026060370903 CONTRACT 2575295-PAY APP #12-WSU SUBSTATION BATTERY SYSTEM | HH |  | 0 | 2119.01 | 0 | 0 |  | 2575295 | 6813
2026-06-02 | PO 246990-WSU RMP PERFORMED SCOPE GAX300FC2026060270709 | HH |  | 0 | 361914 | 361914 | 0 |  |  | 6813
13/26 | SOLAR FARMERS DEVCO LLC GAX300FC2026071472917 CONTRACT 2575295-PAY APP #13-WSU SUBSTATION BATTERY SYSTEM |  |  | 0 | 91355.27 | 91355.27 | 0 |  |  | 6813
13/26 | SOLAR FARMERS DEVCO LLC GAX300FC2026071472918 CONTRACT 2575295-PAY APP #13-WSU SUBSTATION BATTERY SYSTEM |  |  | 0 | 4808.17 | 4808.17 | 0 |  |  | 6813
13/26 | IDT30026000000322 CHANGING REVENUE_SOURCE TO 4658 |  | -1346.85 | -1346.85 |  | 0 | -1346.85 |  |  | 4760
13/26 | IDT30026000000322 CHANGING REVENUE_SOURCE TO 4658 |  | 1346.85 | 1346.85 |  | 0 | 1346.85 |  |  | 4658
13/26 | IDT30026000000318 CHANGING REVENUE_SOURCE TO 4658 |  | -2393543.79 | -2393543.79 |  | 0 | -2393543.79 |  |  | 4760
13/26 | IDT30026000000318 CHANGING REVENUE_SOURCE TO 4658 |  | -2393543.79 | -2393543.79 |  | 0 | -2393543.79 |  |  | 4658
13/26 | IDT30026000000318 CHANGING REVENUE_SOURCE TO 4658 |  | 2393543.79 | 2393543.79 |  | 0 | 2393543.79 |  |  | 4760
13/26 | IDT30026000000318 CHANGING REVENUE_SOURCE TO 4658 |  | 2393543.79 | 2393543.79 |  | 0 | 2393543.79 |  |  | 4658
13/26 | IDT30026000000317 CHANGING REVENUE_SOURCE TO 4658 |  | 1945762.5 | 1945762.5 |  | 0 | 1945762.5 |  |  | 4658
13/26 | IDT30026000000317 CHANGING REVENUE_SOURCE TO 4658 |  | -1945762.5 | -1945762.5 |  | 0 | -1945762.5 |  |  | 4760
13/26 | IDT30026000000316 CHANGING REVENUE_SOURCE TO 4658 |  | 3629266.82 | 3629266.82 |  | 0 | 3629266.82 |  |  | 4658
13/26 | IDT30026000000316 CHANGING REVENUE_SOURCE TO 4658 |  | -3629266.82 | -3629266.82 |  | 0 | -3629266.82 |  |  | 4760
13/26 | IDT30026000000316 CHANGING REVENUE_SOURCE TO 4658 |  | 1234417 | 1234417 |  | 0 | 1234417 |  |  | 4658
13/26 | IDT30026000000316 CHANGING REVENUE_SOURCE TO 4658 |  | -1234417 | -1234417 |  | 0 | -1234417 |  |  | 4760
|  |  |  | 0 |  | 0 | 0
FY'27 |  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 25407810
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency