## PROJECT
RESERVES:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR
| FUNDING |  | HEF WSU |  |  |  | DESIGN
| STATE RISK NUMBER |  | 08118 |  |  |  | INSPECTION
| PROJECT TITLE |  | WSU - STUDENT SERVICES REMODEL AND MEP |  |  |  | INSURANCE
| PROJECT # |  | 25418810 | CLOSED |  |  | CONTINGENCY/LEGAL
| CODING BLOCK |  | 3000-300-3402-FXAAA-25418810 |  |  | 0 | TOTAL | 0
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
3313.61
YR | CURRENT TOTALS |  | 6993981.91 | 0 | 6993981.91 | 6993981.91 | 0 | 3313.61 |  |  | 3313.61
[11 empty] | 0 | -3313.61
| REIMBURSE COSTS WITH CD RESERVE STARTING FY26. |  |  | 0 |  | 0 | 0
FY'25 |  |  |  | 0 |  | 0 | 0
2024-11-19 | GSBS PC dba GSBS ARCHITECTS - CONTRACT | N/A |  | 0 |  | 684589 | 0 |  | 2570138
2024-11-19 | GSBS AMD 001 | CO |  | 0 |  | 153660 | 0 |  | 2570138
2024-12-09 | GSBS GAX FC2024120946468 | EH |  | 0 | 317143.71 | 0 | 0 |  | 2570138 | 6861
2025-01-15 | GSBS PC GAX300FC2025011548131 | HH |  | 0 | 130110.24 | 0 | 0 |  | 2570138 | 6861
2025-03-10 | GSBS PC GAX300FC2025031050742 | TR |  | 0 | 43027.56 | 0 | 0 |  | 2570138 | 6861
2025-02-25 | GSBS PC GAX300FC2025022550024 | TR |  | 0 | 130110.24 | 0 | 0 |  | 2570138 | 6861
2025-03-14 | UTAH STATE FIRE MARSHAL'S OFFICE GAX30025C5000121 | HH |  | 0 | 1091.84 | 1091.84 | 0 |  |  | 6873
2025-03-31 | WEST COAST CODE CONSULTANTS INC GAX30025C5000123 | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-01-07 | GSBS AMD 002 | CO |  | 0 |  | -14560 | 0 |  | 2570138
2025-04-10 | GSBS PC GAX300FC2025041052136 | TR |  | 0 | 20329.73 | 0 | 0 |  | 2570138 | 6861
2025-04-25 | TRNSF TO 25418810 FROM 21137300 PROJ RESERVE FOR FY26 EARLY DESIGN COSTS YTD IDT30025C30000125 | HH | 641938.32 | 641938.32 |  | 0 | 641938.32 |  |  | 4666
2025-05-06 | WEST COAST CODE CONSULTANTS INC GAX30025C5000139 | TR |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-06-02 | ENGAGE CONTRACTING INC GAX300FC2025053054521 CONTRACT 2575446-PAY APP #1-WSU STUDENT SERVICES RMDL AND MEP, PH I | TR |  | 0 | 190145.07 | 0 | 0 |  | 2575446 | 6813
2025-06-02 | ENGAGE CONTRACTING INC GAX300FC2025053054522 CONTRACT 2575446-PAY APP #1-WSU STUDENT SERVICES RMDL AND MEP, PH I | TR |  | 0 | 10007.64 | 0 | 0 |  | 2575446 | 6813
2025-06-10 | GSBS PC GAX300FC2025060954968 CONTRACT 2570138-WSU STUDENT SERVICES REMODEL AND MEP | TR |  | 0 | 32527.56 | 0 | 0 |  | 2570138 | 6861
2025-06-27 | ENGAGE CONTRACTING INC GAX300FC2025062655897 CONTRACT 2575446-PAY APP #2-WSU STUDENT SERVICES RMDL AND MEP, PH I | TR |  | 0 | 356471.47 | 0 | 0 |  | 2575446 | 6813
2025-06-27 | ENGAGE CONTRACTING INC GAX300FC2025062655898 CONTRACT 2575446-PAY APP #2-WSU STUDENT SERVICES RMDL AND MEP, PH I | TR |  | 0 | 18761.66 | 0 | 0 |  | 2575446 | 6813
13/25 | ITA3002500000117 DFCM Course of Construction May 1, 2025 thru May 31, 2025 (See Excel attachment) $13,895,546.44 | TR |  | 0 | 10220.04 | 10220.04 | 0 |  |  | 6872
13/25 | GSBS PC GAX300FC2025070256254 CONTRACT 2570138-WSU STUDENT SERVICES REMODEL AND MEP | TR |  | 0 | 12197.83 | 0 | 0 |  | 2570138 | 6861
13/25 | IDT30025C30000158 LEGAL FEES FROM 25418810 TO 21257300 | TR |  | 0 | 4754 | 4754 | 0 |  |  | 6870
13/25 | TRNSF TO 25418810 FROM 21136300 PROJ RESERVE FOR FY26 EARLY DESIGN | TR | 635210.27 | 635210.27 |  | 0 | 635210.27 |  |  | 4666
2025-04-28 | ENGAGE CONTRACTING INC - CONTRACT | CO |  | 0 |  | 4753509 | 0 |  | 2575446
2025-04-30 | WEST COAST CODE CONSULTANTS INC - CONTRACT | CO |  | 0 |  | 45000 | 0 |  | 2570312
FY'26
2025-08-02 | ROCMONT INDUSTRIAL CORPORATION GAX300FC2025080157548 PO 238038-WSU SS LEAD X-RAY RM-REMOVE LEAD LINING IN XRAY ROOM | HH |  | 0 | 7793.75 | 7793.75 | 0 |  |  | 6819
2025-08-06 | ENGAGE CONTRACTING INC GAX300FC2025080557714 CONTRACT 2575446-PAY APP #3-WSU STUDENT SERVICES RMDL AND MEP, PH I | TR |  | 0 | 525353.29 | 0 | 0 |  | 2575446 | 6813
2025-08-06 | ENGAGE CONTRACTING INC GAX300FC2025080557715 CONTRACT 2575446-PAY APP #3-WSU STUDENT SERVICES RMDL AND MEP, PH I | TR |  | 0 | 27650.17 | 0 | 0 |  | 2575446 | 6813
2025-08-12 | GSBS PC GAX300FC2025081157951 CONTRACT 2570138-WSU STUDENT SERVICES REMODEL AND MEP | TR |  | 0 | 12197.84 | 0 | 0 |  | 2570138 | 6861
2025-08-15 | WSU AGENCY COMMITMENT PC0 6 - 25418810 | HH | 3313.61 | 3313.61 |  | 0 | 3313.61 |  |  |  | 3313.61
2025-08-15 | IDT30026C30000006 Return FY25 Early Supplemental Transfers From 25418810 TO 21136300 PROJ Reserve | HH | -1277148.59 | -1277148.59 |  | 0 | -1277148.59 |  |  | 4665
2025-08-16 | IDT30026C30000007 2025 GS SB 2 ITEM 148 FY 26 CAPITAL DEVELOPMENT - HIGHER ED FUND | HH | 8204500 | 8204500 |  | 0 | 8204500 |  |  | 4667
2025-08-16 | IDT30026C30000008 WSU AGENCY COMMITMENT PC0 6 - 25418810 | HH | 3313.61 | 3313.61 |  | 0 | 3313.61 |  |  | 4761
2025-08-16 | IDT30026C30000008 WSU AGENCY COMMITMENT PC0 6 - 25418810 | HH | -3313.61 | -3313.61 |  | 0 | -3313.61 |  |  | 4761
2025-08-18 13:05 | ENGAGE CONTRACTING INC - CO 001 | CO |  | 0 |  | 32466.79 | 0 |  | 2575446
2025-08-08 | WEBER STATE UNIVERSITY CONTRACT | CO |  | 0 |  | 1260000 | 0 |  | 2675057
2025-08-28 | WEBER STATE UNIVERSITY CR30026M5000014 25418810 WSU - STUDENT SERVICES REMODEL AND MEP | HH |  | 0 |  | 0 | 0 | 3313.61 |  | 4760
2025-09-04 | ENGAGE CONTRACTING INC GAX300FC2025090358935 CONTRACT 2575446-PAY APP #4-WSU STUDENT SERVICES RMDL AND MEP, PH I | HH |  | 0 | 646881.69 | 0 | 0 |  | 2575446 | 6813
2025-09-04 | ENGAGE CONTRACTING INC GAX300FC2025090358936 CONTRACT 2575446-PAY APP #4-WSU STUDENT SERVICES RMDL AND MEP, PH I | HH |  | 0 | 34046.41 | 0 | 0 |  | 2575446 | 6813
2025-09-10 | GSBS PC GAX300FC2025090959175 CONTRACT 2570138-WSU STUDENT SERVICES REMODEL AND MEP | HH |  | 0 | 12197.83 | 0 | 0 |  | 2570138 | 6861
2025-09-06 | WEST COAST CODE CONSULTANTS INC GAX30026C5000017 Plan Review Services 07/09/2025-1ST REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-09-25 | WEST COAST CODE CONSULTANTS INC GAX30026C5000036 Plan Review Services 08/06/2025-1ST REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-10-02 | ENGAGE CONTRACTING INC GAX300FC2025100160185 CONTRACT 2575446-PAY APP 5-WSU STUDENT SERVICES RMDL & MEP, PH I | HH |  | 0 | 596834.57 | 0 | 0 |  | 2575446 | 6813
2025-10-02 | ENGAGE CONTRACTING INC GAX300FC2025100160186 CONTRACT 2575446-PAY APP 5-WSU STUDENT SERVICES RMDL & MEP, PH I | HH |  | 0 | 31412.35 | 0 | 0 |  | 2575446 | 6813
2025-10-15 | GSBS PC GAX300FC2025101460791 CONTRACT 2570138-WSU STUDENT SERVICES REMODEL AND MEP | HH |  | 0 | 12197.84 | 0 | 0 |  | 2570138 | 6861
2025-10-11 | WEST COAST CODE CONSULTANTS INC GAX300FC2025101060721 CONTRACT 2570312-WSU STUDENT SERVICES REMODEL AND MEP, PH I | HH |  | 0 | 922.2 | 0 | 0 |  | 2570312 | 6873
2025-10-15 | UTAH STATE FIRE MARSHAL'S OFFICE GAX30026C5000042 FIRE SPRINKLER PLANS - 25-756 -09-30-2025 | HH |  | 0 | 1100 | 1100 | 0 |  |  | 6873
2025-10-01 | ENGAGE CONTRACTING INC - CO 002 | CO |  | 0 |  | 42065.76 | 0 |  | 2575446
2025-10-29 | WEST COAST CODE CONSULTANTS INC GAX30026C5000058 Plan Review Services 09/03/2025-1ST REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-10-29 | WEST COAST CODE CONSULTANTS INC GAX30026C5000058 Plan Review Services 09/30/2025-1ST REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-10-29 | WEST COAST CODE CONSULTANTS INC GAX30026C5000058 Plan Review Services 09/30/2025-1ST REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-11-06 | ENGAGE CONTRACTING INC GAX300FC2025110561691 CONTRACT 2575446-PAY APP 6-WSU STUDENT SERVICES RMDL & MEP, PH I | HH |  | 0 | 1004234.82 | 0 | 0 |  | 2575446 | 6813
2025-11-06 | ENGAGE CONTRACTING INC GAX300FC2025110561692 CONTRACT 2575446-PAY APP 6-WSU STUDENT SERVICES RMDL & MEP, PH I | HH |  | 0 | 52854.46 | 0 | 0 |  | 2575446 | 6813
2025-11-12 | WEST COAST CODE CONSULTANTS INC GAX300FC2025111161896 CONTRACT 2570312-WSU STUDENT SERVICES REMODEL AND MEP, PH I | HH |  | 0 | 263.2 | 0 | 0 |  | 2570312 | 6873
2025-11-13 | GSBS PC GAX300FC2025111261969 CONTRACT 2570138-WSU STUDENT SERVICES REMODEL AND MEP | HH |  | 0 | 12197.83 | 0 | 0 |  | 2570138 | 6861
2025-11-26 | ENGAGE CONTRACTING INC GAX300FC2025112562634 CONTRACT 2575446-PAY APP 7-WSU STUDENT SERVICES RMDL & MEP, PH I | HH |  | 0 | 619734.12 | 0 | 0 |  | 2575446 | 6813
2025-11-26 | ENGAGE CONTRACTING INC GAX300FC2025112562635 CONTRACT 2575446-PAY APP 7-WSU STUDENT SERVICES RMDL & MEP, PH I | HH |  | 0 | 32617.59 | 0 | 0 |  | 2575446 | 6813
2025-12-04 | WEST COAST CODE CONSULTANTS INC GAX300FC2025120362924 CONTRACT 2570312-WSU STUDENT SERVICES REMODEL AND MEP, PH I | HH |  | 0 | 624.4 | 0 | 0 |  | 2570312 | 6873
2025-12-10 | GSBS PC GAX300FC2025120963111 CONTRACT 2570138-WSU STUDENT SERVICES REMODEL AND MEP | HH |  | 0 | 12197.84 | 0 | 0 |  | 2570138 | 6861
2025-12-02 | ENGAGE CONTRACTING INC - CO 003 | CO |  | 0 |  | 43961.51 | 0 |  | 2575446
2026-01-10 | WEST COAST CODE CONSULTANTS INC GAX30026C2000095 Plan Review Services 11/25/2025-1ST REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2026-01-10 | GSBS PC GAX300FC2026010964282 CONTRACT 2570138-WSU STUDENT SERVICES REMODEL AND MEP | HH |  | 0 | 12197.83 | 0 | 0 |  | 2570138 | 6861
2026-01-14 | WEST COAST CODE CONSULTANTS INC GAX300FC2026011364478 CONTRACT 2570312-WSU STUDENT SERVICES REMODEL AND MEP, PH I | HH |  | 0 | 1071 | 0 | 0 |  | 2570312 | 6873
2026-01-21 | WEST COAST CODE CONSULTANTS INC GAX300FC2026012064685 CONTRACT 2570312-WSU STUDENT SERVICES REMODEL AND MEP, PH I | HH |  | 0 | 477.4 | 0 | 0 |  | 2570312 | 6873
2026-01-27 | ENGAGE CONTRACTING INC GAX300FC2026012664992 CONTRACT 2575446-PAY APP 8-WSU STUDENT SERVICES RMDL & MEP, PH I | HH |  | 0 | 20214.35 | 0 | 0 |  | 2575446 | 6813
2026-01-27 | ENGAGE CONTRACTING INC GAX300FC2026012664991 CONTRACT 2575446-PAY APP 8-WSU STUDENT SERVICES RMDL & MEP, PH I | HH |  | 0 | 384072.68 | 0 | 0 |  | 2575446 | 6813
2026-01-28 | ENGAGE CONTRACTING INC GAX300FC2026012765137 CONTRACT 2575446-PAY APP 9-WSU STUDENT SERVICES RMDL & MEP, PH I | HH |  | 0 | 304675.18 | 0 | 0 |  | 2575446 | 6813
2026-01-28 | ENGAGE CONTRACTING INC GAX300FC2026012765138 CONTRACT 2575446-PAY APP 9-WSU STUDENT SERVICES RMDL & MEP, PH I | HH |  | 0 | 16035.54 | 0 | 0 |  | 2575446 | 6813
2026-02-10 | GSBS PC GAX300FC2026020965843 CONTRACT 2570138-WSU STUDENT SERVICES REMODEL AND MEP | HH |  | 0 | 12197.84 | 0 | 0 |  | 2570138 | 6861
2026-02-18 | WEST COAST CODE CONSULTANTS INC GAX300FC2026021766113 CONTRACT 2570312-WSU STUDENT SERVICES REMODEL AND MEP, PH I | HH |  | 0 | 740.6 | 0 | 0 |  | 2570312 | 6873
2026-02-13 | ENGAGE CONTRACTING INC - CO 004 | CO |  | 0 |  | 7811.42 | 0 |  | 2575446
2026-02-25 | ENGAGE CONTRACTING INC GAX300FC2026022466470 CONTRACT 2575446-PAY APP 10-WSU STUDENT SERVICES RMDL & MEP, PH I | HH |  | 0 | 7420.85 | 0 | 0 |  | 2575446 | 6813
2026-02-25 | ENGAGE CONTRACTING INC GAX300FC2026022466471 CONTRACT 2575446-PAY APP 10-WSU STUDENT SERVICES RMDL & MEP, PH I | HH |  | 0 | 390.57 | 0 | 0 |  | 2575446 | 6813
2026-03-11 | GSBS PC GAX300FC2026031067177 CONTRACT 2570138-WSU STUDENT SERVICES REMODEL AND MEP | HH |  | 0 | 12197.83 | 0 | 0 |  | 2570138 | 6861
2026-03-17 | WEST COAST CODE CONSULTANTS INC GAX300FC2026031667478 CONTRACT 2570312-WSU STUDENT SERVICES REMODEL AND MEP, PH I | HH |  | 0 | 107.8 | 0 | 0 |  | 2570312 | 6873
2026-04-29 | WEST COAST CODE CONSULTANTS INC GAX300FC2026042869253 CONTRACT 2570312-WSU STUDENT SERVICES REMODEL AND MEP, PH I | HH |  | 0 | 312.2 | 0 | 0 |  | 2570312 | 6873
2026-04-29 | GSBS PC GAX300FC2026042869257 CONTRACT 2570138-WSU STUDENT SERVICES REMODEL AND MEP | HH |  | 0 | 40659.45 | 0 | 0 |  | 2570138 | 6861
2026-05-05 | WEBER STATE UNIVERSITY GAX300FC2026050469486 CONTRACT 2675057-INV 2675057-1-WSU STUDNT SRVCE REMODEL & MEP | HH |  | 0 | 754372.9 | 0 | 0 |  | 2675057 | 6832
2026-05-12 | WEBER STATE UNIVERSITY GAX300FC2026051169814 CONTRACT 2675057-INV 2675057-1-WSU STUDNT SRVCE REMODEL & MEP | HH |  | 0 | 505627.1 | 0 | 0 |  | 2675057 | 6832
2026-04-28 12:26 | WEST COAST CODE CONSULTANTS INC AMD 001 | CO |  | 0 |  | -40481.2 | 0 |  | 2570312
2026-05-27 | IDT30026000000057 AIM Transaction 24 - Transfer from project 25418810 to project 27013810 | HH | -1213831.7 | -1213831.7 |  | 0 | -1213831.7 |  |  | 4663
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 25418810
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency