## PROJECT
RESERVES:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR
| FUNDING | [5 empty] | DESIGN
| STATE RISK NUMBER |  | 04018 |  |  |  | INSPECTION
| PROJECT TITLE |  | WSU - ALLIED HEALTH SOUTH BUILDING MEP UPGRADE |  |  |  | INSURANCE
| PROJECT # |  | 26310810 | OPEN |  |  | CONTINGENCY/LEGAL
| CODING BLOCK |  | 3000-300-3349-FWBAA-26310810 |  |  | 1903947.45 | TOTAL | 0
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
2540875.41
YR | CURRENT TOTALS |  | 4679000 | 2138124.59 | 2540875.41 | 4444822.86 | 234177.14 | 0 |  |  | 0 | 0
[11 empty] | 2540875.41 | 0
|  |  |  | 0 |  | 0 | 0
FY'26 |  |  |  | 0 |  | 0 | 0
2025-09-09 | IDT30026C30000012 2025 GS SB 2 ITEM 148 FY 26 CAPITAL DEVELOPMENT - HIGHER ED FUND | HH | 4679000 | 4679000 |  | 0 | 4679000 |  |  | 4667
2025-11-20 | Salmon Mechanical LLC CONTRACT | CO |  | 0 |  | 2351737 | 0 |  | 2675207
2026-01-15 | IDT30026C30000047 LEGAL FEES FROM 26310810 TO 21257300 FY26 Q2 BILLINGS | HH |  | 0 | 3000 | 3000 | 0 |  |  | 6138
2026-02-11 | WEBER STATE UNIVERSITY GAX300FC2026021065906 CONTRACT 2675298-WSU ALLIED HEALTH SOUTH MEP | HH |  | 0 | 11027 | 0 | 0 |  | 2675298 | 6188
2026-02-07 | Salmon Mechanical LLC GAX300FC2026020665771 CONTRACT 2675207-PAY APP #1-WSU ALLIED HEALTH SOUTH MEP UPGRADE | HH |  | 0 | 27926.44 | 0 | 0 |  | 2675207 | 6813
2026-02-07 | Salmon Mechanical LLC GAX300FC2026020665772 CONTRACT 2675207-PAY APP #1-WSU ALLIED HEALTH SOUTH MEP UPGRADE | HH |  | 0 | 1469.81 | 0 | 0 |  | 2675207 | 6813
2026-02-12 | WEST COAST CODE CONSULTANTS INC CONTRACT | CO |  | 0 |  | 30000 | 0 |  | 2670327
2026-02-04 | WEBER STATE UNIVERSITY CONTRACT | CO |  | 0 |  | 1000000 | 0 |  | 2675298
2026-03-03 | Salmon Mechanical LLC GAX300FC2026030266662 CONTRACT 2675207-PAY APP #2-WSU ALLIED HEALTH SOUTH MEP UPGRADE | HH |  | 0 | 6762.34 | 0 | 0 |  | 2675207 | 6813
2026-03-03 | Salmon Mechanical LLC GAX300FC2026030266663 CONTRACT 2675207-PAY APP #2-WSU ALLIED HEALTH SOUTH MEP UPGRADE | HH |  | 0 | 355.91 | 0 | 0 |  | 2675207 | 6813
2026-03-19 | UTAH STATE FIRE MARSHAL'S OFFICE GAX30026C2000162 GENERAL BUILDING FIRE PLANS -26-097-02.05.2026 | HH |  | 0 | 75 | 75 | 0 |  |  | 6873
2026-03-19 | IDT30026C30000012 2025 GS SB 2 ITEM 148 FY 26 CAPITAL DEVELOPMENT - HIGHER ED FUND | HH | 4679000 | 4679000 |  | 0 | 4679000 |  |  | 4667
2026-03-19 | IDT30026C30000012 2025 GS SB 2 ITEM 148 FY 26 CAPITAL DEVELOPMENT - HIGHER ED FUND | HH | -4679000 | -4679000 |  | 0 | -4679000 |  |  | 4667
2026-04-17 | Salmon Mechanical LLC GAX300FC2026041668850 CONTRACT 2675207-PAY APP #3-WSU ALLIED HEALTH SOUTH MEP UPGRADE | HH |  | 0 | 2033.3 | 0 | 0 |  | 2675207 | 6813
2026-04-17 | Salmon Mechanical LLC GAX300FC2026041668849 CONTRACT 2675207-PAY APP #3-WSU ALLIED HEALTH SOUTH MEP UPGRADE | HH |  | 0 | 38632.65 | 0 | 0 |  | 2675207 | 6813
2026-04-22 | WEST COAST CODE CONSULTANTS INC GAX30026C2000179 Plan Review Services 02/25/2026-1st Review | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2026-05-05 | Salmon Mechanical LLC GAX300FC2026050469512 CONTRACT 2675207-PAY APP #4-WSU ALLIED HEALTH SOUTH MEP UPGRADE | HH |  | 0 | 59390.94 | 0 | 0 |  | 2675207 | 6813
2026-05-05 | Salmon Mechanical LLC GAX300FC2026050469513 CONTRACT 2675207-PAY APP #4-WSU ALLIED HEALTH SOUTH MEP UPGRADE | HH |  | 0 | 3125.84 | 0 | 0 |  | 2675207 | 6813
2026-05-16 | WEST COAST CODE CONSULTANTS INC GAX30026C5000104 Plan Review Services 03/11/2026-1ST REVIEW | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2026-06-03 | Salmon Mechanical LLC GAX300FC2026060270813 CONTRACT 2675207-PAY APP #5-WSU ALLIED HEALTH SOUTH MEP UPGRADE | HH |  | 0 | 552053.07 | 0 | 0 |  | 2675207 | 6813
2026-06-03 | Salmon Mechanical LLC GAX300FC2026060270814 CONTRACT 2675207-PAY APP #5-WSU ALLIED HEALTH SOUTH MEP UPGRADE | HH |  | 0 | 29055.42 | 0 | 0 |  | 2675207 | 6813
2026-06-12 | WEBER STATE UNIVERSITY GAX300FC2026061171260 CONTRACT 2675298-WSU ALLIED HEALTH SOUTH MEP | HH |  | 0 | 365994.93 | 0 | 0 |  | 2675298 | 6188
2026-07-03 | Salmon Mechanical LLC GAX300FC2026070272387 CONTRACT 2675207-PAY APP #6-WSU ALLIED HEALTH SOUTH MEP UPGRADE | HH |  | 0 | 32973.58 | 0 | 0 |  | 2675207 | 6813
2026-07-03 | Salmon Mechanical LLC GAX300FC2026070272386 CONTRACT 2675207-PAY APP #6-WSU ALLIED HEALTH SOUTH MEP UPGRADE | HH |  | 0 | 626498.02 | 0 | 0 |  | 2675207 | 6813
2026-07-10 | WEBER STATE UNIVERSITY GAX300FC2026070972754 CONTRACT 2675298-WSU ALLIED HEALTH SOUTH MEP | HH |  | 0 | 30563.32 | 0 | 0 |  | 2675298 | 6188
2026-06-12 12:00 | Salmon Mechanical LLC CO 001 | CO |  | 0 |  | 310073.02 | 0 |  | 2675207
|  |  |  | 0 |  | 0 | 0
FY'27 |  |  |  | 0 |  | 0 | 0
2026-08-04 | Salmon Mechanical LLC GAX300FC2026080373591 CONTRACT 2675207-PAY APP #7-WSU ALLIED HEALTH SOUTH MEP UPGRADE |  |  | 0 | 712203.45 | 712203.45 | 0 |  |  | 6813
2026-08-04 | Salmon Mechanical LLC GAX300FC2026080373592 CONTRACT 2675207-PAY APP #7-WSU ALLIED HEALTH SOUTH MEP UPGRADE |  |  | 0 | 37484.39 | 37484.39 | 0 |  |  | 6813
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 26310810
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency