## PROJECT
RESERVES:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR
| FUNDING |  | WILDLIFE RESOURCES |  |  |  | DESIGN
| STATE RISK NUMBER | [5 empty] | INSPECTION
| PROJECT TITLE |  | DWR LOGAN NEW WARM WATER AQUACULTURE HATCHERY BUILDING |  |  |  | INSURANCE
| PROJECT # |  | 20467520 | OPEN |  |  | CONTINGENCY/LEGAL
| CODING BLOCK |  | 3000-300-3502-FWAAA-20467520 |  |  | 72101.27 | TOTAL | 0
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
YR | CURRENT TOTALS |  | 9710900.91 | 951195.27 | 8759705.64 | 8831806.91 | 879094 | 0 |  |  | 0 | 0
[11 empty] | 0 | 0
1000-560-56049-RFH-7520-XEFM-E4D570XXX
1000-560-5049-RFH-7520-XEFM-E0FMSL16-E1B670XXX
|  |  |  | 0 |  | 0 | 0
FY'20 |  |  |  | 0 |  | 0 | 0
13/20 | ITA 560 20*1799 | PG | 74483.33 | 74483.33 |  | 0 | 74483.33 |  |  | 4737
13/20 | ITA 560 20*1813 E4P74OXXX | NP | 240800 | 240800 |  | 0 | 240800 |  |  | 4737
13/20 | ITA 560 20*1826 E1B670XXX | NP | 260000 | 260000 |  | 0 | 260000 |  |  | 4737
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'21 |  |  |  | 0 |  | 0 | 0
2020-11-03 | ITA 560 21*370 REV FROM DWR E0FMSL16 E4Q040XXX | DF | 2000000 | 2000000 |  | 0 | 2000000 |  |  | 4737
13/21 | ITA 560 21*1520 | NP | 100000 | 100000 |  | 0 | 100000 |  |  | 4737
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'22 |  |  |  | 0 |  | 0 | 0
13/22 | ITA 560 22*1627 PER Chris Vanheusen | NP | 1800000 | 1800000 |  | 0 | 1800000 |  |  | 4737
13/22 | ITA 560 22*1635 per Chris Vanheusen | NP | 203000 | 203000 |  | 0 | 203000 |  |  | 4737
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'23 |  |  |  | 0 |  | 0 | 0
2022-09-01 | IDT TRNSF DWR FUNDS FROM 22374520 TO CLOSE THAT PROJECT | DF | 107102.94 | 107102.94 |  | 0 | 107102.94 |  |  | 4737
2022-12-14 | ITA 560 23*735 PER Chris Vanheusen | DF | 3000000 | 3000000 |  | 0 | 3000000 |  |  | 4737
2023-01-18 | FORSGREN ASSOCIATES INC - CONTRACT | N/A |  | 0 |  | 667400 | 0 |  | 2370233
2023-02-15 | FORSGREN ASSOCIATES INC-GAX FC2023021515133 | DF |  | 0 | 892.5 | 0 | 0 |  | 2370233 | 6861
2023-03-15 | DWA CONSTRUCTION INC. GAX FC2023031516230 | DF |  | 0 | 10282.65 | 10282.65 | 0 |  |  | 6811
2023-03-22 | DWA CONSTRUCTION INC. GAX FC2023031516230 | DF |  | 0 | -10282.65 | -10282.65 | 0 |  |  | 6811
2023-05-18 | FORSGREN ASSOC GAX FC2023051819137 | DF |  | 0 | 79481.25 | 0 | 0 |  | 2370233 | 6861
2023-05-30 | FORSGREN ASSOC GAX FC2023053019489 | DF |  | 0 | 55228.11 | 0 | 0 |  | 2370233 | 6861
2023-05-30 | ZIONS/FORSGREN RTNG GAX FC2023053019490 | DF |  | 0 | 7557.5 | 0 | 0 |  | 2370233 | 6861
2023-06-29 | ITA 560 23* 1967 | DF | 270000 | 270000 |  | 0 | 270000 |  |  | 4737
2023-06-29 | ITA 560 23*1968 | DF | 100000 | 100000 |  | 0 | 100000 |  |  | 4737
2023-06-29 | ITA 560 23*1969 | DF | 87615 | 87615 |  | 0 | 87615 |  |  | 4737
13/23 | ITA 560 23*2290 PER CHRIS V. | DF | 400000 | 400000 |  | 0 | 400000 |  |  | 4737
13/23 | ITA 560 23*2310 PER CHRIS V. | DF | 100000 | 100000 |  | 0 | 100000 |  |  | 4737
13/23 | FORSGREN ASSOC GAX FC2023072823027 | DF |  | 0 | 113530.68 | 0 | 0 |  | 2370233 | 6861
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'24 |  |  |  | 0 |  | 0 | 0
2023-08-15 | FORSGREN ASSOC GAX FC2023081523645 | DF |  | 0 | 88535.02 | 0 | 0 |  | 2370233 | 6861
2023-08-18 | FORSGREN ASSOC GAX F23*074 | DF |  | 0 | 39589.97 | 0 | 0 |  | 2370233 | 6861
2023-09-18 | FORSGREN ASSOC GAX FC2023091825137 | DF |  | 0 | 119941.98 | 0 | 0 |  | 2370233 | 6861
2023-10-13 | FORSGREN ASSOC GAX FC2023101326325 | DF |  | 0 | 25556.24 | 0 | 0 |  | 2370233 | 6861
2023-11-21 | FORSGREN ASSOC GAX FC2023112127972 | DF |  | 0 | 13651.75 | 0 | 0 |  | 2370233 | 6861
2023-12-20 | WC3 PLAN REVIEW SVCS NOV 2023 PHONE CALLS | DF |  | 0 | 125 | 125 | 0 |  |  | 6861
2023-12-20 | WC3 PLAN REVIEW SVCS NOV 2023 1ST REVIEW | DF |  | 0 | 875 | 875 | 0 |  |  | 6861
2023-12-20 | WC3 PLAN REVIEW SVCS NOV 2023 2ND REVIEW | DF |  | 0 | 375 | 375 | 0 |  |  | 6861
2024-01-02 | UT ST FIRE MARSHAL GAX 24C5*155 | DF |  | 0 | 215.6 | 215.6 | 0 |  |  | 6861
2024-01-04 | FORSGREN ASSOC GAX FC2024010429802 | DF |  | 0 | 8967.5 | 0 | 0 |  | 2370233 | 6861
2024-01-10 | FORSGREN ASSOC GAX FC2024011030206 | DF |  | 0 | 2617.72 | 0 | 0 |  | 2370233 | 6861
2024-01-17 | WC3 PLAN REVIEW 12.12.23 GAX 24C5*168 | DF |  | 0 | 125 | 125 | 0 |  |  | 6861
2024-01-24 | DWA CONSTRUCTION INC - CONTRACT | N/A |  | 0 |  | 6849176.1 | 0 |  | 2475263
2024-02-09 | FORSGREN ASSOC GAX FC2024020931666 | DF |  | 0 | 2393.78 | 0 | 0 |  | 2370233 | 6861
2024-02-29 | DFCM MGMT FEES TO 24425300 FROM 20467520 | DF | -49107 | -49107 |  | 0 | -49107 |  |  | 6865
2024-03-07 | ITA 24*083 DFCM COFC INS JAN 1 - JAN 31 2024 | DF |  | 0 | 6849.18 | 6849.18 | 0 |  |  | 6872
2024-03-13 | ITA 24*085 | DF |  | 0 | 6849.18 | 6849.18 | 0 |  |  | 6872
2024-03-20 | FORSGREN ASSOC GAX FC202403203346 | DF |  | 0 | 4898.75 | 0 | 0 |  | 2370233 | 6861
2024-03-24 | TRNSF TO 21257300 FROM 20467520 LEGAL FEES | DF |  | 0 | 3711 | 3711 | 0 |  |  | 6870
2024-03-29 | OCEANS DESIGN GAX FC2024032933900 | DF |  | 0 | 283955 | 283955 | 0 |  |  | 6811
2024-04-09 | FORSGREN ASSOC GAX FC2024040934491 | DF |  | 0 | 12336.25 | 0 | 0 |  | 2370233 | 6861
2024-03-27 | FORSGREN ASSOC AMD 001 | CO |  | 0 |  | 18400 | 0 |  | 2370233
2024-04-30 | TRNSF TO 20467520 FROM 24278520 PER ROGER MELLENTHIN | DF | 12593 | 12593 |  | 0 | 12593 |  |  | 4737
2024-04-30 | TRNSF TO 20467520 FROM 20324520 PER ROGER MELLENTHIN | DF | 37685.56 | 37685.56 |  | 0 | 37685.56 |  |  | 4737
2024-05-06 | DWA CONST GAX FC2024050635753 | DF |  | 0 | 544464.95 | 0 | 0 |  | 2475263 | 6811
2024-05-06 | ZIONS/DWA RTNG GAX FC2024050635754 | DF |  | 0 | 28656.05 | 0 | 0 |  | 2475263 | 6811
2024-05-15 | FORSGREN ASSOC GAX FC2024051536189 | DF |  | 0 | 11410 | 0 | 0 |  | 2370233 | 6861
2024-05-20 | UTAH TESING AND ENGINEERING LLC - CONTRACT | N/A |  | 0 |  | 42901.28 | 0 |  | 2470559
2024-05-20 | WC3 PLAN REVIEW GAX 24C5*283 | DF |  | 0 | 125 | 125 | 0 |  |  | 6861
2024-06-04 | LOGAN CITY GAX FC2024060437109 | DF |  | 0 | 30901 | 30901 | 0 |  |  | 6811
2024-06-27 | DWA CONST GAX300FC2024062538523 |  |  | 0 | 400855.35 | 0 | 0 |  | 2475263 | 6811
2024-06-27 | ZIONS/DWA RTNG GAX300FC2024062538524 |  |  | 0 | 21097.65 | 0 | 0 |  | 2475263 | 6811
13/24 | ITA 560 24*3006 |  | 232872 | 232872 |  | 0 | 232872 |  |  | 4737
13/24 | ITA 560 24* 3007 |  | 720184 | 720184 |  | 0 | 720184 |  |  | 4737
13/24 | UT TEST & ENG GAX FC2024070239055 |  |  | 0 | 1098.72 | 1098.72 | 0 |  |  | 6873
13/24 | UT TEST & ENG GAX FC2024070239140 |  |  | 0 | 969.72 | 0 | 0 |  | 2470559 | 6873
13/24 | DWA CONST GAX FC2024071640017 |  |  | 0 | 790419 | 0 | 0 |  | 2475263 | 6811
13/24 | ZIONS/DWA RTNG GAX FC202401640018 |  |  | 0 | 41601 | 6811 | 0 |  | 2475263 | 6811
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'25 |  |  |  | 0 |  | 0 | 0
2024-08-20 | FORSGREN ASSOC GAX F24*082 | DF |  | 0 | 9491.25 | 0 | 0 |  | 2370233 | 6861
2024-08-20 | DWA CONST GAX FC2024082041327 | DF |  | 0 | 710150.65 | 0 | 0 |  | 2475263 | 6811
2024-08-20 | ZIONS/DWA RTNG GAX FC2024082041328 | DF |  | 0 | 37376.35 | 0 | 0 |  | 2475263 | 6811
2024-08-23 | FORSGREN ASSOC GAX FC2024082341510 | DF |  | 0 | 2692.5 | 0 | 0 |  | 2370233 | 6861
2024-08-28 | FORSGREN ASSOC GAX F24*087 | DF |  | 0 | 21102.95 | 0 | 0 |  | 2370233 | 6861
2024-09-09 | UT TEST & ENG GAX FC2024090842095 | DF |  | 0 | 398.88 | 0 | 0 |  | 2470559 | 6873 |  | ADD TO AUG IDT TO CORR UNIT FROM 3501
2024-09-16 | FORSGREN ASSOC GAX FC2024091642556 | DF |  | 0 | 6187.01 | 0 | 0 |  | 2370233 | 6861
2024-09-17 | DWA CONST GAX FC2024091742640 | DF |  | 0 | 344819.6 | 0 | 0 |  | 2475263 | 6811
2024-09-17 | ZIONS/DWA RTNG GAX FC2024091742641 | DF |  | 0 | 18148.4 | 0 | 0 |  | 2475263 | 6811
2024-09-27 | UT TESTING GAX FC2024092743152 | DF |  | 0 | 148.96 | 0 | 0 |  | 2470559 | 6873
2024-10-02 | BIOMARK GAX FC2024100243425 | DF |  | 0 | 10000 | 10000 | 0 |  |  | 6811
2024-11-06 | DWA CONST GAX FC2024110645052 | DF |  | 0 | 411053.6 | 0 | 0 |  | 2475263 | 6811
2024-11-06 | ZIONS/DWA RTNG GAX FC2024110645053 | DF |  | 0 | 21634.4 | 0 | 0 |  | 2475263 | 6811
2024-10-28 | FORSGREN ASSOC AMD 002 | CO |  | 0 |  | 8925 | 0 |  | 2370233
2024-11-13 | FORSGREN ASSOC GAX FC2024111345337 | DF |  | 0 | 9552 | 0 | 0 |  | 2370233 | 6861
2024-11-15 | FORSGREN ASSOC GAX FC2024111545444 | DF |  | 0 | 7188.75 | 0 | 0 |  | 2370233 | 6861
2024-11-18 | DWA CONST CO 001 | CO |  | 0 |  | 105612.43 | 0 |  | 2475263
2024-11-25 | DWA CONST GAX FC2024112145707 | DF |  | 0 | 399499.7 | 0 | 0 |  | 2475263 | 6811
2024-11-25 | ZIONS/DWA RTNG GAX FC2024112145708 | DF |  | 0 | 21026.3 | 0 | 0 |  | 2475263 | 6811
2024-12-09 | UT TEST GAX FC2024120946474 | EH |  | 0 | 1610.6 | 0 | 0 |  | 2470559 | 6873
2024-12-18 | FORSGREN ASSOC GAX FC2024121846897 | EH |  | 0 | 5122.5 | 0 | 0 |  | 2370233 | 6861
2024-12-19 | DWA CONST GAX FC2024121947024 | EH |  | 0 | 304856.61 | 0 | 0 |  | 2475263 | 6811
2024-12-19 | ZIONS/DWA RTNG GAX FC2024121947025 | EH |  | 0 | 16045.09 | 0 | 0 |  | 2475263 | 6811
2025-01-10 | INTEGRATED AQUA SYSTEMS GAX300FC2025011047862 | EH |  | 0 | 99336 | 99336 | 0 |  |  | 6811
2025-01-16 | FORSGREN ASSOC GAX300FC2025011648228 | EH |  | 0 | 4280 | 0 | 0 |  | 2370233 | 6861
2025-01-21 | DWA CONST GAX300FC202501248397 | EH |  | 0 | 238153.63 | 0 | 0 |  | 2475263 | 6811
2025-01-21 | ZIONS/DWA CONST RTNG GAX300FC202501248398 | EH |  | 0 | 12534.4 | 0 | 0 |  | 2475263 | 6811
2025-01-30 | UT TEST GAX FC2025012948854 | EH |  | 0 | 2065.06 | 0 | 0 |  | 2470559 | 6873
2025-02-07 | UTAH TESTING & ENG GAX300FC2025020749301 | HH |  | 0 | 1521.52 | 0 | 0 |  | 2470559 | 6873
2025-03-05 | DWA CONST GAX300FC2025030550439 | HH |  | 0 | 465919.47 | 0 | 0 |  | 2475263 | 6811
2025-03-05 | DWA CONST GAX300FC2025030550440 | HH |  | 0 | 24522.08 | 0 | 0 |  | 2475263 | 6811
2025-02-03 | DWA CONST CO 002 | CO |  | 0 |  | 66398.31 | 0 |  | 2475263
2025-02-21 | FORSGREN ASSOC AMD 003 | CO |  | 0 |  | 50298 | 0 |  | 2370233
2025-04-08 | UTAH TESTING AND ENGINEERING LLC GAX300FC2025040851993 | HH |  | 0 | 897.8 | 0 | 0 |  | 2470559 | 6873
2025-04-17 | DWA Construction Inc GAX300FC2025041752503 | HH |  | 0 | 581749.65 | 0 | 0 |  | 2475263 | 6811
2025-04-17 | DWA Construction Inc GAX300FC2025041752504 | HH |  | 0 | 30618.4 | 0 | 0 |  | 2475263 | 6811
2025-04-17 | DWA Construction Inc GAX300FC2025041752505 | HH |  | 0 | 525487.32 | 0 | 0 |  | 2475263 | 6811
2025-04-17 | DWA Construction Inc GAX300FC2025041752506 | HH |  | 0 | 27657.23 | 0 | 0 |  | 2475263 | 6811
2025-05-13 | DWA Construction Inc GAX300FC2025051353730 | HH |  | 0 | 232596.1 | 0 | 0 |  | 2475263 | 6811
2025-05-13 | DWA Construction Inc GAX300FC2025051353731 | HH |  | 0 | 12241.9 | 0 | 0 |  | 2475263 | 6811
2025-05-23 | UTAH TESTING AND ENGINEERING LLC GAX300FC2025052254141 CONTRACT 2470559-WARM WATER AQUACULTURE BUILDING | HH |  | 0 | 1621.6 | 0 | 0 |  | 2470559 | 6873
2025-06-10 | UTAH TESTING AND ENGINEERING LLC GAX300FC2025060954933 CONTRACT 2470559-WARM WATER AQUACULTURE BUILDING | HH |  | 0 | 73.96 | 0 | 0 |  | 2470559 | 6873
2025-06-24 | DWA CONST CO 003 | CO |  | 0 |  | 45344.51 | 0 |  | 2475263
13/25 | UTAH TESTING AND ENGINEERING LLC GAX300FC2025070456400 CONTRACT 2470559-WARM WATER AQUACULTURE BUILDING | HH |  | 0 | 1179.18 | 0 | 0 |  | 2470559 | 6873
13/25 | FORSGREN ASSOCIATES INC GAX300FC2025071557040 CONTRACT 2370233-DWR LOGAN WARM WATER AQUACULTURE HATCHRY | HH |  | 0 | 3995 | 0 | 0 |  | 2370233 | 6861
13/25 | FORSGREN ASSOCIATES INC GAX300FC2025071557041 CONTRACT 2370233-DWR LOGAN WARM WATER AQUACULTURE HATCHRY | HH |  | 0 | 2962.24 | 0 | 0 |  | 2370233 | 6861
13/25 | FORSGREN ASSOCIATES INC GAX300FC2025071557042 CONTRACT 2370233-DWR LOGAN WARM WATER AQUACULTURE HATCHRY | HH |  | 0 | 19609.25 | 0 | 0 |  | 2370233 | 6861
13/25 | FORSGREN ASSOCIATES INC GAX300FC2025071557043 CONTRACT 2370233-DWR LOGAN WARM WATER AQUACULTURE HATCHRY | HH |  | 0 | 14139.55 | 0 | 0 |  | 2370233 | 6861
13/25 | FORSGREN ASSOCIATES INC GAX300FC2025071557044 CONTRACT 2370233-DWR LOGAN WARM WATER AQUACULTURE HATCHRY | HH |  | 0 | 14267.5 | 0 | 0 |  | 2370233 | 6861
13/25 | TRNSF TO 20467520 FROM 25386520 EXCESS CLOSE FOR CONSTRUCTION | HH | 13672.08 | 13672.08 |  | 0 | 13672.08 |  |  | 4737
13/25 | DWA Construction Inc GAX300FC2025071657083 CONTRACT 2475263-PAY APP #14-LOGAN WARM WATER AQUACULTURE HATCHERY BLDG | HH |  | 0 | 313079.84 | 0 | 0 |  | 2475263 | 6811
13/25 | DWA Construction Inc GAX300FC2025071657084 CONTRACT 2475263-PAY APP #14-LOGAN WARM WATER AQUACULTURE HATCHERY BLDG | HH |  | 0 | 16477.89 | 0 | 0 |  | 2475263 | 6811
13/25 | DWA Construction Inc GAX300FC2025071657085 CONTRACT 2475263-PAY APP #15-LOGAN WARM WATER AQUACULTURE HATCHERY BLDG | HH |  | 0 | 93283.9 | 0 | 0 |  | 2475263 | 6811
13/25 | DWA Construction Inc GAX300FC2025071657086 CONTRACT 2475263-PAY APP #15-LOGAN WARM WATER AQUACULTURE HATCHERY BLDG | HH |  | 0 | 4909.68 | 0 | 0 |  | 2475263 | 6811
13/25 | Oceans Design Inc GAX300FC2025072857367 PO237721 DWR WARM WATER AQUACULTURE BLDG SELF-CLEANING TANKS | HH |  | 0 | 283955 | 283955 | 0 |  |  | 6811
13/25 | Roger R. Warren GAX300FC2025072957449 PO237904 DWR WARM WTR AQUACULTURE HATCHERY BLG WATER SPIKES | HH |  | 0 | 10800 | 10800 | 0 |  |  | 6811
|  |  |  | 0 |  | 0 | 0
FY'26 |  |  |  | 0 |  | 0 | 0
2025-07-17 13:43 | DWA CONST CO 004 | CO |  | 0 |  | 66479.1 | 0 |  | 2475263
2025-09-27 | UTAH TESTING AND ENGINEERING LLC GAX300FC2025092659973 CONTRACT 2470559-WARM WATER AQUACULTURE BUILDING | HH |  | 0 | 60.6 | 0 | 0 |  | 2470559 | 6873
2025-09-27 | UTAH TESTING AND ENGINEERING LLC GAX300FC2025092659974 CONTRACT 2470559-WARM WATER AQUACULTURE BUILDING | HH |  | 0 | 3167.86 | 0 | 0 |  | 2470559 | 6873
2025-09-27 | UTAH TESTING AND ENGINEERING LLC GAX300FC2025092659975 CONTRACT 2470559-WARM WATER AQUACULTURE BUILDING | HH |  | 0 | 499.3 | 0 | 0 |  | 2470559 | 6873
2025-10-03 | DWA Construction Inc GAX300FC2025100260291 CONTRACT 2475263-PAY APP #16-LOGAN WARM WATER AQUACULTURE HATCHERY BLDG | HH |  | 0 | 152951.63 | 0 | 0 |  | 2475263 | 6811
2025-10-03 | DWA Construction Inc GAX300FC2025100260292 CONTRACT 2475263-PAY APP #16-LOGAN WARM WATER AQUACULTURE HATCHERY BLDG | HH |  | 0 | 8050.09 | 0 | 0 |  | 2475263 | 6811
2025-10-03 | DWA Construction Inc GAX300FC2025100260293 CONTRACT 2475263-PAY APP #17-LOGAN WARM WATER AQUACULTURE HATCHERY BLDG | HH |  | 0 | 156591.39 | 0 | 0 |  | 2475263 | 6811
2025-10-03 | DWA Construction Inc GAX300FC2025100260294 CONTRACT 2475263-PAY APP #17-LOGAN WARM WATER AQUACULTURE HATCHERY BLDG | HH |  | 0 | 8241.65 | 0 | 0 |  | 2475263 | 6811
2025-10-29 | Integrated Aqua Systems GAX300FC2025102861302 PO 240364 - LOGAN FISH HATCHERY | HH |  | 0 | 2092 | 2092 | 0 |  |  | 6811
2026-12-23 | FORSGREN ASSOC AMD 004 | CO |  | 0 |  | 0 | 0 |  | 2370233
2026-01-21 | FORSGREN ASSOCIATES INC GAX300FC2026012064675 CONTRACT 2370233-DWR LOGAN WARM WATER AQUACULTURE HATCHRY | HH |  | 0 | 33074.97 | 0 | 0 |  | 2370233 | 6861
2026-01-16 | DWA CONST CO 005 | CO |  | 0 |  | 162673.5 | 0 |  | 2475263
2026-02-21 | FORSGREN ASSOCIATES INC GAX300FC2026022066321 CONTRACT 2370233-DWR LOGAN WARM WATER AQUACULTURE HATCHRY | HH |  | 0 | 5162.5 | 0 | 0 |  | 2370233 | 6861
2026-02-24 | DWA Construction Inc GAX300FC2026022366396 CONTRACT 2475263-PAY APP #18-LOGAN WARM WATER AQUACULTURE HATCHERY BLDG | HH |  | 0 | 210324.65 | 0 | 0 |  | 2475263 | 6811
2026-02-24 | DWA Construction Inc GAX300FC2026022366397 CONTRACT 2475263-PAY APP #18-LOGAN WARM WATER AQUACULTURE HATCHERY BLDG | HH |  | 0 | 11069.72 | 0 | 0 |  | 2475263 | 6811
2026-03-12 | FORSGREN ASSOCIATES INC GAX300FC2026031167278 CONTRACT 2370233-DWR LOGAN WARM WATER AQUACULTURE HATCHRY | HH |  | 0 | 8555 | 0 | 0 |  | 2370233 | 6861
2026-04-10 | FORSGREN ASSOCIATES INC GAX300FC2026040968416 CONTRACT 2370233-DWR LOGAN WARM WATER AQUACULTURE HATCHRY | HH |  | 0 | 3330 | 0 | 0 |  | 2370233 | 6861
2026-05-05 | DWA Construction Inc GAX300FC2026050469528 CONTRACT 2475263-PAY APP #19-LOGAN WARM WATER AQUACULTURE HATCHERY BLDG | HH |  | 0 | 8203.85 | 0 | 0 |  | 2475263 | 6811
2026-05-05 | DWA Construction Inc GAX300FC2026050469529 CONTRACT 2475263-PAY APP #19-LOGAN WARM WATER AQUACULTURE HATCHERY BLDG | HH |  | 0 | 431.78 | 0 | 0 |  | 2475263 | 6811
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 20467520
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency