## PROJECT
RESERVES:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR | 0
| FUNDING |  | GFFY2022 |  |  |  | DESIGN/OTHER COSTS | 0
| STATE RISK NUMBER |  | 00610,00611 |  |  |  | INSPECTION | 0
| PROJECT TITLE |  | DNR DWR SPRINGVILLE CRO/SV HATCHERY MAINTENANCE AND STORAGE SHOP |  |  |  | INSURANCE | 25.38
| PROJECT # |  | 22035520 | CLOSED
| CODING BLOCK |  | 3000-300-3345-FXA-22035520 |  |  | 0 | TOTAL | 25.38
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
YR | CURRENT TOTALS |  | 2156059.85 | 18.39 | 2156041.46 | 2156041.46 | 18.39 | 0 |  |  | 0 | 0
[11 empty] | 0 | 0
| 1000-560-5015-RFB-7520-XEAD-E4X477000 |  |  | 0 |  | 0 | 0
FY'21 |  |  |  | 0 |  | 0 | 0
2021-05-04 | ARCHITECTURAL NEXUS, INC. - CONTRACT | N/A |  | 0 |  | 77400 | 0 |  | 2171174
2021-06-20 | ARCHITECTURAL NEXUS GAX 21C9*376 | NP |  | 0 | 29992.5 | 0 | 0 |  | 2171174 | 6861
2021-06-10 | ARCHITECTURAL NEXUS GAX 21C9*377 | NP |  | 0 | 8707.5 | 0 | 0 |  | 2171174 | 6861
2021-06-10 | MERIDIAN ENG GAX 21C9*411 | NP |  | 0 | 2295 | 2295 | 0 |  |  | 6861
2021-06-17 | EARTH TECH GAX 219*467 | NP |  | 0 | 2200 | 2200 | 0 |  |  | 6861
2021-06-22 | ARCHITECTURAL NEXUS AMD 001 | CO |  | 0 |  | 8702.68 | 0 |  | 2171174
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'22 |  |  |  | 0 |  | 0 | 0
2021-08-17 | ARCHITECTURAL NEXUS GAX 22C9*124 | DF |  | 0 | 20312.68 | 0 | 0 |  | 2171174 | 6861
2021-08-30 | ARCHITECTURRAL NEXUS AMD 002 | CO |  | 0 |  | 1749 | 0 |  | 2171174
2021-09-01 | IET TRNSF FY'22 CAP IMPR FUNDS FROM 22397300 | DF | 1200000 | 1200000 |  | 0 | 1200000 |  |  | 4667
2021-09-01 | IET TRNSF BUDGETED CONTINGENCY TO 21138300 | DF | -87500 | -87500 |  | 0 | -87500 |  |  | 4663
2021-09-01 | IET TRNSF LEGAL BUDGET TO 21257300 | DF |  | 0 | 1000 | 1000 | 0 |  |  | 6138
2021-09-27 | ARCHITECTURAL NEXUS GAX FC21*4105 | DF |  | 0 | 9489 | 0 | 0 |  | 2171174 | 6861
2021-10-14 | ARCHI NEXUS GAX FC20211014739 | DF |  | 0 | 1122.3 | 0 | 0 |  | 2171174 | 6861
2021-10-19 | EARTH TECH GAX FC20211018769 | DF |  | 0 | 150 | 150 | 0 |  |  | 6861
2021-10-19 | WC3 GAX 22C5*236 | DF |  | 0 | 330 | 330 | 0 |  |  | 6861
2021-12-07 | UT ST FIRE MRSHL GAX 22C5*269 | DF |  |  | 155.21 | 155.21 | 0 |  |  | 6861
2021-12-20 | WC3 GAX 22C5*281 | DF |  | 0 | 110 | 110 | 0 |  |  | 6861
2022-01-11 | ARCHI NEXUS GAX FC202201112440 | DF |  | 0 | 619.2 | 0 | 0 |  | 2171174 | 6861
2022-01-13 | ARCHI NEXUS GAX FC202201132479 | DF |  | 0 | 967.5 | 0 | 0 |  | 2171174 | 6861
2022-01-21 | MERIDIAN ENG GAX FC202201212593 | DF |  | 0 | 255 | 255 | 0 |  |  | 6861
2022-02-01 | IET TRNSF FUNDS FROM PRJ RESERVE 21137300 FOR CONSTR CONTRACT AWARD SHARE | DF | 543274 | 543274 |  | 0 | 543274 |  |  | 4666
2022-02-16 | ITA 560 22*777 SHARE OF CONST CONT AWARD | DF | 300000 | 300000 |  | 0 | 300000 |  |  | 4737 | dnr funding $300,000 for constr contract
2022-02-15 | ARCHI NEXUS GAX FC202202153076 | DF |  | 0 | 1161 | 0 | 0 |  | 2171174 | 6861
2022-02-25 | PRT BUILDERS LLC - CONTRACT | N/A |  | 0 |  | 1843274 | 0 |  | 2275331
2022-03-01 | IET TRNSF FUNDS FROM CONTG RESERVE 21138300 FOR CO 001 AND DESIGN OVER BUDGET COSTS | DF | 36359.64 | 36359.64 |  | 0 | 36359.64 |  |  | 4664
2022-03-25 | PRT BUILDERS CO 001 | CO |  | 0 |  | 23492.75 | 0 |  | 2275331
2022-04-13 | ARCHITECTURAL NEXUS AX FC202204134179 | DF |  | 0 | 3096 | 0 | 0 |  | 2171174 | 6861
2022-04-13 | SPRINGVILLE CITY CORP GAX FC202204134156 | DF |  | 0 | 27139.36 | 27139.36 | 0 |  |  | 6811
2022-04-19 | ITA 22*072 COFC INSURANCE | DF |  | 0 | 1474.62 | 1474.62 | 0 |  |  | 6872
2022-04-29 | PRT BUILDERS GAX FC202204294539 | DF |  | 0 | 202865.61 | 0 | 0 |  | 2275331 | 6811
2022-04-29 | ZIONS/PRT BLDRS RTNG GAX FC202204294540 | DF |  |  | 10677.14 | 0 | 0 |  | 2275331 | 6811
2022-05-11 | ARCHITECUTURAL NEXUS GAX FC202205114920 | DF |  | 0 | 2476.8 | 0 | 0 |  | 2171174 | 6861
2022-05-18 | BGT PARTNERS GAX FC202205185103 | DF |  | 0 | 150 | 150 | 0 |  |  | 6861
2022-05-18 | IET TRNSF FUNDS FROM CONTG RESERVE 21138300 FOR CO 002 | DF | 100852.43 | 100852.43 |  | 0 | 100852.43 |  |  | 4664
2022-05-23 | PRT BUILDERS CO 002 | CO |  | 0 |  | 100852.43 | 0 |  | 2275331
2022-06-02 | PRT BUILDERS GAX FC202206025468 | NP |  | 0 | 114475 | 0 | 0 |  | 2275331 | 6811
2022-06-02 | ZIONS/PRT BUILDERS RTNG GAX FC202206025469 | NP |  | 0 | 6025 | 0 | 0 |  | 227331 | 6811
2022-06-02 | IET TRNSF FUNDS FROM CONTG RESERVE 21138300 FOR ADDITIONAL DESIGN FEES | NP | 12708 | 12708 |  | 0 | 12708 |  |  | 4664
2022-06-06 | SHUMS CODA ASSOC GAX FC202206065497 | NP |  | 0 | 853.66 | 853.66 | 0 |  |  | 6873
2022-06-09 | ARCHI NEXUS GAX FC202206095703 | NP |  | 0 | 2322 | 0 | 0 |  | 2171174 | 6861
2022-06-14 | ARCHITECTURAL NEXUS AMD 003 | CO |  | 0 |  | 12708 | 0 |  | 2171174
2022-06-28 | PRT BUILDERS GAX FC202206286292 | NP |  | 0 | 187625 | 0 | 0 |  | 2275331 | 6811
2022-06-28 | ZIONS/PRT RTNG GAX FC202206286293 | NP |  | 0 | 9875 | 0 | 0 |  | 2275331 | 6811
2022-06-28 | ARCHI NEXUS GAX FC202206286269 | NP |  | 0 | 5263.2 | 0 | 0 |  | 2171174 | 6861
13/22 | UT ST FIRE MARSHAL GAX 22C5*491 | NP |  | 0 | 155.21 | 155.21 | 0 |  |  | 6861
13/22 | SHUMS CODA GAX 22C9*805 | NP |  | 0 | 2191.24 | 2191.24 | 0 |  |  | 6873
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'23 |  |  |  | 0 |  | 0 | 0
2022-08-01 | PRT BUILDERS GAX FC02208016582 | DF |  | 0 | 417762.5 | 0 | 0 |  | 2275331 | 6811
2022-08-01 | ZIONS/PRT RTNG GAX FC202208016583 | DF |  | 0 | 21987.5 | 0 | 0 |  | 2275331 | 6811
2022-08-11 | ARCHI NEXUS GAX FC202208116964 | DF |  | 0 | 2044.8 | 0 | 0 |  | 2171174 | 6861
2022-08-19 | WC3 GAX 23C5*006 PLAN REVIEW 7/22 | DF |  | 0 | 440 | 440 | 0 |  |  | 6861
2022-08-19 | IDT TRNSF FUNDS FROM CONTG RESERVE FOR INSPECTION COSTS | DF | 1409.47 | 1409.47 |  | 0 | 1409.47 |  |  | 4664
2022-09-12 | PRT BUILDERS GAX FC202209128015 | DF |  | 0 | 246050 | 0 | 0 |  | 2275331 | 6811
2022-09-12 | ZIONS/PRT RTNG GAX FC202209128016 | DF |  | 0 | 12950 | 0 | 0 |  | 2275331 | 6811
2022-09-15 | ARCHI NEXUS GAX FC202209158311 | DF |  | 0 | 1652.04 | 0 | 0 |  | 2171174 | 6861
2022-10-03 | PRT BUILDERS GAX FC202210039138 | DF |  | 0 | 265667.5 | 0 | 0 |  | 2275331 | 6811
2022-10-03 | ZIONS/PRT BUILDERS RTNG GAX FC202210039139 | DF |  | 0 | 13982.5 | 0 | 0 |  | 2275331 | 6811
2022-10-05 | IET150230327800010506 TECH HOURLY RATE | DF |  | 0 | 214.2 | 214.2 | 0 |  |  | 68536
2022-10-20 | ARCHI NEXUS GAX FC202210209825 | DF |  | 0 | 3685.32 | 0 | 0 |  | 2171174 | 6861
2022-10-20 | IET1502304B2970000091 PRC AMER TECH RQ151942 LABOR | DF |  | 0 | 1125 | 1125 | 0 |  |  | 6853
2022-10-20 | IDT TRNSF FUNDS FROM CONTG RESERVE 21138300 FOR DTS COSTS | DF | 1339.2 | 1339.2 |  | 0 | 1339.2 |  |  | 4664
2022-10-27 | SHUMS CODA GAX FC2022102610061 | DF |  | 0 | 1658.81 | 1658.81 | 0 |  |  | 6873
2022-10-27 | PRT BUILDERS GAX FC2022102710190 | DF |  | 0 | 239011.45 | 0 | 0 |  | 2275331 | 6811
2022-10-27 | ZIONS/PRT RTNG GAX FC2022102710191 | DF |  | 0 | 12579.55 | 0 | 0 |  | 2275331 | 6811
2022-11-01 | IDT TRNSF FUNDS FROM CONTG RESERVE 21138300 FOR INSPECTION | DF | 1633.43 | 1633.43 |  | 0 | 1633.43 |  |  | 4664
2022-11-18 | SHUMS CODA GAX FC2022111811151 | DF |  | 0 | 952.42 | 952.42 | 0 |  |  | 6873
2022-11-21 | ARCHI NEXUS GAX FC2022112111246 | DF |  | 0 | 2922.84 | 0 | 0 |  | 2171174 | 6861
2022-12-05 | IET150230533900010254 TECH HOURLY RATE | DF |  | 0 | 1071 | 1071 | 0 |  |  | 6853
2022-12-08 | PRT BUILDERS GAX FC2022120812099 | DF |  | 0 | 183235.46 | 0 | 0 |  | 2275331 | 6811
2022-12-08 | ZIONS/PRT RTNG GAX FC202212082100 | DF |  | 0 | 9643.97 | 0 | 0 |  | 2275331 | 6811
2022-12-20 | SHUMS CODA ASSOC GAX FC2022122012568 | DF |  | 0 | 312 | 312 | 0 |  |  | 6873
2023-01-04 | IET150230600400010245 TECH HOURLY RATE | DF |  | 0 | 1570.8 | 1570.8 | 0 |  |  | 6853
2023-01-04 | PRT BUILDERS GAX FC2023010413128 | DF |  | 0 | 12545.7 | 0 | 0 |  | 2275331 | 6811
2023-01-04 | ZIONS/PRT BLDRS RTNG GAX FC2023010413129 | DF |  | 0 | 660.3 | 0 | 0 |  | 2275331 | 6811
2023-01-10 | SHUMS CODA GAX FC2023011013357 | DF |  | 0 | 429 | 429 | 0 |  |  | 6873
2023-01-10 | IDT TRNSF FUNDS FROM CONTG RESERVE 21138300 FOR CO 003 AND IT AND INSPECTION COSTS | DF | 41362.22 | 41362.22 |  | 0 | 41362.22 |  |  | 4664
2023-01-19 | PRT BUILDERS CO 003 | CO |  | 0 |  | 37027 | 0 |  | 2275331
2023-01-18 | IET1502307B0180000072 PRC AMER TECH | DF |  | 0 | 4332.86 | 4332.86 | 0 |  |  | 6853
2023-01-18 | IDT TRNSF FUNDS FROM CONTG RESERVE 21138300 FOR DTS COSTS | DF | 4332.86 | 4332.86 |  | 0 | 4332.86
2023-02-08 | ARCHI NEXUS GAX300FC2023020714602 | DF |  | 0 | 4725 | 0 | 0 |  | 2171174 | 6861
2023-02-06 | PRT BUILDERS LLC GAX 300FC2023020314409 | DF |  | 0 | 35007.12 | 0 | 0 |  | 2275331 | 6811
2023-02-06 | ZIONS/RTNG PRT BLDRS GAX 300FC2023020314410 | DF |  | 0 | 2019.88 | 0 | 0 |  | 2275331 | 6811
2023-02-13 | SHUMS CODA GAX FC2023021314853 | DF |  | 0 | 288.6 | 288.6 | 0 |  |  | 6873
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'25 |  |  |  | 0 |  | 0 | 0
2024-08-22 | IDT 25C3*019 TRNSF TO 21137300 PRO RES FROM 22035520 | DF | 288.6 | 288.6 |  | 0 | 288.6 |  |  | 4666
13/24 | IDT 24C3*400 TRNSF TO 22035520 FROM 21137300 PRO RES |  | 288.6 | 288.6 |  | 0 | 288.6 |  |  | 4666
13/24 | IDT 24C3*400 TRNSF TO 22035520 FROM 21137300 PRO RES |  | 288.6 | 288.6 |  | 0 | 288.6 |  |  | 4666
2024-12-27 | REMOVE DUPLICATE IDT 24C3*400 PORJECT 22035520 | EH | -288.6 | -288.6 |  | 0 | -288.6 |  |  | 4666
2024-12-27 | REMOVE DUPLICATE IDT 25C3*019 PROJECT 22035520 | EH | -288.6 | -288.6 |  |  | -288.6 |  |  | 4666
2026-07-14 | IDT15026DP000212 Americom Refund |  |  | 0 | -18.39 | -18.39 | 0 |  |  | 6481
| PROJECT CLOSED |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 22035520
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency