## PROJECT
RESERVES:
| DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT | [5 empty] | CONSTR
| FUNDING |  | GFFY2024 |  |  |  | DESIGN
| STATE RISK NUMBER |  | 00000 |  |  |  | INSPECTION
| PROJECT TITLE |  | DWR NEW LOA FISH HATCHERY BUILDING |  |  |  | INSURANCE
| PROJECT # |  | 24204520 | OPEN |  |  | CONTINGENCY/LEGAL
| CODING BLOCK |  | 3000-300-3347-FWCAA-24204520 |  |  | 23530951.78 | TOTAL | 0
|  |  |  | CASH ON |  |  |  | TREASURY | CONT | OBJ
| DESCRIPTION |  | RECEIPTS | HAND | PAYMENTS | ENCUMB | UNENCUMB | RECEIPTS | # | # | RE's | EST REV
YR | CURRENT TOTALS |  | 56854374.1 | 30866079.94 | 25988294.16 | 49519245.94 | 7335128.16 | 0 |  |  |  | 0
0
|  |  |  | 0 |  | 0 | 0
FY'24 |  |  |  | 0 |  | 0 | 0
2023-09-01 | PBIET150240822312110691 CAFÉ ZUPAS | DF |  | 0 | 77.9 | 77.9 | 0 |  |  | 6879
2023-09-18 | SUNRISE ENGINEERING INC - CONTRACT | N/A |  | 0 |  | 3123399 | 0 |  | 2470114
2023-12-26 | SUNRISE ENG GAX FC2023122629496 | DF |  | 0 | 10814 | 0 | 0 |  | 2470114 | 6861
2023-12-26 | SUNRISE ENG GAX FC2023122629497 | DF |  | 0 | 45380.68 | 0 | 0 |  | 2470114 | 6861
2023-12-26 | SUNRISE ENG GAX FC2023122629498 | DF |  | 0 | 32976.24 | 0 | 0 |  | 2470114 | 6861
2024-01-03 | BUDGETED CD CONTINGENCY - 24204520 | DF | -1972508 | -1972508 |  | 0 | -1972508 |  |  | 4663
2024-01-09 | PBIET150241234608170225 USGS - RMS | DF |  | 0 | 529.75 | 529.75 | 0 |  |  | 6861
2024-01-26 | HILL WEST ENVIRONMENTAL LLC - CONTRACT | N/A |  | 0 |  | 90750 | 0 |  | 2470288
2024-01-30 | SUNRISE ENG GAX FC2024013031148 | DF |  | 0 | 17465.4 | 0 | 0 |  | 2470114 | 6861
2024-02-05 | TRNSF FY24 CAP DEV FUNDS TO 24204520 FROM 24376300 SB 2 Item 45 | DF | 56843000 | 56843000 |  | 0 | 56843000 |  |  | 4667
2024-02-08 | HILL WEST ENVIRO GAX FC2024040831614 | DF |  | 0 | 17041.87 | 0 | 0 |  | 2470288 | 6819
2024-03-11 | WC3 PLAN REVIEW GAX 24C5*221 | DF |  | 0 | 875 | 875 | 0 |  |  | 6861
2024-03-14 | UT ST FIRE MARSHAL GAX 24C5*230 | DF |  | 0 | 75 | 75 | 0 |  |  | 6861
2024-03-19 | HARWARD & REES - CONTRACT | N/A |  | 0 |  | 594305 | 0 |  | 2475344
2024-04-17 | THERMAL WEST INDUSTRIAL INC - CONTRACT | N/A |  | 0 |  | 193640 | 0 |  | 2475406
2024-04-26 | ITA 24*121 COFC INS | DF |  | 0 | 594.31 | 594.31 | 0 |  |  | 6872
2024-05-07 | HILL WEST ENVIRO GAX FC204050735835 | DF |  | 0 | 6020.82 | 0 | 0 |  | 2470288 | 6819
2024-05-13 | SUNRISE ENG GAX FC2024051336077 | DF |  | 0 | 166173.5 | 0 | 0 |  | 2470114 | 6861
2024-05-13 | SUNRISE ENG GAX FC2024051336078 | DF |  | 0 | 225744.52 | 0 | 0 |  | 2470114 | 6861
2024-05-23 | HARWARD & REES GAX FC2024052336683 | DF |  | 0 | 81666.27 | 0 | 0 |  | 2475344 | 6811
2024-05-23 | ZIONS/HARWARD REES RTNG GAX FC2024052336684 | DF |  | 0 | 4298.23 | 0 | 0 |  | 2475344 | 6811
2024-05-24 | CALVIN L WADSWORTH CONSTRUCTION LLC - CONTRACT | N/A |  | 0 |  | 830908.61 | 0 |  | 2475483
2024-06-11 | THERMAL WEST INDUS GAX FC2024061137710 | TR |  | 0 | 70363.93 | 0 | 0 |  | 2475406 | 6819
2024-06-11 | ZONS/THERMAL WEST RTNG GAX FC2024061137711 | TR |  | 0 | 3703.37 | 0 | 0 |  | 2475406 | 6819
2024-06-13 | SUNRISE ENG GAX FC2024061337904 | TR |  | 0 | 51706.95 | 0 | 0 |  | 2470114 | 6861
2024-06-13 | SUNRISE ENG GAX FC2024061337914 | TR |  | 0 | 103174.37 | 0 | 0 |  | 2470114 | 6861
2024-06-14 | HILL WEST GAX FC2024061437970 | TR |  | 0 | 7717 | 0 | 0 |  | 2470288 | 6819
2024-06-25 | THERMAL WEST CO 001 | CO |  | 0 |  | 4864 | 0 |  | 2475406
13/24 | SUNRISE ENG GAX FC2024071539897 | TR |  | 0 | 120423 | 0 | 0 |  | 2470114 | 6861
13/24 | HARWARD & REES GAX FC2024071539955 | TR |  | 0 | 94610.02 | 0 | 0 |  | 2475344 | 6811
13/24 | ZIONS/HARWARD REES RTNG GAX FC2024071539956 | TR |  | 0 | 4979.48 | 0 | 0 |  | 2475344 | 6811
13/24 | HARWARD & REES GAX FC2024071539957 | TR |  | 0 | 57401.85 | 0 | 0 |  | 2475344 | 6811
13/24 | ZIONS/HARWARD REES RTNG GAX FC2024071539958 | TR |  | 0 | 3021.15 | 0 | 0 |  | 2475344 | 6811
13/24 | THERMAL WEST GAX FC2024071740094 | TR |  | 0 | 109245.82 | 0 | 0 |  | 2475406 | 6819
13/24 | ZIONS/THERMAL WEST RTNG GAX FC2024071740095 | TR |  | 0 | 5749.78 | 0 | 0 |  | 2475406 | 6819
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FY'25 |  |  |  | 0 |  | 0 | 0
2024-07-31 | JAMES VIERRA GAX F24*012 | DF |  | 0 | 1754.3 | 1754.3 | 0 |  |  | 6873
2024-08-07 | CALVIN WADSWORTH GAX FC2024080740819 | DF |  | 0 | 234633.85 | 0 | 0 |  | 2475483 | 6811
2024-08-07 | ZIONS/CALVIN WADSWORTH RTNG GAX FC2024080740820 | DF |  | 0 | 12349.15 | 0 | 0 |  | 2475483 | 6811
2024-08-09 | SUNRISE ENG GAX FC2024080940882 | DF |  | 0 | 121783.93 | 0 | 0 |  | 2470114 | 6861
2024-08-19 | ITA 25*007 COFC INS | DF |  | 0 | 830.91 | 830.91 | 0 |  |  | 6872
2024-08-23 | HARWARD & REES GAX FC2024082341515 | DF |  | 0 | 177421.05 | 0 | 0 |  | 2475344 | 6811
2024-08-23 | ZIONS/HARWARD RTNG GAX FC2024082341516 | DF |  | 0 | 9337.95 | 0 | 0 |  | 2475344 | 6811
2024-08-06 | IDT 25C3*006 XFER LEGAL FEES TO 21257300 | DF |  | 0 | 21917 | 21917 | 0 |  |  | 6870
2024-09-11 | CALVIN WADSWORTH GAX FC2024091142289 | DF |  | 0 | 258257.43 | 0 | 0 |  | 2475483 | 6811
2024-09-11 | ZIONS/WADSWORTH RTNG GAX FC2024091142290 | DF |  | 0 | 13592.5 | 0 | 0 |  | 2475483 | 6811
2024-09-12 | JAMES VIERRA GAX FC2024091242323 | DF |  | 0 | 2047.55 | 2047.55 | 0 |  |  | 6873
2024-09-19 | HARWARD & REES CO 001 | CO |  | 0 |  | 158070.45 | 0 |  | 2475344
2024-09-19 | SUNRISE ENG GAX FC2024091942745 | DF |  | 0 | 256027.93 | 0 | 0 |  | 2470114 | 6861
2024-10-03 | HILL WEST GAX FC2024100343510 | DF |  | 0 | 5541 | 0 | 0 |  | 2470288 | 6819
2024-10-03 | HILL WEST GAX FC2024100343511 | DF |  | 0 | 6083.1 | 0 | 0 |  | 2470288 | 6819
2024-10-03 | CALVIN WADSWORTH GAX FC2024100343521 | DF |  | 0 | 230292.35 | 0 | 0 |  | 2475483 | 6811
2024-10-03 | ZIONS/WADSWORTH RTNG GAX FC2024100343522 | DF |  | 0 | 12120.65 | 0 | 0 |  | 2475483 | 6811
2024-10-08 | SUNRISE ENG GAX FC2024100843719 | DF |  | 0 | 286204.51 | 0 | 0 |  | 2470114 | 6861
2024-10-23 | HARDWARD & REES GAX FC2024102344393 | DF |  | 0 | 178377.65 | 0 | 0 |  | 2475344 | 6811
2024-10-23 | ZIONS/HARDWARD REES RTNG GAX FC2024102344394 | DF |  | 0 | 9388.3 | 0 | 0 |  | 2475344 | 6811
2024-11-01 | TRNSF TO 24204520 FROM 21139300 RETURN PROJ CONTINGENCY | DF | 1972508 | 1972508 |  | 0 | 1972508
2024-11-04 | CALVIN WADSWORTH GAX FC2024110444855 | DF |  | 0 | 66179.55 | 0 | 0 |  | 2475483 | 6811
2024-11-04 | ZIONS/CALVIN WADSWORTH RTNG GAX FC2024110444856 | DF |  | 0 | 3483.13 | 0 | 0 |  | 2475483 | 6811
2024-11-15 | SUNRISE ENG GAX FC2024111545448 | DF |  | 0 | 251589.63 | 0 | 0 |  | 2470114 | 6861
2024-11-15 | THERMAL WEST CO 002 | CO |  | 0 |  | 14772 | 0 |  | 2475406
2024-11-20 | UT ST FIRE MARSHAL GAX 25C5*059 | DF |  | 0 | 75 | 75 | 0 |  |  | 6873
2024-12-02 | WC3 PLAN REVIEW GAX 25C5*068 | DF |  | 0 | 250 | 250 | 0 |  |  | 6873
2024-12-10 | SUNRISE ENG GAX FC202412104568 | EH |  | 0 | 195091.22 | 0 | 0 |  | 2470114 | 6861
2024-12-12 | HARWARD & REES CO 002 | CO |  | 0 |  | 187551.92 | 0 |  | 2475344
2024-12-12 | CALVIN WADSWORTH CO 001 | CO |  | 0 |  | 3798.5 | 0 |  | 2475483
2024-12-20 | TRNSF TO 24204520 FROM 22309300 HAZMAT | EH | 11374.1 | 11374.1 |  | 0 | 11374.1 |  |  | 4654
2024-12-19 | HARWARD & REES GAX FC2024121947015 | EH |  | 0 | 268756.82 | 0 | 0 |  | 2475344 | 6811
2024-12-19 | ZIONS/HARWARD RTNG GAX FC2024121947016 | EH |  | 0 | 14145.1 | 0 | 0 |  | 2475344 | 6811
2025-01-10 | CALVIN L WADSWORTH CONST GAX300FC2025011047946 | EH |  | 0 | 3608.57 | 0 | 0 |  | 2475483 | 6811
2025-01-10 | ZIONS/ CALVIN L WADSWORTH CONST RTNG GAX300FC2025011047947 | EH |  | 0 | 189.93 | 0 | 0 |  | 2475483 | 6811
2025-01-15 | SUNRISE ENGIN. GAXFC2025011548132 | EH |  | 0 | 125380.95 | 0 | 0 |  | 2470114 | 6861
2025-02-02 | True Grit Construction, Inc. - CONTRACT | CO |  | 0 |  | 881075.68 | 0 |  | 2575380
2025-02-11 | JAMES VIERRA GAX300FC2025021149424 | HH |  | 0 | 487.98 | 487.98 | 0 |  |  | 6873
2025-02-11 | JAMES VIERRA GAX300FC2025021149426 | HH |  | 0 | 393.38 | 393.38 | 0 |  |  | 6873
2025-03-04 | SUNRISE ENGIN. GAX300FC2025030450328 | HH |  | 0 | 170981.78 | 0 | 0 |  | 2470114 | 6861
2025-02-11 | SUNRISE ENGINEERING AMD 001 | CO |  | 0 |  | 6129 | 0 |  | 2470114
2025-03-19 | SUNRISE ENGINEERING AMD 002 | CO |  | 0 |  | 65788 | 0 |  | 2470114
2025-04-15 | HARWARD & REES CO 003 | CO |  | 0 |  | 26353.75 | 0 |  | 2475344
2025-04-15 | True Grit Construction, Inc. GAX300FC2025041552324 | HH |  | 0 | 85680.69 | 0 | 0 |  | 2575380 | 6811
2025-04-15 | True Grit Construction, Inc. GAX300FC2025041552325 | HH |  | 0 | 4509.51 | 0 | 0 |  | 2575380 | 6811
2025-04-22 | SUNRISE ENGINEERING LLC GAX300FC2025042252629 | HH |  | 0 | 49780.6 | 0 | 0 |  | 2470114 | 6861
2025-04-24 | ITA3002500000080 | HH |  | 0 | 1894.31 | 1894.31 | 0 |  |  | 6872
2025-05-02 | True Grit Construction, Inc. GAX300FC2025050253179 | HH |  | 0 | 176919.92 | 0 | 0 |  | 2575380 | 6811
2025-05-02 | True Grit Construction, Inc. GAX300FC2025050253180 | HH |  | 0 | 9311.57 | 0 | 0 |  | 2575380 | 6811
2025-05-02 | HARWARD AND REES GAX300FC2025050253181 | HH |  | 0 | 59733.39 | 0 | 0 |  | 2475344 | 6811
2025-05-02 | HARWARD AND REES GAX300FC2025050253182 | HH |  | 0 | 3143.86 | 0 | 0 |  | 2475344 | 6811
2025-05-06 | SHUMS CODA ASSOCIATES INC GAX300FC2025050653265 | HH |  | 0 | 2328.7 | 2328.7 | 0 |  |  | 6873
2025-05-15 | WARREN WATER BROOM - CONTRACT | CO |  | 0 |  | 46400 | 0 |  | 2575488
2025-05-27 | UTAH STATE FIRE MARSHAL'S OFFICE GAX30025C5000143 GENERAL BUILDING FIRE PLANS - 25-350- 04-24-2025 | HH |  | 0 | 2321.92 | 2321.92 | 0 |  |  | 6873
2025-06-03 | SUNRISE ENGINEERING LLC GAX300FC2025060254597 CONTRACT 2470114 - NEW LOA FISH HATCHERY DESIGN | HH |  | 0 | 25709 | 0 | 0 |  | 2470114 | 6861
2025-06-05 | SUNRISE ENGINEERING LLC GAX300FC2025060454743 CONTRACT 2470114 - NEW LOA FISH HATCHERY DESIGN | HH |  | 0 | 83246.72 | 0 | 0 |  | 2470114 | 6861
2025-06-12 | True Grit Construction, Inc. GAX300FC2025061155207 CONTRACT 2575380-PAY APP #3-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 213626.92 | 0 | 0 |  | 2575380 | 6811
2025-06-12 | True Grit Construction, Inc. GAX300FC2025061155208 CONTRACT 2575380-PAY APP #3-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 11243.52 | 0 | 0 |  | 2575380 | 6811
2025-06-12 | THERMAL WEST INDUSTRIAL, INC GAX300FC2025061155220 CONTRACT 2475406-PAY APP#3-LOA FISH HATCHERY ABATEMENT | HH |  | 0 | 23002.44 | 0 | 0 |  | 2475406 | 6819
2025-06-12 | THERMAL WEST INDUSTRIAL, INC GAX300FC2025061155221 CONTRACT 2475406-PAY APP#3-LOA FISH HATCHERY ABATEMENT | HH |  | 0 | 1210.66 | 0 | 0 |  | 2475406 | 6819
2025-06-13 10:21 | TRUE GRIT CO 001 | CO |  | 0 |  | 2426.7 | 0 |  | 2575380
2025-06-26 | WEST COAST CODE CONSULTANTS INC GAX30025C5000158 Plan Review Services 05/05/2025-1ST REVIEW | HH |  | 0 | 1125 | 1125 | 0 |  |  | 6873
2025-06-26 | WEST COAST CODE CONSULTANTS INC GAX30025C5000158 Plan Review Services 05/14/2025-PHONE CALL(S) | HH |  | 0 | 125 | 125 | 0 |  |  | 6873
2025-06-26 | SHUMS CODA ASSOCIATES INC GAX300FC2025062555719 TESTING AND INSPECTION SERVICES | HH |  | 0 | 5839.3 | 5839.3 | 0 |  |  | 6873
2025-06-26 | SUNRISE ENGINEERING LLC GAX300FC2025062555770 CONTRACT 2470114 - NEW LOA FISH HATCHERY DESIGN | HH |  | 0 | 30219.53 | 0 | 0 |  | 2470114 | 6861
13/25 | GARKANE ENERGY COOPERATIVE INC GAX300FC2025070156107 PO 237003-DSGN/INSTALL-PWR TO RNGR HSES & PRELIM WRK MN BLDG | HH |  | 0 | 29756.44 | 29756.44 | 0 |  |  | 6879
13/25 | SUNRISE ENGINEERING LLC GAX300FC2025070156128 CONTRACT 2470114 - NEW LOA FISH HATCHERY DESIGN | HH |  | 0 | 15322.7 | 0 | 0 |  | 2470114 | 6861
13/25 | True Grit Construction, Inc. GAX300FC2025070256306 CONTRACT 2575380-PAY APP #4-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 155735.49 | 0 | 0 |  | 2575380 | 6811
13/25 | True Grit Construction, Inc. GAX300FC2025070256307 CONTRACT 2575380-PAY APP #4-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 8196.61 | 0 | 0 |  | 2575380 | 6811
13/25 | SHUMS CODA ASSOCIATES INC GAX300FC2025071557032 237486-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 2272.38 | 2272.38 | 0 |  |  | 6873
13/25 | WC3 CONSULTANTS GAX30025C5000160 | TR |  | 0 | 875 | 875 | 0 |  |  | 6873
FY'26
2025-08-09 | True Grit Construction, Inc. GAX300FC2025080857924 CONTRACT 2575380-PAY APP #5-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 131393.88 | 0 | 0 |  | 2575380 | 6811
2025-08-09 | True Grit Construction, Inc. GAX300FC2025080857925 CONTRACT 2575380-PAY APP #5-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 6915.47 | 0 | 0 |  | 2575380 | 6811
2025-08-12 | SHUMS CODA ASSOCIATES INC GAX300FC2025081157933 237882-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 322.48 | 322.48 | 0 |  |  | 6873
2025-08-18 | TRUE GRIT CO 002 | CO |  | 0 |  | -7537.89 | 0 |  | 2575380
2025-08-28 | 24204520 DWR NEW LOA FISH HATCHERY BUILDING ITA5602600000168 | HH |  | 0 | 621.92 | 621.92 | 0 |  |  | 6811
2025-08-28 | 24204520 DWR NEW LOA FISH HATCHERY BUILDING ITA5602600000169 | HH |  | 0 | 621.92 | 621.92 | 0 |  |  | 6811
2025-08-29 | ITA5602600000142 24204520 DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | -621.92 | -621.92 | 0 |  |  | 6811
2025-09-04 | FREMONT WATERWORKS COMPANY GAX300FC2025090358892 PO 238333-WATER METER CONNECTION/INSTALL FEE-LOA FISH HATCHERY | HH |  | 0 | 9100 | 9100 | 0 |  |  | 6811
2025-09-17 | MACS TECH LLC GAX300FC2025091659504 PO 239264-PORTABLE ONSITE SECURITY CAMERAS TO MONITOR PROP | HH |  | 0 | 5100 | 5100 | 0 |  |  | 6879
2025-09-19 | PROFESSIONAL TITLE, LLC GAX300FC2025091859600 PO 239439-TITLE WORK - LOA FISH HATCHERY | HH |  | 0 | 1300 | 1300 | 0 |  |  | 6861
2025-09-18 | SUNRISE ENGINEERING LLC GAX300FC2025091759561 CONTRACT 2470114 - NEW LOA FISH HATCHERY DESIGN | HH |  | 0 | 7454.05 | 0 | 0 |  | 2470114 | 6861
2025-09-18 | Roger R. Warren GAX300FC2025091759582 CONTRACT 2575488-WATER SPIKE WS250 ADAPTED FOR 2PUMP-FIT WITH CLEAN OUT. FLEX HOSE2CAM LOCK FITTI | HH |  | 0 | 46400 | 0 | 0 |  | 2575488 | 6832
2025-09-18 | True Grit Construction, Inc. GAX300FC2025091759589 CONTRACT 2575380-PAY APP #6-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 53033.08 | 0 | 0 |  | 2575380 | 6811
2025-09-18 | True Grit Construction, Inc. GAX300FC2025091759590 CONTRACT 2575380-PAY APP #6-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 2791.22 | 0 | 0 |  | 2575380 | 6811
2025-09-17 | TRUE GRIT CO 003 | CO |  | 0 |  | 7160.31 | 0 |  | 2575380
2025-10-09 | SUNRISE ENGINEERING LLC GAX300FC2025100860576 CONTRACT 2470114 - NEW LOA FISH HATCHERY DESIGN | HH |  | 0 | 30047.2 | 0 | 0 |  | 2470114 | 6861
2025-10-09 | True Grit Construction, Inc. GAX300FC2025100860603 CONTRACT 2575380-PAY APP #7-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 7780.79 | 0 | 0 |  | 2575380 | 6811
2025-10-09 | True Grit Construction, Inc. GAX300FC2025100860604 CONTRACT 2575380-PAY APP #7-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 409.52 | 0 | 0 |  | 2575380 | 6811
2025-10-16 | Hill West Environmental LLC GAX300FC2025101560854 CONTRACT 2470288 LOA FISH HATCHERY | HH |  | 0 | 5072 | 0 | 0 |  | 2470288 | 6819
2025-10-23 | FREMONT WATERWORKS COMPANY GAX300FC2025102261099 PO 240331-DWR NEW LOA FISH HATCHERY WATER RIGHTS | HH |  | 0 | 20000 | 20000 | 0 |  |  | 6811
2025-11-07 | CENTRAL UTAH PUBLIC HEALTH DPT GAX300FC2025110661733 PO 240634-SEPTIC PERMIT LOA FISH HATCHERY | HH |  | 0 | 500 | 500 | 0 |  |  | 6811
2025-11-20 | SUNRISE ENGINEERING LLC GAX300FC2025111962321 CONTRACT 2470114 - NEW LOA FISH HATCHERY DESIGN | HH |  | 0 | 20180.9 | 0 | 0 |  | 2470114 | 6861
2025-12-03 | True Grit Construction, Inc. GAX300FC2025120262839 CONTRACT 2575380-PAY APP #9-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 113035.89 | 0 | 0 |  | 2575380 | 6811
2025-12-03 | True Grit Construction, Inc. GAX300FC2025120262840 CONTRACT 2575380-PAY APP #9-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 5949.26 | 0 | 0 |  | 2575380 | 6811
2025-12-05 | MACS TECH LLC GAX300FC2025120462956 PO 241508-DNR /DWR LOA FISH HATCHERY | HH |  | 0 | 3850 | 3850 | 0 |  |  | 6879
2025-11-26 | Phaze Concrete Inc CONTRACT | CO |  | 0 |  | 40469398.1 | 0 |  | 2675225
2025-11-28 | TRUE GRIT CO 005 | CO |  | 0 |  | 3234.06 | 0 |  | 2575380
2025-11-28 | TRUE GRIT CO 004 | CO |  | 0 |  | 171538.56 | 0 |  | 2575380
2025-12-24 | Phaze Concrete Inc GAX300FC2025122363778 CONTRACT 2675225-PAY APP #1-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 379797.89 | 0 | 0 |  | 2675225 | 6811
2025-12-24 | Phaze Concrete Inc GAX300FC2025122363779 CONTRACT 2675225-PAY APP #1-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 19989.36 | 0 | 0 |  | 2675225 | 6811
2025-12-23 | SUNRISE ENGINEERING LLC GAX300FC2025122263729 CONTRACT 2470114 - NEW LOA FISH HATCHERY DESIGN | HH |  | 0 | 12807.66 | 0 | 0 |  | 2470114 | 6861
2026-10-14 | HILL WEST AMD 001 | CO |  | 0 |  | -43274.21 | 0 |  | 2470288
2026-02-03 | Phaze Concrete Inc GAX300FC2026020265434 CONTRACT 2675225-PAY APP #2-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 928191.8 | 0 | 0 |  | 2675225 | 6811
2026-02-03 | Phaze Concrete Inc GAX300FC2026020265435 CONTRACT 2675225-PAY APP #2-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 48852.2 | 0 | 0 |  | 2675225 | 6811
2026-02-03 | SUNRISE ENGINEERING LLC GAX300FC2026020265398 CONTRACT 2470114 - NEW LOA FISH HATCHERY DESIGN | HH |  | 0 | 8570.66 | 0 | 0 |  | 2470114 | 6861
2026-02-11 | SHUMS CODA ASSOCIATES INC GAX300FC2026021065862 PO 241524-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 1051.4 | 1051.4 | 0 |  |  | 6873
2026-02-11 | SHUMS CODA ASSOCIATES INC GAX300FC2026021065863 243541-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 1052.8 | 1052.8 | 0 |  |  | 6873
2026-02-13 | True Grit Construction, Inc. GAX300FC2026021266025 CONTRACT 2575380-PAY APP #10-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 40765.09 | 0 | 0 |  | 2575380 | 6811
2026-02-13 | True Grit Construction, Inc. GAX300FC2026021266026 CONTRACT 2575380-PAY APP #10-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 2145.53 | 0 | 0 |  | 2575380 | 6811
2026-02-18 | SUNRISE ENGINEERING LLC GAX300FC2026021766108 CONTRACT 2470114 - NEW LOA FISH HATCHERY DESIGN | HH |  | 0 | 33581.73 | 0 | 0 |  | 2470114 | 6861
2026-02-13 | TRUE GRIT CO 006 | CO |  | 0 |  | -6620.98 | 0 |  | 2575380
2026-03-17 | Phaze Concrete Inc GAX300FC2026031667486 CONTRACT 2675225-PAY APP #3-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 1520190 | 0 | 0 |  | 2675225 | 6811
2026-03-17 | Phaze Concrete Inc GAX300FC2026031667487 CONTRACT 2675225-PAY APP #3-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 80010 | 0 | 0 |  | 2675225 | 6811
2026-03-24 | BGT PARTNERS LLC GAX300FC2026032367731 PO 244728-LOA FISH HATCHERY SPECIAL INSPECTION SERVICES | HH |  | 0 | 10939.65 | 10939.65 | 0 |  |  | 6873
2026-04-02 | Phaze Concrete Inc GAX300FC2026040168124 CONTRACT 2675225-PAY APP #4-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 2821110.5 | 0 | 0 |  | 2675225 | 6811
2026-04-02 | Phaze Concrete Inc GAX300FC2026040168125 CONTRACT 2675225-PAY APP #4-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 148479.5 | 0 | 0 |  | 2675225 | 6811
2026-04-04 | GARKANE ENERGY COOPERATIVE INC GAX300FC2026040368224 PO 245035-NEW LOA FISH HATCHERY MAIN POWER TRANSFORMER-UTILITY | HH |  | 0 | 87143.88 | 87143.88 | 0 |  |  | 6811
2026-04-16 | GARKANE ENERGY COOPERATIVE INC GAX300FC2026041568649 PO 245270 - NEW LOA FISH HATCHERY UTILITY | HH |  | 0 | 52514.99 | 52514.99 | 0 |  |  | 6811
2026-04-16 | SUNRISE ENGINEERING LLC GAX300FC2026041568731 CONTRACT 2470114 - NEW LOA FISH HATCHERY DESIGN | HH |  | 0 | 89911.02 | 0 | 0 |  | 2470114 | 6861
2026-04-14 09:15 | Phaze Concrete CO 001 | CO |  | 0 |  | 19741.31 | 0 |  | 2675225
2026-04-14 09:28 | Phaze Concrete CO 002 | CO |  | 0 |  | 25225.71 | 0 |  | 2675225
2026-05-16 | SUNRISE ENGINEERING LLC GAX300FC2026051570058 CONTRACT 2470114 - NEW LOA FISH HATCHERY DESIGN | HH |  | 0 | 55417.34 | 0 | 0 |  | 2470114 | 6861
2026-05-15 | Phaze Concrete Inc GAX300FC2026051470043 CONTRACT 2675225-PAY APP #5-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 4077400 | 0 | 0 |  | 2675225 | 6811
2026-05-15 | Phaze Concrete Inc GAX300FC2026051470044 CONTRACT 2675225-PAY APP #5-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 214600 | 0 | 0 |  | 2675225 | 6811
2026-05-13 | UTAH STATE FIRE MARSHAL'S OFFICE GAX30026C5000098 FIRE ALARM PLANS - 25-215 - 03/12/2026 | HH |  | 0 | 238.17 | 238.17 | 0 |  |  | 6873
2026-05-22 | BGT PARTNERS LLC GAX300FC2026052170300 PO 246515-LOA FISH HATCHERY INSPECTIONS | HH |  | 0 | 16858.9 | 16858.9 | 0 |  |  | 6873
2026-05-28 | Phaze Concrete Inc GAX300FC2026052770570 CONTRACT 2675225-PAY APP #6-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 4423200 | 0 | 0 |  | 2675225 | 6811
2026-05-29 | SUNRISE ENGINEERING LLC GAX300FC2026052870584 CONTRACT 2470114 - NEW LOA FISH HATCHERY DESIGN | HH |  | 0 | 50216.01 | 0 | 0 |  | 2470114 | 6861
2026-05-28 | Phaze Concrete Inc GAX300FC2026052770571 CONTRACT 2675225-PAY APP #6-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 232800 | 0 | 0 |  | 2675225 | 6811
2026-07-09 | GAX300FC2026070972660 PO 248134-LOA FISH HATCHERY MAIN BLDGS T & I | HH |  | 0 | 21593.05 | 21593.05 | 0 |  |  | 6879
2026-07-08 | GAX300FC2026070872510 PO 247843-LOA FISH HATCHERY WATER METER CONNECTION FEE | HH |  | 0 | 10384.19 | 10384.19 | 0 |  |  | 6811
2026-07-08 | GAX300FC2026070872547 TESTING AND INSPECTION | HH |  | 0 | 15941 | 15941 | 0 |  |  | 6873
2026-07-07 | GAX30026C2000335 CONTRACT 2675225-PAY APP #7-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 2907000 | 0 | 0 |  | 2675225 | 6811
2026-07-07 | GAX30026C2000336 CONTRACT 2675225-PAY APP #7-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 153000 | 0 | 0 |  | 2675225 | 6811
2026-07-06 | GAX300FC2026070672410 PO 247844-LOA FISH HATCHERY INSPECTIONS | HH |  | 0 | 1095 | 1095 | 0 |  |  | 6873
2026-06-30 | GAX300FC2026063072204 CONTRACT 2470114 - NEW LOA FISH HATCHERY DESIGN | HH |  | 0 | 51286.23 | 0 | 0 |  | 2470114 | 6861
2026-06-19 | GAX300FC2026061971664 CONTRACT 2575380-PAY APP #12-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 20740.86 | 0 | 0 |  | 2575380 | 6811
2026-06-19 | GAX300FC2026061971665 CONTRACT 2575380-PAY APP #12-DWR NEW LOA FISH HATCHERY BUILDING | HH |  | 0 | 1091.62 | 0 | 0 |  | 2575380 | 6811
2026-06-11 | GAX30026C5000116 Plan Review Services 04/22/2026 - 1ST REVIEW | HH |  | 0 | 250 | 250 | 0 |  |  | 6873
2026-06-11 | GAX300FC2026061171254 CONTRACT 2470114 - NEW LOA FISH HATCHERY DESIGN | HH |  | 0 | 33963.43 | 0 | 0 |  | 2470114 | 6861
13/26 | BGT PARTNERS LLC GAX300FC2026071472896 CONTRACT 2670555 - DWR NEW LOA FISH HATCHERY BUILDING |  |  | 0 | 22619.5 | 22619.5 | 0 |  |  | 6873
2026-06-10 07:03 | SUNRISE ENGINEERING LLC AMD 003 | CO |  | 0 |  | 129850 | 0 |  | 2470114
FY'26 |  |  |  | 0 |  | 0 | 0
2026-07-07 | SPECTRUM BIOTECHNOLOGIES, LLC CONTRACT | CO |  | 0 |  | 424675.3 | 0 |  | 2675522
2026-08-04 | Phaze Concrete Inc GAX300FC2026080373583 CONTRACT 2675225-PAY APP #8-DWR NEW LOA FISH HATCHERY BUILDING |  |  | 0 | 1649865 | 1649865 | 0 |  |  | 6811
2026-08-04 | Phaze Concrete Inc GAX300FC2026080373584 CONTRACT 2675225-PAY APP #8-DWR NEW LOA FISH HATCHERY BUILDING |  |  | 0 | 86835 | 86835 | 0 |  |  | 6811
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0

## BUDGET
DIVISION OF FACILITIES CONSTRUCTION & MANAGEMENT
#REF!
| PROJECT # | 24204520
TOTALS TO
FUNDING: | BY SOURCE
XXXXX
XXXXX
XXXXX
XXXXX
XXXXX
TOTAL AVAILABLE FUNDING |  |  |  | 0 | 4433332.16
11419959.84
ENCUMBRANCES TO DATE: |  |  | BUDGET | ACTUAL | 15853292
DESIGN |  |  |  |  | 15853292
AGREEMENT # 1 |  |  | XXXXX
OTHER |  |  | XXXXX
OTHER |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
DESIGN CONTINGENCY - |  |  | XXXXX
SURVEY SERVICES |  |  |  | XXXXX
PROGRAM ANALYSIS |  |  |  | XXXXX
ENVIRONMENTAL - GEOTECHNICAL SERVICES |  |  |  | XXXXX
TRAVEL EXPENDITURES |  |  |  | XXXXX
RISK MANAGEMENT - CONSTRUCTION INSURANCE |  |  |  | XXXXX
MISC. EXPENDITURES |  |  |  | XXXXX
LIFE CYCLE COSTING |  |  | XXXXX
XXXXX
XXXXX
CONSTRUCTION |  |  | XXXXX
XXXXX
RESERVES:
FURNISHINGS |  |  | XXXXX | XXXXX
XXXXX
% FOR THE ARTS |  |  | XXXXX | XXXXX
MOVING/OCCUPANCY COSTS |  |  | XXXXX | XXXXX
TESTING & INSPECTION |  |  | XXXXX
TOTAL ENCUMBRANCES/BUDGET TO DATE |  |  | 0 | 0
UNENCUMBERED BALANCE TO DATE |  |  |  | 0
excess contingency